## Slide 1: SHA-2 Readiness and Plans
Maarten Litmaath
CERN
GDB, 2013-12-11

## Slide 2: Sites
Steadily upgrading remaining affected services to SHA-2 compliant versions
Main concern are Storage Elements
Nov 28 EGI OMB meeting:
  5 dCache, 7 StoRM still to be done
OSG:
  BNL  Dec 17
  FNAL  started, aiming to be ready in Dec

## Slide 3: Clients
dCache SRM client needs a newer version to be able to handle SHA-2 host certs!
Some CMS sites may have configured that client for their local staging operations
Some CMS users were using it recently
2.6.12 released on Dec 2 as part of EMI-3 Update 11
2.2.x update for EMI-2 is being prepared

## Slide 4: Experiments
Each of the experiments has tested a lot and not run into any showstoppers
  SHA-2 certs were obtained from the new CERN CA and registered in VOMS as secondary certificates
The experiments look ready for SHA-2

## Slide 5: Timelines
By mid January the WLCG infrastructure is expected to be essentially ready
  We may be able to ignore any remaining stragglers by the end of Jan
It is unlikely for SHA-2 certs to appear still this year
  The OSG CA foresees starting mid Jan
  The CERN CA will switch when WLCG is ready
    New SHA-1 certs get 6-month lifetime since Dec 1

## Slide 6: VOMRS
VOMRS does not support SHA-2 directly
  But secondary certs can be of SHA-2 type
It is to be replaced by VOMS-Admin
  With a different GUI and CLI for the experiments to adapt to
VOMS-Admin test setup is being prepared
  Loaded with VOMRS data a few weeks ago
  Configuration needed to be cleaned up
  VOMS-Admin instability being investigated