## Sheet1
Component	Lead	O(6Months) 1.8.8	O(1 year) 1.8.9	O(2 years)

Admin Tools	Lead: skipsey

		Enumerate the usages of dpns/dpm APIs	Use HTTP/DAV commands, not dpns
Bamboo Plugins	Lead: Martin Philipp Hellmich
		Hope that the mock plugin works
DMLITE ADAPTER	Lead: Fabrizio Furano

DMLITE CORE	Lead: Fabrizio Furano

DMLITE GRIDFTP	Lead: David Smith

DMLITE HDFS	Lead: Andrea Manzi
				Support high availability HDFS
			Dmlite acts as kerberos client towards HDFS
DMLITE LIBRARIAN	Lead: Fabrizio Furano

DMLITE MEMCACHE	Lead: Martin Philipp Hellmich

DMLITE MYSQL	Lead: Martin Philipp Hellmich

DMLITE ORACLE	Lead: Fabrizio Furano

DMLITE PROFILER	Lead: Fabrizio Furano
		1st round of extensions: avg values, activeMQ producer, (see with Dashboard people?)
DMLITE PYTHON	Lead: Ivan Calvet

DMLITE S3	Lead: Martin Philipp Hellmich

DMLITE SHELL	Lead: Ivan Calvet
		do pool configuration for the new (and legacy) pools
DMLITE SRM	Lead: David Smith

DMLITE VFS	Lead: Fabrizio Furano

DPM	Lead: Fabrizio Furano

DPM HTTPD	Lead: Alejandro Alvarez Ayllon

DPM Yaim	Lead: Oliver Keeble

External	Lead: Fabrizio Furano

Federations	Lead: Fabrizio Furano

Ganesha	Lead: Shu-Ting Liao

GRIDFTP	Lead: David Smith
		Redirection is released
LCGDM	Lead: Fabrizio Furano

LFC	Lead: Fabrizio Furano

LFC Yaim	Lead: Oliver Keeble

MSG	Lead: Fabrizio Furano

Nagios	Lead: Ivan Calvet

NFS	Lead: Shu-Ting Liao

Panda Pilot	Lead: Shu-Ting Liao

PerfSuite	Lead: Martin Philipp Hellmich
		support kerberos authentication
Puppet	Lead: Martin Philipp Hellmich
		add xrootd support	copy configuration from lcgdm to dmlite, using the dmlite shell do the setup of gridmaps, create vo directories, …. (dmlite config component by component (plugins, frontends)
Scripts	Lead: Fabrizio Furano

SRM	Lead: David Smith

WebDAV	Lead: Alejandro Alvarez Ayllon
		Implement PATCH		Kerberos?” Shibboleth?
XROOTD	Lead: David Smith

XrdHTTP	Lead: Fabrizio Furano
		First release (see document)

Dpm-drain HTTP		Internal prerelease for the collaboration	Release
Hot files replication			Internal prerelease for the collaboration
Drupal site		Investigate with Cath

TBD now
Test bed		Refurbish testbed
Mock stuff		Make mock config for building candidate-release that now is 1.8.7