## Slide 1: PROTOTYPE DEVELOPMENT ISSUES AND ACTIVITIES
Francisco García
Helsinki Institute of Physics – University of Helsinki

## Slide 2
2
Twin GEM-TPC BOX PRODUCTION and PROCUREMENT
GENERAL ISSUES
SUMMARY
OUTLINE

## Slide 3
Twin GEM-TPC BOX PRODUCTION and PROCUREMENTS
3
The box has:
1.- CNC machine too small at
Jyväskylä  outsourced
2.- Al 7000
3.- Weight 7 kg
4.- Alignment slit on walls
5.- Windows frames:
Al  Mylar
Stainless Steel  Vacuum
6.- Production  few weeks
7.- Price of brick  450 €
8.- KF flange adapter modify
9.- Handle will be change
10.- Tolerance of 100 will be match

## Slide 4: GENERAL ISSUES
4
Optical Images of foils are in progress and soon there will be ready a set of parameter per GEM
Leakage Current measurements are ready
GEM foils for the stack will be selected based on optical and leakage current criteria
Divider and Readout pad plane PCB are needed to start production the Test bench design and production
Capacitance measure setup will be adapt for the new Readout Pad plane characterization
Paper for the S417 beam test will be circulated soon: histogram source files are needed, the GEMEX operation will be described and conclusions are already presented in Waldorf meeting.

## Slide 5: SUMMARY
5
The Boxes will be ready soon: one to GSI and one at HIP within 4 weeks
The Readout pad plane will be outsourced from a company  Production between
6 – 8 weeks
Capacitance measurement for 4 readout pad planes PCBs  2 weeks expected
Filter PCBs are needed about 14 per detector  Production and test 4 weeks
 Top GEM foil filter with 10 Mohm
 Bottom GEM foil filter with 1 Mohm
Resistor divider 2 per field cage  Assembling and test at Comenious Univ.
Detector Flanges, design is ready  production within 4 weeks
External and Internal Cables  production within 2 weeks
Air and Vacuum windows  Production within 3 weeks