## Slide 1: Overview of SMACC-QA
Recall of SMACC-QA organization
Tuning the procedures
Main results from the QC teams
Auditors findings
Ranko Ostojic
23 July 2013

## Slide 2
Long Shutdown 1
F. Bordry
SMACC: J-Ph. Tock
Main arc splices consolidation
F. Savary
Open/Close IC & DN200
A. Musso
Sleeves cutting
Splice de/resoldering
BB surfacing
Shunt installation
Special interventions
N. Bourcey
Cryomagnets exchange
Connect. Cryostat cons.
PIMs
Specific issues
Heavy NC
Opening/ Closure of IC Partial and complete W bellows & ther. shields
Installation of DN200
Quality Assurance
R. Ostojic
Electrical QC: C Scheuerlein - Welding QC: JM Dalin
Beam vacuum QC: C Garion
Open/close IC QC: D Bodart
QA support
ELQA
K. Dahlerup
Continuity
HV test
Leak Tests
P. Cruikshank
Beam lines
Cryogenics lines
Insulation vacuum
Coordination, Support and Infrastructure
M. Pojer
Radiation protection
Safety
Access
Coordination with Survey, Instrumentation, Transport, LS1 planning, QPS, cryogenics,… Test teams on a chain of IC
Reporting tools
DFBA
A. Perin
Splices and BB
TIG welding
S. Atieh
- Orbital & manual

## Slide 3: SMACC-QA Organization
Production Inspections
Actor: Operators and supervisors
Level: Interconnection
Documents: IP for each activity
CERN Audit
Actor: Team of experienced CERN staff
Level: All
Documents: IPs, TPs, CERN rules
Quality Control
Actor: QC team
Level: Interconnection, Subsector
Documents: TP for each QC activity
QA Team
Actor: QA team
Level: All
Documents: IPs, TPs
Actions:
Review and decision on NCs and border-line cases
Follow-up of audits and production quality trends
Follow-up and timely completion of test reports and MTF entries

## Slide 4: QC Team Leaders
Ch. Scheuerlein
ELQC
J-M. Dalin
WELD
D. Bodart
C. Garion
ICIT
K. Dahlerup-Petersen
ELQA
VAC
P. Cruikshank

## Slide 5: SMACC-QA Team
Splice Consolidation Team Leader and Internal-QC Leader
Quality Control Team Leaders
F. Savary
R. Principe
D. Bodart
C. Garion
Ch. Scheuerlein
J-M. Dalin
K. Dahlerup-P
P. Cruikshank
S. Feher
R. Ostojic
M. Struik
J-P. Tock
M. Pojer
QA Support
SMACC Project Leader
and Coordination

## Slide 6: Experts
S. Atieh
F. Bertinelli
A. Verweij
ELQC
J-P. Brachet
G. Favre
WELD
A. Musso
V. Parma
ICIT
S. Le Naour
R. Mompo
ELQA
VAC
N. Kos
R. Kersevan

## Slide 7: CERN Auditors
G. Favre
S. Feher
P. Galbraith
M. Lamont
S. Mathot
R. Ostojic
M. Struik
H. Ten Kate
D. Tommasini
L. Williams

## Slide 8: Typical SMACC Workflow
Typically:
  “Production step n” paired with “QC step n”
The two activities performed by independent teams.
Coordination of activities through WISH.
Management of NCR through MTF.

## Slide 9: Decision Line
QA Team
Decision by Consensus
NCR opened in MTF
Actions and NCR Closure
Yes
Difficult case
Decision by RO and JPhT
No
Very high impact case
Decision by F. Bordry

## Slide 10: Informing and Reporting
Use of MTF tools:
  retrieval and analysis of NCRs,
  notification lists for informing relevant teams on creation and status of critical NCRs.
Regular SMACC-QA Team meetings, every Tuesday and Thursday.
Regular reporting to LSC on production quality trends and nature and statistics of NCRs.

## Slide 11: Tuning the procedures
The QC activities are based on a set of procedures (LHC-QBBI-TP), which are well understood and their methods thoroughly validated in workshop conditions.
The teams are reacting to the inspection results from the tunnel “on-line”, and the experience gained is used to streamline the procedures and adjust the acceptance criteria.

## Slide 12: Inspection of ultrasound welding
Change of ultrasound welding machine settings from CP=0.6 to 0.8 in 2009.
Gauge used for inspection has 3.1 mm width and is too small for CP=0.8.
Based on measurements of recently produced welds, gauge width increased to 3.4 mm.
New version of the inspection procedure (LHC-QBBI-TP-0003) released.

## Slide 13: Inspection of the shunts
Visual inspection of the top and bottom shunts modified (criterion of continuity of fillets suppressed)
New version of the procedure released (LHC-QBBI-TP-0007).

## Slide 14
Insulation boxes The problem
About 35% of busbars outside position tolerance.
Clearance box/M-flange insufficient to avoid box damage during welding.

## Slide 15: Insulation boxes Modification of baseline
The standard box is modified to have rounded corners at the extremities (wall thickness reduced from 3 mm to 1.3 mm). Polyimide layers added to cover the extremities.
The assembly procedure (LHC-QBBI-TP-0024) updated and released.

## Slide 16: Insulation boxes The standard repair
In case of interference:
Corners cut back so that the box cover is outside M-flanges.
U-pieces recovered from the existing insulation, reinstalled on busbars (mechanically protect the busbars and improve electrical insulation).

## Slide 17: Insulation boxes Inspection procedure
The inspection procedure (LHC-QBBI-TP-0008) updated and released.
The procedure defines the role of the LMF-QC and ELQC teams in the inspection process at different times, when visual aspect of the boxes differs due to presence of Eccobond filling.

## Slide 18: Revisiting geometrical acceptance criteria Global alignment gauge
Geometrical constraints of the insulation box were reanalyzed.
The dimensions of the global gauges are confirmed.

## Slide 19: Revisiting geometrical acceptance criteria Height gauge
A new type of gauge for checking the bottom surface of the busbars was tried out but with negative result.
The dimensions of the present C-gauges are confirmed.

## Slide 20
Main results from the QC teams

## Slide 21: ICIT: cases of equipment damage
  Equipment damage from the initial LHC installation confirmed or discovered in several sectors.
  During LS1:
    Certain number of PIMs and nested bellows were damaged during M-line cutting.
    Temperature sensor wires broken during MQ diode consolidation.
    Additional protections ordered and installed.

## Slide 22: ELQC
A large number of inspections have been performed covering all steps of the 13 kA splice consolidation “train”. In general:
  A high number of defective splices needs to be repaired:
    In S56, 25% of the splices had to be redone, 20% due to geometrical defects.
    In S67, 30% of the splices are defective, 13% due to electrical defects (R8).
    Exploratory inspections were done in S78 and S81: 25-30% of defective splices may be expected in other sectors.
  The quality of all repair and consolidation steps is satisfactory, similar to that obtained in the workshop and during 2008/09 campaign.
  ELQC is an essential element of SMACC-QA and all steps need to be maintained in the remaining sectors. (Possible suppression of one inspection step for newly made splices to be discussed during the Review).
Heavily damaged SC cable was found in a quadrupole segment with an Rcold outlier. All other segments of this type are being inspected before the repair is decided.

## Slide 23: Statistics QC of existing splices
Sector 5-6
Final
Inspected splices |  | 1272 | %
Conform |  | 956 | 75.2
Non-conform |  | 316 | 24.8
 | R8 | 30 | 2.4
 | Splice alignment | 57 | 4.5
 | Splice height | 178 | 14.0
 | Deformed lip | 15 | 1.8
 | Splice width | 6 | 0.5
 | Flange exchange | 22 | 1.7
Geometrical defects
20.8%

## Slide 24: Statistics QC of existing splices
Sector 6-7
Final
Inspected splices |  | 1266 | %
Conform |  | 890 | 70.3
Non-conform |  | 376 | 29.7
 | R8 | 170 | 13.5
 | Splice alignment | 66 | 5.2
 | Splice height | 116 | 9.1
 | Deformed lip | 14 | 1.1
 | Assembly | 10 | 0.8
Geometrical defects
15.4%

## Slide 25: Case of heavily damaged SC cable
Heavily damaged cable was found in a M2-int of QBBI.A21L6, part of a segment with an Rcold outlier, with clear signs of a busbar and cable overheating.
A campaign has been launched to open all other segments with Rcold outliers, to verify if similar damage occurred.
All splices in these segments are blocked until a full picture of possible damage is available and a strategy of repair is decided.

## Slide 26: ELQA, WELD, VAC
ELQA
ELQA tests performed every afternoon. Frequent disruptions due to poorly insulated clamps. High humidity in the tunnel a concern.
  Up to now, only “technological” shorts.
Frequency of ELQA tests?
  Questioned but maintained on daily basis; to be discussed during the Review.
WELD
M-line welding picking up. Excellent quality.
DN200 weld well advanced. Inspections show very good quality with a few NCs easily repaired.
VAC
M-leak checks about to start in the first vacuum subsector.

## Slide 27: Auditor findings -1
Is the force applied in a controlled way?
W-bellows checked?
Protective cover replaced?

## Slide 28: Auditor findings - 2
Cleanliness of surfaces is a standing concern
Traces of glue and Kapton on machined surfaces and machining tools.
Efficiency of cleaning (oxidization, glue) before soldering?
Traceability of solder?

## Slide 29: Summary – 1
The QA for SMACC relies on the production teams, on the QC team, and the team of CERN auditors.
  All elements of the QA organisation are fully operational.
The teams are reacting to the production and inspection results essentially “on-line”. Feedback from the tunnel is used to streamline the inspection procedures and acceptance criteria.
  A significant number of QC steps have been performed with existing/updated procedures.

## Slide 30: Summary – 2
A significant number of splices have to be redone, dominated by the geometrical defects.
  In S56, 25% of the splices were redone, 20% due to geometrical defects.
  In S67, 30% of the splices are defective, 13% due to electrical defects (R8).
  A similar number of defective splices is expected in other sectors.
Heavily damaged SC cable was found in a quadrupole segment with an Rcold outlier. All other segments of this type are being inspected and an appropriate strategy of repair is being discussed.
Protection of IC components and cleanliness during work remain a major concern.

## Slide 31: Back-up
Initiating and management of NCRs

## Slide 32: Basics of NC Management
LHC QA Plan – basis for all projects in the A&T sector, including SMACC.
The principles of non-conformities management given in QAP301 – “Handling of Non-conforming Equipment”.
Two classes of non-conformities:
  CRITICAL: have an impact on performance, durability, interchangeability, health or safety, interface to other LHC systems,
  NON-CRITICAL: all the others.
Project engineer decides on whether a non-conformity is critical or non-critical. Approves the non-critical NCs.
Critical non-conformities require approval of project engineer + project management.

## Slide 33: …Within SMACC-QA …
F. Savary
R. Principe
Ch. Scheuerlein
J-M. Dalin
D. Bodart
C. Garion
K. Dahlerup-P
P. Cruikshank
S. Feher
R. Ostojic
M. Struik
J-P. Tock
M. Pojer
Experts
(≡)
Ch. Scheuerlein
J-M. Dalin
D. Bodart
C. Garion
K. Dahlerup-P
P. Cruikshank
“Project Engineers”
(≡)
“Project Management”

## Slide 34: Production Step n
Production step n
Standard IP
Non-Standard IP
(Validated repair)
Internal-QC
NOK
OK
OK
Traveler
WISH
NOK
Go
Traveler in MTF
QC step n
Internal-QC/QC
Non-critical NC
(“Use-As-Is”)
NCR opened in MTF
Critical NC
Internal-QC

## Slide 35: Quality Control step n
QC step n
Standard TP
Critical NC
OK
or Non-Critical NC
(“Use-As-Is”)
OK
WISH
Go
Test Report in MTF
Production step n+1
QA Team Decision
NCR opened in MTF
Experts
QA Support
Action, Documentation Complete
Close NCR in MTF
SMACC
Coordination
Test Report
Action
Production team
QC team

## Slide 36: Decision Line
QA Team
Decision by Consensus
NCR opened in MTF
Actions and NCR Closure
Yes
Difficult case
Decision by RO and JPhT
No
Very high impact case
Decision by F. Bordry

## Slide 37: Statistics Critical NCRs
 | Open | Closed
LMF train Internal QC | - | 4
ICIT | 5 | 6
ELQC | 15 | 59
WELD | - | 1
ELQA | - | 1
VAC | 34 | 41
SMACC
22 July 2013