## Slide 1
Fourth LHC Splice Review Geneva – 22 to 24 July 2013
The Splice Consolidation Train
F. Savary with contributions from M. Duret, L. Grand-Clément, F. Lackner, H. Prin, R. Principe, S. Triquet, and many others

## Slide 2: Outline
Organization
  Communication channels
  Production work plans
  The train QA structure
  Consolidation work flows
Production rates and trends
QA indicators
  Data logs vs nominal working conditions
  How do we master quality?
Major issues
  How to deal with them?
  Impact on work and procedures
Quadrupole diodes
Conclusions

## Slide 3: Organization & work flows

## Slide 4: Communication channels
LS1 Committee
CSI
SMACC Project Leader
Splices consolidation train
QA
Production
SMACC QA
Meetings
2 / Week
Meetings
3 / Week
SMACC Meeting

## Slide 5: Production work plans
M-Line Cutting
Splices consolidation train H. Prin & F. Lackner
Production
Remove insulation
De-soldering
Re-soldering
Copper machining
Shunt
Install insulation
Quadrupole diodes
 WORK PLANS
1
2
3
4
5
6
7
8

## Slide 6: Production work plans
Via email every evening after ELQA validation tests
General message and specific ones to provide guidelines, and insist on important points / priorities
To all “opérateurs responsables”, the two “chefs de chantier” and the LMF mechanical and logistics services
With copy to LMF QA and CSI Office Leader
Dashboards per activity per ongoing sector
Printed on site and distributed in the morning

## Slide 7: Work plan – Open M
Ongoing activity
Done or cancelled
Ready to start

## Slide 8: Work plan – De-soldering, 1

## Slide 9: Work plan – De-soldering, 2

## Slide 10: Train QA Structure
[Resp.] R. Principe
[QC1] Becle S.
[QC3] Berthet R.
[QC2] Housiaux O.
[Data recording] Menu S.
Collect data from loggers
DFS
MTF-EDMS
Ensure procedures are respected
Detect ncr’s at early stage, and issue ncr’s documentation
Provide support as needed
Barely sufficient

## Slide 11: M-Line cutting – St16 Work Flow
Daily Work Plan
M-Line Cutting
Flange Lip ok
Data entered in WISH
Measuring position | Result
M1 - X0-Left | 8.55 mm
M1 - X4-Left | 8.33 mm
M1 - X8-Left | 8.48 mm
M1 - X0-Right | 8.91 mm
M1 - X4-Right | 8.43 mm
M1 - X8-Right | 8.76 mm
… | …

M-Flange to be replaced
CSI to initiate step
NO

## Slide 12: St16 – Follow up file

## Slide 13: M1 Ext. De-soldering – St21 WF
Daily Work Plan (following ELQC test results)
De-soldering
Sc cable status and bb extremities ok
Data entered in WISH
Wish records
De-soldering machine id.
Operators id. and date
Stabilization machine id. (resistive heating)

Inform SMACC and QA about NCR’s (e.g., sc cable damaged)
NO
Data entered in EDMS
EDMS records
Temperature profiles (de-soldering and stabilization)
Exact time of the cycle
General remarks
Number of cycles

## Slide 14: De-soldering follow up files
To find it in the data logger!
Up to 2

## Slide 15: De-soldering follow up files

## Slide 16: Production Rates & Trends

## Slide 17: Open M
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
Open M | 13 | 34 | 38 | 17 | 63 | 26 | 40 | 34 | 69 | 62 | 0 | 28 | 51
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Target rate 53 IC’s / Week
Achieved av. rate 39 IC’s / Week
13 weeks

## Slide 18: M De-solder & cable stabilization
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
M De-solder & cable resurfacing | 5 | 12 | 30 | 40 | 34 | 41 | 50 | 47 | 75 | 52 | 48 | 71 | 51
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved av. rate 41 splices / Week
There seems to be a limit here
Insufficient capacity!

## Slide 19: QA indicators

## Slide 20: Splice soldering – Nom. process
LHC-QBBI-IP-0013 (released in EDMS):
The splice parts are put together with a clamping vise with a force of 23 kN
Induction heating is used
Sn-Ag 96/4, melting point 221°C
Temperature control probe set to 250°C
The heating process stops automatically after 2 min
Cooling of the clamping vise is initiated manually by the operator, @ 100°C
Chart: Time [hh:mm:ss]
Phase 1: Ramp up
Phase 2: Plateau @ 250 °C for 2 min.
Stop heating
Start cooling of clamping vise
Melting T Sn-Ag 221°C
Temperature monitoring probe

## Slide 21: Soldering statistics S56
Till July 10th, 2013
 | Done | % | To do | % | Total | Anomalies | %
M1 ext | 78 | 100 | 0 | 0 | 78 | 4 | 5.12
M1 int | 91 | 100 | 0 | 0 | 91 | 6 | 6.59
M2 ext | 33 | 94.28 | 2 | 5.71 | 35 | 0 | 0
M2 int | 37 | 97.36 | 1 | 2.63 | 38 | 0 | 0
M3 ext | 50 | 98.03 | 1 | 1.96 | 51 | 2 | 4
M3 int | 48 | 94.11 | 3 | 5.88 | 51 | 2 | 4.16
Total | 337 | 97.96 | 7 | 2.03 | 344 | 14 | 4.15

## Slide 22: Soldering – typical anomalies
‘Anomalies’ means T profile outside allowable range
Chart: Time [s]
230°C
400°C

## Slide 23: Classification of anomalies
There are, to date, 14 deviations from nominal conditions, outside allowable range
Classification
  M1 line: 10 (71%)
  Insufficient temperature: 11 (78%)
    NB: QBQI.18L6 = low temperature
  Excessive temperature and/or process interruption: 3 (21%)
  Cycle duration: 1 (0.7%)

## Slide 24: Resolution of anomalies
Insufficient temperature
  Overall, 3% of the splices redone
  In most cases, due to the utilization of damaged temperature monitoring probes (made of Inconel). The melting is verified by witness filler, which is put in contact with the outside surface of the splice
  The temperature monitoring probes were replaced, and will be replaced systematically after several cycles (following inspection)
  Accasionally, the temperature monitoring probes were not installed correctly. To avoid this, we have organized refresher courses
Excessive temperature, or interruption of the process
  Overall, 0.8% of the splices redone
  Due to bad positioning of the temperature control probe. To avoid this, we have organized refresher courses
For the few occurrences: LMF to redo the splice, and the cable will be checked by ELQC (e.g. for excessive T)

## Slide 25: Catalog of defect (the past …)

## Slide 26: Today quality (e.g. QBQI.25L6)

## Slide 27: Splice de-soldering – Nom. process
LHC-QBBI-IP-0022 released in EDMS
Induction heating is used (260 °C)
Heating till melting, and U/cover can be removed
Chart: Time [s]
| 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 105 | 110 | 115 | 120 | 125 | 130
Ref. temperature | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
Monitoring probe | 37.5 | 36.6 | 35.9 | 36.8 | 44.6 | 56.9 | 73.4 | 92.8 | 111.8 | 129.4 | 146.4 | 161 | 173.9 | 185.6 | 197.5 | 209.1 | 220.4 | 231.7 | 242.7 | 252.2 | 257.5 | 259.3 | 254.1 | 243.2 | 233 | 224.1 | 216.3

## Slide 28: De-soldering statistics S56
Till July 16, 2013
 | Done | % | To do | % | Total | Anomalies | %
M1 ext | 79 | 100 | 0 | 0 | 79 | 25 | 31.64
M1 int | 92 | 100 | 0 | 0 | 92 | 25 | 27.17
M2 ext | 34 | 100 | 0 | 0 | 34 | 10 | 29.41
M2 int | 39 | 100 | 0 | 0 | 39 | 10 | 25.64
M3 ext | 52 | 100 | 0 | 0 | 52 | 10 | 19.23
M3 int | 53 | 98.14 | 1 | 1.85 | 54 | 10 | 18.51
Total | 349 | 99.71 | 1 | 0.28 | 350 | 90 | 25.71

## Slide 29: De-soldering T curves
Chart: M1, M2, and M3 TMAX < 260°C
QQBI.19R5 INT | 37.5 | 39.4 | 47.3 | 57.6 | 68.2 | 79.3 | 90.8 | 102 | 113.1 | 124.2 | 134.9 | 145.7 | 156.3 | 166.3 | 172.7 | 177 | 181.1 | 182.5 | 189.9 | 197 | 200.7 | 203.5 | 198.9 | 190 | 186.1 | 181.1 | 174.9 | 167.4 | 161.3 | 152.7 | 145.1 | 141.3 | 136.7 | 134.1 | 130.2 | 126.3
QQBI.19R5 EXT | 23 | 23 | 23 | 23.6 | 30.6 | 40.9 | 51.9 | 63.3 | 74.9 | 86.8 | 99.2 | 111.5 | 124.3 | 137 | 149.6 | 162.4 | 174.4 | 186.3 | 198.1 | 207.6 | 213.2 | 219.1 | 226.3 | 231.2 | 233.4 | 228.1 | 218.4 | 210.5 | 203.7 | 194.4 | 187.9 | 177.6 | 168.8 | 163 | 158.1 | 154.1 | 150.3
QBQI.27R5 EXT | 25.9 | 25.8 | 25.8 | 25.8 | 25.7 | 25.7 | 25.7 | 25.6 | 29.7 | 48.4 | 72.9 | 98.6 | 119.4 | 139.9 | 158.4 | 175.1 | 191.2 | 206.9 | 221.4 | 235.1 | 245.4 | 254.8 | 258.6 | 253.4 | 243.1 | 234.5 | 223.4 | 201.4 | 190.2 | 180.1 | 173 | 167.2 | 161.7 | 156.4 | 156.3 | 152.7 | 150.3 | 146.4 | 143.8 | 140.2 | 136.6 | 136.4 | 142.5 | 140.9 | 137 | 133.8 | 130.2 | 126.4 | 124 | 121.6 | 119.1
QBBI.A32L6 INT | 32.5 | 32.7 | 32.8 | 33 | 34.2 | 43.8 | 59.1 | 73.9 | 85.7 | 97.2 | 110.7 | 124.6 | 138.9 | 154.1 | 168.1 | 180.7 | 193.1 | 205.9 | 218.6 | 229.7 | 239.4 | 245.7 | 249.1 | 252.3 | 257.5 | 256.8
QBBI.A30L6 INT | 35.1 | 34.9 | 36.1 | 40.6 | 48 | 57.1 | 67.3 | 78.2 | 89.8 | 101.9 | 114.2 | 127.5 | 141 | 154.6 | 167.7 | 181.5 | 196.1 | 207.7 | 220 | 230.9 | 236.9 | 242.2 | 246.9 | 249.9 | 252.6 | 254.4 | 255.9 | 257.4 | 253 | 243.9 | 235.6 | 227.7 | 220.5 | 214 | 208.1 | 202.5 | 197 | 192.1 | 187.1 | 182.7 | 178.6 | 175.3 | 172.1 | 168.9 | 165.7 | 162.6 | 159.4 | 156.4 | 153.5
QBBI.A30L6 EXT | 22.3 | 22.3 | 22.3 | 23.5 | 34.3 | 47.6 | 57.9 | 68.5 | 80.8 | 93.1 | 105 | 117.6 | 130.3 | 142.7 | 155.4 | 168.2 | 180.9 | 193.1 | 205.6 | 218.9 | 230 | 236.8 | 242.3 | 247.5 | 250.8 | 253.2 | 255.4 | 249.2 | 239.7 | 231.5 | 224.2 | 217.3 | 211 | 205.9 | 200.9 | 196.3 | 192 | 187.9 | 183.9 | 180.2 | 176.6 | 173.1 | 169.7 | 166.4 | 163.3 | 160.1 | 156.8 | 153.3 | 149.4 | 145.6 | 140.9 | 133.6 | 115.3 | 93 | 74.6
QBBI.B29L6 INT | 31.1 | 31 | 31 | 31 | 33.7 | 45 | 59 | 71.4 | 82.9 | 95.3 | 108.5 | 121.9 | 135.2 | 148.9 | 161.6 | 174.4 | 186.9 | 200.4 | 214.4 | 227.1 | 237.1 | 242.1 | 246.7 | 250.8 | 253.9 | 255.8 | 257.2 | 258.9 | 255.9 | 245.4 | 236.4 | 228.4 | 221.1 | 214.2 | 208.6 | 203.6 | 198.8 | 193.8 | 188.9 | 183.7 | 179 | 174.9 | 170.6 | 167.3 | 163.5 | 160.3
QBBI.B29L6 EXT | 22.9 | 22.9 | 23.8 | 31.6 | 43.3 | 55.4 | 67.1 | 78.5 | 90.2 | 102.3 | 114.5 | 127 | 140.5 | 154 | 166.3 | 177 | 188.2 | 201.5 | 214.8 | 227.6 | 239.5 | 247 | 251.6 | 254.9 | 258.1 | 257.9 | 248.4 | 235.9 | 226.9 | 219.1 | 212.1 | 205.7 | 199.5 | 193.7 | 188.3 | 183.9 | 180.9 | 174.3 | 167
QBBI.B28L6 INT | 22.8 | 22.8 | 22.8 | 27.9 | 43.1 | 55.9 | 65.6 | 77.1 | 88.5 | 100.3 | 112.1 | 124.3 | 136.4 | 148.7 | 160.7 | 172.9 | 184.7 | 196 | 208.9 | 222.5 | 233.8 | 240.7 | 245.8 | 250.6 | 253.5 | 255.4 | 254.1 | 248.4 | 240 | 229.3 | 220.6 | 213.6 | 207.5 | 201.3 | 196.2 | 192 | 186.6 | 182.4 | 178.8 | 174.9 | 171.6 | 168.1 | 164.7 | 161.6 | 158.4 | 155.5 | 152.7 | 149.9 | 147.1 | 144.4 | 141.7 | 139.2 | 136.9 | 134.5 | 132.1 | 129.8 | 127.3
QBBI.B28L6 EXT | 31.6 | 31.4 | 31.2 | 31.1 | 34.3 | 44.6 | 55.9 | 67.6 | 80 | 92.7 | 105.8 | 119.1 | 132.8 | 146.6 | 160.2 | 173.4 | 186.5 | 199.6 | 212.9 | 225.3 | 234.1 | 240 | 244.9 | 248.7 | 251.5 | 253.6 | 255.1 | 256.3 | 254.8 | 248.8 | 238.6 | 228 | 217.5
QBQI.20L6 INT | 25.2 | 25.1 | 25.1 | 25.1 | 31.1 | 42.1 | 53.7 | 66.5 | 80.1 | 94.3 | 108.8 | 123.9 | 139.4 | 154.4 | 168.1 | 180.9 | 193.3 | 205.9 | 218.9 | 230.5 | 240 | 246.6 | 251.2 | 254.6 | 257.2 | 259.2 | 259.4 | 245.5 | 232.9 | 223.2
T lower than expected

## Slide 30: De-soldering
Categories of defects after de-soldering in S56
Chart: Week #
| 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Cable exploded | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Strands cut and/or bevelled | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 4 | 3 | 8
Sc cable bevelled (sides) | 0 | 1 | 1 | 5 | 0 | 4 | 4 | 3 | 0 | 0
Sc cable misaligned | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
Bus bar lip deformed | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0

## Slide 31: Cable stabilization
Chart: t [s]
LHC-QBBI-IP-0015 released in EDMS
Resistive heating is used
Plateau of 3-4 min @ 240°C

## Slide 32: Stabilization statistics S56
Till July 16, 2013
 | Done | % | To do | % | Total | Anomalies | % | Thermal | % | Other | %
M1 ext | 79 | 100 | 0 | 0 | 79 | 4 | 5.1 | 3 | 75 | 1 | 25
M1 int | 92 | 100 | 0 | 0 | 92 | 4 | 4.3 | 2 | 50 | 2 | 50
M2 ext | 34 | 100 | 0 | 0 | 34 | 3 | 8.8 | 2 | 66.6 | 1 | 33.3
M2 int | 39 | 100 | 0 | 0 | 39 | 8 | 20.5 | 0 | 0 | 8 | 100
M3 ext | 52 | 100 | 0 | 0 | 52 | 2 | 3.8 | 1 | 50 | 1 | 50
M3 int | 53 | 98.14 | 1 | 1.85 | 54 | 3 | 5.6 | 0 | 0 | 3 | 100
Total | 349 | 99.7 | 1 | 0.28 | 350 | 24 | 6.8 | 8 | 33.3 | 16 | 66.6

## Slide 33: Stabilization (‘thermal’ anomalies)
Chart: Time [s]
260°C
220°C

## Slide 34: Shunt soldering – Nom. process
LHC-QBBI-IP-0021 released in EDMS
Resistive heating is used
Sn-Pb 60/40, melting point 188°C
Ramp up to 205 °C in ~5 min, then plateau for 2.5 min

## Slide 35: Shunt soldering statistics S56
 | Done | % | To do | % | Total | Anomalies | % | Th. | % | Other | %
M1 | 222 | 97.79 | 5 | 2.2 | 227 | 2 | 0.9 | 2 | 100 | 0 | 0
M2 | 222 | 97.79 | 5 | 2.2 | 227 | 2 | 0.9 | 1 | 50 | 1 | 50
M3-ext | 222 | 97.79 | 5 | 2.2 | 227 | 4 | 1.8 | 4 | 100 | 0 | 0
M3-int | 222 | 97.79 | 5 | 2.2 | 227 | 3 | 1.35 | 2 | 66.66 | 1 | 33.33
Total | 222 | 97.79 | 5 | 2.2 | 227 | 11 | 4.95 | 10 | 90.9 | 2 | 18.18

## Slide 36: Shunt soldering
Chart: Time [s]
QBQI.32R5 LEFT TOP | 138 | 144 | 144 | 146 | 146 | 148 | 148 | 148 | 153 | 153 | 162 | 162 | 172 | 172 | 177 | 177 | 177 | 181 | 181 | 189 | 189 | 198 | 198 | 204 | 204 | 205 | 205 | 205 | 205 | 205 | 208 | 208 | 207 | 207 | 209 | 209 | 209 | 209 | 210 | 210 | 212 | 212 | 211 | 211 | 213 | 213 | 212 | 212 | 214 | 214 | 214

## Slide 37: Example of shunted splices
QBQI.25L6

## Slide 38: Major issues / difficulties

## Slide 39: Not everything is perfect!

## Slide 40: Museum of horrors …

## Slide 41: … implying some adjustments
Defects exceeding the tolerance limits, especially impacting on the installation of the insulation box, and requiring modifications of the insulation system
Main impacts:
  Need to develop adequate solutions
  Additional work to carry out tests and mock-up assemblies, to validate the proposed solutions
  Modify some of the procedures and repeat the approval process
  Production rate affected during the first months, and impact on the welding activity
  Expansion of the train to treat conforming cases, and increased production times due to the logistics effort
Step in copper joint
Bending deformation
Gaps in copper joint

## Slide 42: Local gauge …

## Slide 43: … and global gauge
21
0
+1

## Slide 44: Spool cables
Lines M1 & M2
Too long
Do not fit into the combs of the new insulation system
Some of them will have to be cut, shortened, and re-welded
Good case

## Slide 45: Capture tooling
The amount of capture tooling did not match the actual needs due to unexpected expansion of the train
  We started with 500 items
  We have manufactured additional 1200 (simple)
Are mounted after M-lines are cut-opened, and are removed in the end, after resin injection

## Slide 46: Insulation system …
Quadrupole splices
Dipole splices
VRESIN= 58 ml / splice
VRESIN= 50 ml / splice
Injection hose
… Had to be revised to cope with the non-conforming radial position of the bus bars in the M-Flange

## Slide 47: Optimizing injection parameters
In order to
  Avoid over pressure during injection (risk of bursting the tubes)
  Avoid excessive temperature (< 50˚C @ any time of the process)
  Ensure shunt covering (min. of 50% required in the shunt region)
  Avoid lack of transversal filling (min. of 2 x 20 mm on either side of the screws)
  Avoid injecting excessive amount of resin (risk of higher stresses on the screws)
Lack of Eccobond
Over injection
Lack of Eccobond

## Slide 48: Quad. bus bars
[-0;+1.5]
[-1;+1]
[-1.5;+0]
 | Parameter | Nominal | Tolerance limit
Bus Bar with Insulation | HPOS. | 26.1 | 27.6
 | VPOS. | 15.1 | 16.1
 | RGAPBB-Flange | 10.9 | 9.1
Insulation Box standard | RGAPBox-Flange | 3.8 | 2
Insulation box modified | RGAPBox-Flange | 5.4 | 3.6

## Slide 49: Dipole bus bars
[-0;+1.5]
[-1;+1]
[-1.5;+0]
 | Parameter | Nominal | Tolerance limit
Bus Bar with Insulation | HPOS. | 26.1 | 27.6
 | VPOS. | 8.1 | 9.1
 | RGAPBB-Flange | 13.4 | 11.7
Insulation box standard | Bot RGAPBox-Flange | 7.1 | 5.4
 | Top RGAPBox-Flange | 3.6 | 1.9
Insulation box modified | Bot RGAPBox-Flange | 8.2 | 6.5
 | Top RGAPBox-Flange | 5.2 | 3.5

## Slide 50: Measurements, RGAPBB-Flange
Chart: # of measuring positions
73 IC’s were checked in S67, from QBBI.8R6 to QBBI.B31R6
2 RGAP measured for the quadrupole BB, and 2 / 4 for the dipoles
For the quadrupole BB, 80 out of 206, i.e. 39%, of the measuring points are below 9.1 mm, i.e. outside the specified tolerance, and 17, i.e. 8% would not allow the installation of the standard box for which a minimum gap of 7.1 mm is needed
For the modified box (see next slides), a gap of 5.5 mm will be sufficient
Av. RGAP quad’s: 9.9 mm
Av. RGAP dip’s: 12.5 mm

## Slide 51: Solution – New baseline
Wall thickness reduced from 3 mm to 1.3 mm @ both ends
Two layers of 70 µm polyimide tape @ both ends
To protect the box against severe damage during welding of M-lines in case of contact, especially sticking with the flange

## Slide 52: When there is interference …
Glue the VP310 U profile on the bus bar insulation with Araldite, then continue with the standard process, i.e. apply the 50 µm polyimide foil around the bus bar, and finally the filling pocket, and the insulation box. VP310 is an additional mechanical/thermal and electrical insulation

## Slide 53: Fall back solution
De-solder, reshape the bus bar ends, and re-solder

## Slide 54: Update of the procedures, 1
Splice soldering (LHC‐QBBI‐IP‐0013)
  2 min plateau @ 250°C, instead of 15 s @ 240°C
Cu machining
  Harmonization of the criteria between LMF QA and ELQC (0.15 mm flatness and measurement procedure)
Shunt soldering
  Solder fillet and aspect of the reservoir
New version for the following procedures
  LHC‐QBBI‐IP‐0024 (Insulating box installation)
  LHC‐QBBI‐IP‐0028 (Eccobond injection procedure)

## Slide 55: Update of the procedures, 2
Visual inspection of the insulation system after injection, according to test procedure edms 1240302 to verify that:
  Eccobond® fills a large volume of the box
  The locking screws are in good contact between top and bottom box parts
  There are no visible crack
  The insulation box is correctly positioned with respect to the M-line flanges
  The spool cables are correctly positioned
  The insulation box satisfies the dimensional tolerances

## Slide 56: Diodes … … of the quadrupole magnets only

## Slide 57: Consolidation highlights

## Slide 58: Diode consolidation – St57
R diode to HS < 15µΩ
Daily Work Plan
Cut-open the diode box
Take pictures
Do electrical checks
El. Checks ok
NO

Consolidation work
DFS
MTF & EDMS
Electrical checks
R BB to HS > 2µΩ
NCR
NCR
Redo the bad contact
NCR
Diode stack substitution

El. check of int. contacts ok
NO
NO
YES
YES
NO

## Slide 59: Measurement procedure
For the internal contacts
The sum of internal contact resistances + the resistance of bus bars is measured
Then, individual contact resistances are calculated
  HS to diode
  Bus bar to HS
U1 I x (Rbb1 + Rc_bb_hs1 + Rhs1 + Rc_d_hs1)
U1
U2
U2 I x (Rbb2 + Rc_bb_hs2 + Rhs2 + Rc_d_hs2)

## Slide 60: Diode to HS + HS to BB
Chart: Internal contacts (Diode to HS + HS to BB)

## Slide 61: Diode BB to connection plate
Chart: Diode BB to connection plate

## Slide 62: Magnet BB to connect. plate
Chart: Magnet BB to connection plate

## Slide 63: Overall status
Sector 5-6 :
  47/47 Opened
  47/47 Measured
  10/47 Consolided
Sector 6-7 :
  51/51 Opened
  51/51 Measured
Sector 7-8 :
  51/51 Opened
  51/51 Measured
Sector 8-1 :
  11/47 Opened

## Slide 64: BB to connection plate contacts
Chart: Measurement #

## Slide 65: NCR QBQI.25R6 and QBQI.34R7
Insulation sleeve not at the right position

## Slide 66: Conclusions
Train organization working fine
Overall very good quality of the work carried out; very few failures
Overall quality of the existing splices lower than expected, i.e. more splices to redo, which appears to be a bottle neck
Issues with the installation of the insulation system, which needed to be adapted, due to imperfect position of the bus bars in the M-flanges
Learning curve phase almost over, acceptance criteria were revised, and the procedures updated accordingly
Train QA too busy
Consolidation of the quadrupole diodes under control, working fine

## Slide 67: With warm thanks to:
The splice consolidation train (production and QA)
  M. Duret, F. Lackner, H. Prin, R. Principe, and S. Triquet
  J.-M. Hubert and A. Aijaz (PAEC), P. Martins, L. Favier, K. Chaouki, M. Dumas, C. Lopez, M. Pozzobon, L. Grand-Clément, P. Canard, R. Faes, and numerous FSU’s
  S. Menu, A. Ulbricht, and H. Monari
The CSI team, M. Pojer and friends
The SMACC QA team, R. Ostojic, C. Scheuerlein and friends
EN-MME
  The welding experts, S. Atieh and friends
  The material scientists, S. Sgobba and friends
  The mechanical instrumentation engineers, M. Guinchard and friends
The SMACC ELQA team, K. Dahlerup-Petersen, G. D’angelo, and friends
The Project Leader and the TE Management for their continuous support
And I have certainly forgotten many others, a thousand apologies!

## Slide 68: Spare slides

## Slide 69: Insulation removal and inspection – St18
Daily Work Plan
Insulation removal
General status of the interconnect ok
Data entered in WISH
Records
Compression tool & machine id
Operators id. and date

Inform SMACC and QA about NCs (e.g., spool damaged)
NO

## Slide 70: St18 – follow-up files

## Slide 71: St18 – follow-up files

## Slide 72: M1 Ext Soldering – St24
Daily Work Plan (following ELQC test results)
Soldering
BB geometry and general status OK
Data entered in WISH
Wish records
Soldering machine id.
Operators id. and date
Lot #. for U and wedge
Lot #. for SnAg
# of extra cycles

Inform SMACC and QA about NCs (e.g. high T during soldering)
Re-do splice soldering, re-heat the splice, or “use as is”
NO
Data entered in EDMS
EDMS records
Temperature profiles
Exact time of the cycle
General remarks
Number of cycles

## Slide 73: Soldering follow up files p. 1/2

## Slide 74: Soldering follow up files p. 2/2

## Slide 75: Cu Machining & Cleaning – St46
Daily Work Plan (following ELQC test results)
Cu machining
Flatness and position (vs. flange) ok
Data entered in WISH
Wish records
Operators id.
Date

Inform SMACC and QA about NCs (e.g., excess machining)
Fix by further machining or “use as is”
NO
Data entered in EDMS
EDMS records
NCs
Paper copy
Follow up files
Exact machining position
General remarks

## Slide 76: Cu machining follow up files

## Slide 77: Shunts installation – St48
Daily Work Plan (following ELQC test results)
Shunt installation
Position and quality of Sn-Pb solder ok
Data entered in WISH

Inform SMACC and QA about NCs
Re-do shunt soldering
NO
Data entered in EDMS
EDMS records
Thermal cycles per shunt
Exact date and time
Wish records
Shunt sold. machine id.
Operators id. and date, et.
Shunt lot number
Extra cycles if any

## Slide 78: Shunt installation follow up files
To find it in the data logger!

## Slide 79: M insulation installation – St54
Daily Work Plan (following ELQC test results)
Insulation
Box position, Eccobond distribution and general status ok
Data entered in WISH

Inform SMACC and QA about NCs (i.e, bad positioning of the bb vs. flange)
Redo ins. box installation (i.e., VP310)
NO
Data entered in EDMS
EDMS records
Eccobond injected volume
Exact date and duration of the injection cycle
Wish records
Compression tool machine id.
Injection machine id.
Operators id. and date, et.
Eccobond lot number
Insulation box lot

## Slide 80: Installation of the box follow up files

## Slide 81: Eccobond injection follow up files

## Slide 82: Procedures status
Chap. | Sub-activity | EDMS | Baseline | Status
3.2 | Découpe soudure manchettes M | 1227123 | LHC-QBBI-IP-0023 | Released
 | Training course | 1261495 |  | 
3.2.1 | Fiche d'instruction pour certification CE | 1234983 |  | 
3.2.2 | Risk assesment form OHS-0-0-5 | 1234987 |  | 
3.2.3 | Safety form | 1234992 |  | 
4.1 | Capture soufflet M | 1198420 | LHC-QBBI-IP-0014 | Released
 | Training course | 1233270 |  | 
4.1.1 | Fiche d'instruction pour certification CE | 1210645 |  | 
4.1.2 | Risk assesment form OHS-0-0-5 | 1210638 |  | 
4.1.3 | Safety form | 1210651 |  | 
4.2 | Dépose isolation interconnexion | 1198424 | LHC-QBBI-IP-0011 | Released
 | Training course | 1235008 |  | 
6.1 | Débrasage par induction U/plat de fermeture | 1218408 | LHC-QBBI-IP-0022 | Released
 | Training course | 1242596 |  | 
6.2 | Stabilisation câble supraconducteur | 1218412 | LHC-QBBI-IP-0015 | Released
 | Training course | 1235753 |  | 
8.1 | Brasage par induction U/plat de fermeture | 1218410 | LHC-QBBI-IP-0013 | Released
 | Training course | 1235010 |  | 
 | Critères Contrôle Qualité Interconnexions 12 kA | 1171359 |  | 
10 | Usinage cuivre avant brasage des shunts | 1227125 | LHC-QBBI-IP-0025 | Released
11.1 | Brasage des shunts sur les busbars | 1224166 | LHC-QBBI-IP-0021 | Released
 | Training course | 1242600 |  | 
11.2 | Débrasage des shunts sur les busbars | 1224636 | LHC-QBBI-IP-0020 | Released
 | Training course | 1242602 |  | 
13.1 | Montage boitier isolation busbar | 1227124 | LHC-QBBI-IP-0024 | Released
 | Training course | 1242604 |  | 
13.2 | Démontage capture soufflet M | 1218413 | LHC-QBBI-IP-0019 | Released
 | Training course | 1242606 |  | 
13.3 | Injection Eccobond |  | LHC-QBBI-IP-0028 | Under approval LHC

## Slide 83: Other procedures
Interconnexion DFBA PG-BB-PIG-TAIL | 1265665 | LHC-DFBA-IP-0004 | Released
Interconnexion DFBA SHM-HCM | 1265664 | LHC-DFBA-IP-0003 | Released
Plan Assurance Qualité | 1251404 |  | Released
Audits internes LS1 | 1261449 |  | Released
Formation-personnel-LS1 | 1261468 |  | Released
Gestion des approvisionnements LS1 | 1261472 |  | Released
Gestion des défauts et des NC LS1 | 1261475 |  | Released
Gestion des déchéts générés en LS1 | 1272591 |  | Released
Gestion des données LS1 | 1272593 |  | Released
Gestion du parc-machines LS1 | 1272595 |  | Released
Contrôle qualité LMF pour LS1 | 1272597 |  | Released

## Slide 84: Insulation removal / M protection
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
M insulation removal and protection | 13 | 26 | 37 | 25 | 67 | 3 | 26 | 11 | 43 | 63 | 56 | 58 | 7
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved rate 33 IC’s / Week

## Slide 85: M Solder
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
M Solder | 0 | 3 | 18 | 15 | 32 | 36 | 33 | 40 | 68 | 50 | 49 | 48 | 61
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved rate 36 splices / Week

## Slide 86: Cu machining & cleaning
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
Cu machining & cleaning | 0 | 12 | 5 | 6 | 23 | 32 | 43 | 22 | 20 | 30 | 37 | 24 | 30
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved rate 23 IC’s / Week

## Slide 87: Shunts installation
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
Shunts installation | 0 | 7 | 5 | 4 | 12 | 20 | 43 | 36 | 21 | 23 | 40 | 30 | 27
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved rate 21 IC’s / Week

## Slide 88: M insulation installation
Chart: 
| W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
M insulation installation | 0 | 0 | 0 | 3 | 1 | 6 | 12 | 3 | 6 | 0 | 14 | 12 | 36
Nominal | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Chart: 
Achieved rate 9 IC’s / Week

## Slide 89: NCR’s on diodes
QBQI.14R5 and QBQI.16R5
  High internal contact resistance detected by indirect measurement (13µΩ instead 5 max)
    Diode had to be partially removed from its cylinder
    Direct measurements have confirmed the high value
    Decision by the Diode Working Group to «use-as-is»
About the three sectors measured
  17 diode stacks out of 149 have at least one value above 7 µΩ
  9 at least one value above 10 µΩ
  2 at least one value above 15 µΩ
    Include QBQI.16R5, QBQI.31R6 has to be measured by direct procedure

## Slide 90: NC QBQI.( 30L8 / 25L8)
Insulation piece was almost in the right position ... but
    Diode blocks the piece rotating
      Special tool is designing
      Or using diode extraction
    Step «Diode reparation check» done on 6/6/2005

## Slide 91: NC QBQI.30R7
Insulation piece without holes
Cold mass 008
«Prototype»

## Slide 92: Measurement procedure, LS1
Contacts has to be computed
  Heat sink / diode
R contact bb,hs + R contact d,hs