## Slide 1: MM detector construction
One or several modules per sector
considerations

## Slide 2
PCB production
PCB material procurement
strip pattern + coverlay
Resistive strip printing
Pillars
r/o panel production
Drift panel production
Mesh glueing
Multiplet assembly
Wedge assembly
Front-end electronics
Wedge test
N=1
Multiplet test
No
Yes
Acceptance test
CERN
Production sites
CERN PCB workshop + industry
QC test

## Slide 3: Number of objects
Item | Total # of objects | Large sectors |  | Small sectors | 
 |  | η strips | stereo strips | η strips | stereo strips
PCBs | 2048 | 512 | 512 | 512 | 512
Drift panels | 192 (576) | 96 (288) |  | 96 (288) | 
Readout panels | 128 (384) | 32 (96) | 32 (96) | 32 (96) | 32 (96)
Assembly of multiplets | 64 (192) | 32 (96) |  | 32 (96) | 
Spacer structure | 32 | 16 |  | 16 | 
For the case of full wedges (in brackets for 3 modules/wedge)

## Slide 4: Options
Granite tables in institutes that have expressed interest in detector construction
Pavia: 3500 x 2500
Rome: 3000 x 1500
Frascati: 4500 x 2500
Dubna: (3550+280) x 2600
CEA Saclay: 3000 x 2000
LMU Munich: 1500 x 1200
Freiburg: ≥4000 x 2000 ??
# mods/wedge | 1 | 2 | 3
 | Max module dimensions |  | 
Large sector | 2200 x 3750 | 2200 x 2800 | 2200 x 1500
Small sector | 1800 x 3600 | 1600 x 2700 | 1300 x 1500
# r/o panels | 2 x 64 | 2 x 128 | 2 x 192
# drift panels | 2 x 96 | 2 x 192 | 2 x 288
# assemblies | 64 | 128 | 192

## Slide 5: Wedge options (large sectors)
2.2 m x 1 m
2.2 m x 1 m
1.7 m x 2 m
2.2 m x 3 m
2.2 m x 1 m

## Slide 6: Wedge options (small sectors)
1.8 m x 1 m
1.5 m x 1 m
1.2 m x 1.8 m
1.3 m x 2.3 m
1.8 m x 1.4 m

## Slide 7: Full wedge vs 2 or 3 modules/wedge
Advantages | Disadvantages
Fewer modules = less time and manpower | Larger area affected in case of construction problem
 | Larger tables, larger tools
Easier integration of services | ? Pressure drop over large dimension ?
Easier implementation of stereo layers | 
No dead space | 
Alignment within wedge by construction | 

## Slide 8: Detector construction model
Splitting of construction into deliverables of same type in one institute, rather than building full detectors in each institute
  Readout PCBs centrally procured by CERN PCB workshop (organization and follow up of production in industry)
  Other material procurement: tbd
  All (or fraction of) drift panels for the large (small) sectors in one place
  All (or fraction of) r/o panels for large (small) sectors in one place (possibly split into eta and stereo panels)
  Assembly and tests of quadruplets of same type (or all) in one place; only place(s) where a clean room is required, number of places tbd
  Mounting of electronics & final tests and assembly at CERN (BB5?)
Advantage:
  Optimization of infrastructure, tooling, and specialists know-how

## Slide 9: Detector construction – drift panels
Drift panels (192/384/576 for 1/2/3 modules/wedge)
  Final design
  Material procurement (stiffener, skins, inserts, gas distribution channels, mesh frame, …)
  Panel glueing
    requires flat table(s) + tooling(s)
    1–2 days/panel (?) function of glueing procedure
  Drift electrode deposition (Cu-clad skins or Cu foil or C-paint or …)
  Mesh glueing - in-house (requires tooling) or external
  Finishing & qualification

## Slide 10: Detector construction – r/o panels
Readout panels (64/128/192 for 1/2/3 modules/wedge)
  Final design
  Material procurement (stiffener, inserts, electronics integration parts, cooling & cabling channels, …)
  Panel glueing
    requires flat table(s) + tooling(s)
    Alignment of readout boards + panel-panel alignment
    1–2 days/panel (?) function of glueing procedure
  Finishing & qualification

## Slide 11: Detector construction – assembly
Assembly and tests of quadruplets (64/128/192 quadruplets for 1/2/3 modules/wedge)
  Clean room required (Class ?) but no marble table (tbc)
  Procurement & qualification of O-rings
  Develop technique of cleaning & closing of multiplets
  Establish qualification procedure and tools
Mounting of final electronics & final test at CERN (BB5?)
Support structure
  Design of detector support system
  Material procurement
  Construction

## Slide 12: Sharing of work
Detector construction Core cost is estimated at ≤3 MCHF
Core cost for MM PCB boards is 2.3 MCHF, detector mechanics ≈0.5 MCHF (this does not include tooling & infrastructure nor manpower costs)
Two scenarios
Delivery of complete and tested detectors by each participating lab
  Granite table(s) & clean room in each lab
  Same for tooling and test benches
  Maximizes work load but more interesting challenges
Construction of panels and assembly & tests in different places
  Needs only the tools required for the specific task (marble tables, clean room)
  Probably more efficient and cheaper

## Slide 13: Arguments for a single panel scenario
Based on the experience with making small, medium, and large panels following the construction scheme that has been outlined in the TDR
We have glued in 1 week two full-size small-sector panels using an improvised stiff-back (glued in two days)
The method as such works
What we have not yet in hand is the glueing, in particular the glueing of the 2nd skin on a non-precise stiffener (either honeycomb or foam), i.e., compensating the surface variations by glue.
  Using more precise materials should overcome this problem
  The panel flatness is OK (where the panel is well glued), it is given by the granite table
The difficulty we have encountered is to go from 0.5 x 1 m2 to 1 x 2 m2, no difference to go to 2 x 3.5 m2

## Slide 14: Single panel scenario … cont’d
We have not seen any striking technical argument that speaks against a full-sector module
Performance is clearly better for the full-sector module: no dead areas, no edge effects.
Services are easier, small advantages in the MM board layout, …
Any of the proposed construction techniques can be used to make full-sector panels (I reserve my judgement concerning the Saclay glueing technique,in general, until it is proven to work). The stiffback and vacuum bag techniques can easily be used for large panels; the Frascati method lends itself also to go to large sizes.
The working time is essentially the same for a 1 x 2 m2 or 3.6 x 2 m2 panel
Multiplication of modules means multiplication of tools and time and manpower and costs

## Slide 15: Production time estimate
Panel glueing: (2 panels/ week)
  2 days/panel (occupation of granite table & stiffback or similar)
  2 days for finishing (drilling & controls) – in parallel with glueing
  1 day safety margin
Assume four specialized panel glueing sites
  In a single production site (with a single granite table) all panels (+some spares) can be produced in 1.5 years (leaves a good safety margin)
Assembly & testing of quadruplets:
  Assume two specialized assembly and test sites (large/small)
  1 assembly & test/week or 32 assemblies in 1 year per site
  Well matched to panel production speed, with good safety factor

## Slide 16: Single panel construction scenario
Most efficient: sharing of the construction between labs
For example, the construction could be split as follows:
Construction of small-sector multiplets: INFN/GR
  Drift panels: labs A/B (96 panels, needs granite table)
  Readout panels: lab C (64 panels, needs granite table)
  Assembly + testing: lab D (32 assemblies, needs Clean Room, no granite table)
  Labs E/F/ … participate in design, production of parts & tools, and in testing
Construction of large sector multiplets: CEA Saclay/Dubna/DE
  Drift panels: lab A/B (96 panels, needs granite table)
  Readout panels: lab C (64 panels, needs granite table)
  Assembly + testing: D/… (32 assemblies, needs Clean Room, no granite table)
  Labs E/F/… participate in design, production of parts & tools, and in testing
Spacer structure: CEA/Dubna (large) & INFN (small) [or some other labs]

## Slide 17: Other tasks …
Many other tasks need to be covered
Alignment
  PCB alignment procedure and tools
  Panel alignment procedure and tools
  T-sensors/stress sensors/B-sensors
  Cooling system
  Integration of r/o + other boards
  …