## Slide 1: How to implement all the HL-LHC upgrades
Lucio Rossi for the HL-LHC team
Review of LHC & Injector Upgrade Plans
(RLIUP Workshop)
Archamps 30 October 2013

## Slide 2: HL-LHC : work around the ring > 1.2 km
3000 fb-1 in 10 years
Limited pile up : 140  5 1035 levelled
Nov 2011 : FP7 HiLumi LHC Design Study
20 (+1) Institutes from EU, Ru, USA and JP

## Slide 3: Point 4 : Cryoplant for RF (LS2 2018)
Main aim is to separate SCRF form the arc cooling
But will have capability for a harmonic RF system and for e-lens SC solenoid

## Slide 4: Point 7: horizontal SC links (LS2 2018)

## Slide 5: P2 - DS collimators ions – 11 T (LS2 -2018)
11 T Nb3Sn
Recommended by the Collimation Review

## Slide 6: P7 DS collimation – 11 T (LS2 2018)
11 T Nb3Sn
Colimation review: preparare and then check real need during Run II

## Slide 7: Low impedence collimators(LS2 & LS3)
New material: MoGr

## Slide 8: P1-P5 IR Magnets (IT-D1) Powering, TAS
IT : LARP –CERN
D1: KEK

## Slide 9: The critical zone around IP1 and IP5
1.2 km of LHC !!

## Slide 10: P1-P5 MS Magnets, Powering, TAN
  Q4-Q5-Q6
  MS in Q10 in Sectors 12,45,56,81
Stronger Q5 IR6
2 magnets

## Slide 11: IT robusteness: beam screen is critical
Cold bore
Beam screen
Tungsten inserts
Beam screen and e-clouds in the triplet
Nanographite coatingfor SEY 0.95!
Test at cold in SPS end of 2014
Electrodes (tested at LNF in 2012) also studied
4 LHe channels with inner radius = 1.78 mm
Tungsten density = 19.3 g/cm3 (no packing factor)

## Slide 12: IT dose on critical components in HL-LHC
E. Todesco
F. Cerutti
L. Esposito
However design for rad hard is under way (better insulation, metallic spacers, etc.)

## Slide 13: Crab Cavities

## Slide 14: Situation: from drawings to reality…
LARP-BNL
LARP-ODU-JLAB
UniLancaster-CI-CERN

## Slide 15: And excelent results: RF dipole > 5 MV ¼ w and 4-rods also tested (1.5 MV) cleaning & vacuum issues: new test under way)
Initial goal was 3.5 MV > 5 MV would easy integration

## Slide 16: Crab Cavities for fast beam rotation
Present baseline: 3 cavity /cyomodule
4 cavity/cryomod is under study for Crab Kissing scheme

## Slide 17: Crab Cavities roadmap: beam test SPS
Test with SPS beam foreseen in 2016/17; 2 cavity/cryomod.

## Slide 18: Availability: SC links EPCs, DFBs on surface)
2150 kA
1 pair 700 m 50 kA – LS2
4 pairs 300 m 150 kA (MS)– LS3
4 pairs 300 m 150 kA (IR) – LS3 tens of 6-18 kA CLs pairs in HTS
A. Ballarino

## Slide 19: Availability 2: Magnet QPS upgrade
Removal on surface
2oo3 logic
Upgrade of IC system

## Slide 20: IT cryoplants and new LSS QRL
Avaibility: separation New Inner Triplets (and IPM in MS) from the arc cryogenics.
Keeping redundancy for nearby arc cryoplant
Redundancy with nearby Detector SC Magnets cryoplant

## Slide 21: SCRF 800 MHz harmonic: under study
200 MHz system too recent to discuss integration
P4

## Slide 22: Halo control (hollow e-lens)

## Slide 23: Controlling diffusion rate: hollow e-lens
Promises of hollow e-lens: 1. Control the halo dynamics without affecting the beam core; 2. Control the time-profile of beam losses (avoid loss spikes);
3. Control the steady halo population (crucial in case of CC fast failures).
Remarks: - very convincing experimental experience in other machines!
- full potential can be exploited if appropriate halo monitoring is available.
S. Redaelli
Developed by Fermilab

## Slide 24: Option for improved collimation: crystal
- Can crystal collimation compete with the present very good cleaning system?
- Uncertainty for the scaling to higher energy (e.g.: single diffractive losses).
- Operational challenges for the complex operational cycle (ramp, squeeze, etc...). - Some outstanding machine protection concerns must be addressed. - Can we absorb more than 1 MW in one single block?
S. Redaelli

## Slide 25: Extended Baseline operation scenario
HL-LHC Coord. Group 27 July 2013
M. Lamont

## Slide 26: LHC tunnel will be a hostile environment: robustness, removal to surface (or aside alcove?), remote handling…
 | remaining dose radiation enhancement factor w.r.t. June 2013 (6 months of cooling after RUN I)
LS2 (2019) | 3.4
LS3 (2022) | 4.3
PIC (2035) | 7
US1(2035) | 15
US2(2035) | 22.7
We need to catch up with Integration Studies and Collider-Experiment Interface
1 day workshop on remote handling  start of a WG CERN-wide

## Slide 27: HL-LHC installation fits the present plan
11 T (for DS cryolcoll.) by 2017 for P2 (ions) is difficult: a shift of six months or more would be welcome
Demo of CC in 2016-17 (with SPS beam test); 2022 is challanging; one year more would certainly welcome.
Anticipating infrastructure for LS2: an extended Winter Stop is welcome (but not mandatory)
Summary:
  an extended winter stop end of 2016; 6 months shift of LS2 with LS2 = 1.5 y;
  LS3 covering 2023-24 IS FINE for HL-LHC.
  Longer «delay» or shift would make reconsider the whole schedule (anticipating IR installation in LS2?, Merging LS2-LS3?)

## Slide 28: HL-LHC matrix: equipment, time, cost

## Slide 29: HL-LHC matrix: equipment, time, cost

## Slide 30: HL-LHC matrix: equipment, time, cost

## Slide 31: HL-LHC matrix: equipment, time, cost

## Slide 32: Conclusions
The upgrade is robust for 250 (300 ) fb-1/y
    Means to maintain or increase availability are under study
All hardware is more robust for 3000 fb-1 than it is today for 300 fb-1
Design Study finished by 2015 with the TDR
Margins are there and – once established and proved:
  Possible to decrease pile density and/or increase to 350 fb-1 (71034 of Llevel) thanks to crab kiss (CC in II &  planes) and * of 10 cm (large aperture IT & ATS)
  Increase data collection to > 4000 fb-1