## Slide 1: LS2 TDI – Project Duration Estimate
A. Perillo-Marcone (EN-STI), A. Lechner (EN-STI)
Notes: Method:
individual interviews with group leaders based on the April schedule -> to gather bottom-up data,
EN retreat on 1st July -> the aim was to bring the MTP in line with the last schedule & saving requests from the Council in June
ENMB on 26th July -> validate with group leaders the top-down arbitration

## Slide 2: Preliminary schedule
Start | End | Task | Duration
mid 2013 | mid 2015 | FLUKA + thermo-mechanical studies (material selection, conceptual design) | 2 Years
 |  | Mechanical Design | 4 years
 |  | Prototyping, testing | 
 |  | Manufacture | 
 |  | Assembly | 
 | End 2019 | Installation | 
Durations are only very rough, non committing estimates.
Highly dependent on chosen technology, jaw length, materials, etc.
The chain is not sequential (e.g. prototyping and studies overlap).
EN-STI require the establishment of a baseline by mid 2015, assuming installation by end 2019.