## Slide 1
Status of Linac4
Ion Source Review, 14 November 2013
M. Vretenar, CERN

## Slide 2
A cheering crowd celebrating the first beam accelerated by the RFQ, 13.3.2013
Open Days 2013: 2’500 visitors!
The RFQ installed in its final location in the tunnel, 25.6.13
2013 : a memorable year !
Klystrons and modulators installed in the Linac4 Hall
7.11.2013: ready for 3 MeV beam tests in the tunnel!

## Slide 3: Linac4 layout
Pre-injector (source, magnetic LEBT, 3 MeV RFQ, chopper line)
Three types of accelerating structures, all at 352 MHz (standardization of components).
Beam dump at linac end, switching magnet towards transfer line to PSB.
 | Energy [MeV] | Length [m] | RF Power [MW] | Focusing
RFQ | 0.045 - 3 | 3 | 0.6 | RF
DTL | 3 - 50 | 19 | 5 | 112 PMQs
CCDTL | 50 - 102 | 25 | 7 | 14 PMQ, 7 EMQs
PIMS | 102 - 160 | 22 | 6 | 12 EMQs
Ion species H−
Output Energy 160 MeV
Bunch Frequency 352.2 MHz
Max. Rep. Frequency 2 Hz
Max. Beam Pulse Length 0.4 ms
Max. Beam Duty Cycle 0.08 %
Chopper Beam-on Factor 65 %
Chopping scheme: 222 transmitted /133 empty buckets
Source current 80 mA
RFQ output current 70 mA
Linac pulse current 40 mA
Tr. emittance (source) 0.25 p mm mrad
Tr. emittance (linac exit) 0.4 p mm mrad

## Slide 4: Commissioning 3 MeV
ion source
RFQ
chopper line
Diagnostics line
spectrometer
beam dump
The 3 MeV injector (ion source, LEBT, RFQ, chopper line) has been commissioned with beam in March-May 2013 on a test Stand
  19.2.2013 First usable H- beam (45 keV)
  13.3.2013 Beam through RFQ
  16.4.2013 Beam through chopper line
  21.5.2013 Switch to protons (for higher intensity)
  31.5.2013 End of the beam tests, start transfer to tunnel
First 3 MeV beam on transformer: 10mA H- accelerated through the RFQ at first shot!
Hard time to get there, but commissioning completed in just 3 months!
Bunch Shape Monitor: phase profile of the bunch along the pulse
Emittance scan

## Slide 5
Transverse emittance measured for different solenoid settings.
Beam reconstructed at source output and effective space charge estimate.
16-20 mA current
0.7-0.8 mm.mrad
ε measurement
Sol
Sol
Source
Emittance from the source

## Slide 6: The Linac4 RFQ
Completed in September 2012 (some delays in design, machining, brazing).
RF conditioning in less than a week, commissioning with beam started on 13.3.2013 and completed on 28.3.
Compact and solid design, aiming at high reliability.
The Linac4 RFQ not only focuses and accelerates the beam as required, but so far it does it in a stable, reliable and reproducible way!

## Slide 7
Chart: RF power in the RFQ (kW)
| 447.71330417636244 | 441.57044735331215 | 429.53642676488789 | 416.86938347033515 | 403.64539296760364 | 390.84089579240106 | 380.18939632056242 | 369.82817978026696 | 355.63131856898434 | 346.73685045253171 | 334.1950400261141 | 325.83670100200959 | 317.68740706497658 | 307.60968147407056 | 299.22646366081938 | 285.75905433749517 | 276.69416454115088 | 265.46055619755407 | 257.63211570025805 | 246.03676041476331 | 234.96328208483047 | 209.89398836235242 | 184.501541917948
P=5E-7 mbar | 75.9259 | 74.6914 | 74.0741 | 72.8395 | 72.2222 | 70.9877 | 67.9012 | 68.5185 | 68.5185 | 66.6667 | 62.963 | 62.3457 | 62.963 | 62.963 | 60.4938 | 56.7901 | 54.9383 | 52.4691 | 45.0617 | 37.6543 | 17.284
P=1E-6 mbar | 79.375 | 78.125 | 76.25 | 76.25 | 75.625 | 73.125 | 71.25 | 71.875 | 71.25 | 69.375 | 66.25 | 60 | 65.625 | 65 | 63.125 | 58.75 | 57.5
P=3E-6 mbar | 69.1358 | 67.9012 | 67.284 | 64.8148 | 65.0307 | 65.6442 | 64.4172 | 62.5767 | 61.9632 | 61.9632 | 61.3497 | 59.5092 | 56.4417 | 53.9877
simulation | 7.1563 | 17.188 | 32.7839 | 48.2435 | 54.5276 | 57.8541 | 61.2368 | 64.074 | 66.6266 | 68.6056 | 69.9852 | 71.3126 | 72.0545 | 72.8004 | 73.059 | 73.4019 | 73.6124 | 73.7247 | 74.0014 | 74.2461 | 74.3904 | 74.6331 | 74.8637 | 75.2907 | 75.796 | 75.8823 | 76.1389 | 76.2191 | 76.7806 | 78.0017 | 78.7656 | 79.3351
RFQ transmission vs RFQ RF power
measurements and simulation
V Dimov
70-75% RFQ transmission achieved at nominal settings (<94% design value, but as expected and confirmed by simulations because of the bigger input beam emittance)
LEBT H2 gas pressure was changed to study experimentally the effect of neutralisation
March 2013

## Slide 8: Chopper and MEBT
Chopper line (MEBT), 3.6 m:
2 choppers (double meander lines on ceramic substrate) inside quads;
3 bunching cavities;
5 quadrupoles;
Steerers and diagnostics.
Chopper dump (conical)
Quadrupoles used to increase separation chopped/unchopped beam reducing the required chopper voltage (600 V).
Worked perfectly, rise time (to avoid beam loss) measured by the transfos <10 ns (waiting for more accurate time resolved measurement).
Separation of chopped and unchopped beam measured by the Wire Scanner
“hole” in the beam pulse produced by the chopper

## Slide 9
Longitudinal emittance reconstruction
BU.1 fixed
BU.2 varying
BU.3 OFF
BSM
Measurement
Reconstruction
RFQ
Chart: Buncher 2 Amplitude (A.U.)
| 1508 | 2023 | 2540 | 3050 | 3570 | 2330 | 2740 | 2230
Measurements | 36.9 | 26.67 | 24.11 | 29.87 | 40.29 | 22.43 | 25.41 | 22.5
Simulation | 36.5 | 25.55 | 22.63 | 25.73 | 37.35 | 23.55 | 22.86
Reconstructed | 36.0214 | 24.4788 | 29.9631 | 41.329
 | Expected | Recons.
ΔE (keV) | 21 | 22
Δφ (°) | 7.8 | 8.8

## Slide 10
BSM / Feschenko monitor
BSM measurements
First commissioning completed by INR team

## Slide 11: Installation in B.400
- Infrastructure (Electrical, cooling, ventilation, all cabling) completed
Waveguides and circulators installed
12 klystrons /17 installed
6 modulators /14 installed
Ion source, RFQ, MEBT line installed, HW tests completed
All safety clearances passed on 8.11.13, beam tests starting…

## Slide 12
Commissioning schedule
3 MeV from Oct. 2013
12 MeV, 50 MeV from April 2014
100 MeV from Dec. 2014
160 MeV from mid 2015
Reliability run 2016
3 MeV test stand completed

## Slide 13: Next steps: DTL and CCDTL
DTL Tank 1 assembled, under RF tests.
DTL Tanks 2 and 3 in construction and assembly.
All 7 CCDTL modules (50-100 MeV) delivered, stored and progressively under HP tests.

## Slide 14: The future ?
When are we going to connect Linac4
to the booster and with what particle?
Linac4 will be completed at end 2016.
Converting to H- the PS Booster injection takes 9.2 months (incl. 2 months cool-down and renewed cabling).
LHC will restart in 2015 and run for 3-4 years: it is very difficult to obtain an intermediate stop for Linac4 connection (although physics has plans for a 4.5 months interruption at end 2016).
Options:
(favored): connect with H- at end 2016 (intermediate shut-down for physics) or at end 2017 (early Long Shut-down).
(back-up): use Linac4 as 50 MeV proton injector replacing or in parallel with Linac2 between end 2016 (intermediate physics shutdown) and end 2018 (maximum for long Shutdown start), increasing (proton) current to 80 mA (half current and half emittance than Linac2).