## Slide 1
Status Report Installation works
ISOLDE Hall 170
HIE-ISOLDE
Erwin Siesling on behalf of the HIE integration team
68th ISCC meeting
CERN, 22 October 2013

## Slide 2
Outline
  Status Report HIE Installation October 2013:
  Progress since the last SC meeting in April
  Have there been or are there any delays
  Are we on track with regard to the planning
  What to expect for the next 6 months

## Slide 3
HIE ISOLDE installation progress

## Slide 4
Outdoor progress
Cooling & ventilation:
Cooling towers, Chillers and a large part of the tubing is in place

## Slide 5
Thank you for your attention
Compressor building 198
Cooling & ventilation and EL systems:
Steel structures, Ventilation Unit, Electrical cabinets, Pumps and Piping in place as well as large parts of the ducts and cable trays

## Slide 6
Cold Box building 199
EL systems ground floor:
False floor structure in place for the 3.3kV (Compressors power)

## Slide 7
Cold Box building 199
1st floor, metal structures and Civil Engineering:
Plenum, false floor and reservations done

## Slide 8
ISOLDE hall 170
ISOLDE hall 170:
Civil engineering, metal structures, cooling and ventilation

## Slide 9
Hall 170 ventilation systems
platform
1st extension
2nd extension
New ducts
New diffusers
ISOLDE hall 170: Ventilation ducts put in place

## Slide 10
B. 198 compressor building
Experimental hall 170
B. 199 cold box building
Cooling and ventilation systems
ISOLDE water station:
Old equipment removed, installation new pumps and piping started

## Slide 11
Civil Engineering in Hall 170
Wall to be cut
New trench to add
Platform wall has been cut to provide free passage/access cryo modules: Cleaning campagne was organised to undust equipment

## Slide 12
Civil Engineering in Hall 170
Wall to be cut
New trench to add
New trench in place for cabling into the new shielding tunnel:
Covering tent for dust protection

## Slide 13
Shielding tunnel Hall 170
ISOLDE hall 170: Civil engineering
Installation of the new shielding tunnel walls

## Slide 14
ISOLDE hall 170: Civil engineering
Installation of the new shielding tunnel walls
Shielding tunnel Hall 170

## Slide 15
Shielding tunnel Hall 170
ISOLDE hall 170: Civil engineering
Installation of the shielding door rails

## Slide 16
Metal structures Hall 170
ISOLDE hall 170: Metal structures
Modification of the future rack platform ongoing

## Slide 17
Metal structures Hall 170
ISOLDE hall 170: Metal structures
Modification of the future rack platform ongoing

## Slide 18
Access to Nicole
Metal structures Hall 170
ISOLDE hall 170: Metal structures
Modification of the future rack platform ongoing

## Slide 19
HIE Simplified Planning
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2011
2012
2013
2014
2015
2016
Civil
Main services
Cryo
CM 1&2
5.5MeV/u
HEBT
17 Dec 2012 - Q3 2014
sd
sd
Isolde Ops
shutdown
LS1
HIE installations and tests (Isolde normal operations)
Timeline:
sd
Ventilation
Demi water
Electrical syst.s
Start Isolde shutdown
17 dec 2012
End LS1:Start Low E physics
July 2014
Machine Check-Out
(Isolde normal operations)
Beam commissioning
3 months
HIE physics at 5.5MeV/u
October 2015
sd
Beam Commissioning
(Isolde normal operations)
RF
Cabling
Civil hall
We are here:
Oct 2013

## Slide 20
Activities | Delay with regard to baseline April 2013 |  | building | On track present planning | Critical
Cooling & ventilation: Installation units and piping | 4 months | Introduced by the contractor. New planning in place | 198, 199, 170 | Yes | No 14 March ready for Isolde Low Energy startup
Electrical systems: service buildings | 2 months | Due to CV contractor delay | 198,199 | Yes | No
Integration tunnel infrastructure | - | Open actions on metal structure, vacuum and water piping routing, He shielding, CM supports | 170 | Yes | Yes Critical: tunnel infrastructure + cable trays need structure in place by end Jan’14
Metal Structures: rack platform | 2 months | Due to LS1 load | 170 | Yes | No
Metal Structures: jumper boxes platform | 4 months | Design needs finishing: Data missing from Cryo due to late Cryo Line procurement | 170 | Yes | Yes Critical: cable trays need platform in place end Jan’14
Civil Engineering: trench | 2 months | Unforeseen difficulties with trench cutting | 170 | Yes | No
Civil Engineering: tunnel | 2 months | Due to trench delay | 170 | Yes | No
Cabling: trays and cables | 3 months | Due to late modif rack platform + service buildings CV installations delayed | 199, 170 | Yes | No
Cryogenics: late cryo distribution line | - | Late installation dewar, distribution line & jumper boxes (sept ’14) | 199, 170 | Yes | Yes Critical: very tight with commissioning plan & physics oct’15
Planning: delays and critical

## Slide 21
Metal structures
Platforms Cryo Jumper Boxes: To be in place early 2014

## Slide 22
Tunnel Infrastructure
Tunnel structure and infrastrucure installation to start early 2014

## Slide 23
Coming up:
CV units 199, air ducts (remaining 170), diffusers and smoke extractors B198, 199 and 170: Oct-Nov-Dec 2013

## Slide 24
Installation top walls shielding tunnel: Dec 2013
Coming up:

## Slide 25
Coming up:
Cable trays buildings, tunnel and HEBT: Nov 2013 – March 2014

## Slide 26
Conclusions
  Status Report HIE Installation October 2013:
  Progress since the last SC meeting in April High activity in the hall and service buildings
  Have there been or are there any delays Yes. Indicated and co-activities planning adapted
  Are we on track with regard to the planning Yes. Despite delays we are still in line with the overall schedule which aims for low energy physics during 2014 and HIE physics as of Oct 2015. Critical paths for some activities are being addressed

## Slide 27
HIE ISOLDE Integration
GS/SE : DANIEL PARCHET, ELISEO PERES-DUENAZ
EN/MEF : STEPHANE MARIDOR, ELEFTHERIOS ZOGRAFOS
BE/ABP : FREDERIK WENANDER
BE/OP : DIDIER VOULOT
PH/SME : MARIA BORGE, MAGDA KOWALSKA
EN/HDO : YACINE KADI
BE/RF : MATTEO PASINI, MATTHEW FRASER, DANIEL VALUCH, WALTER VENTURINI, LUCA ARNAUDON
EN/CV : PAUL PEPINSTER, BENOIT LACARELLE, FREDRIC BORRALHO
EN/EL : RENE NECCA, JEAN-CLAUDE GUILLAUME, GEORGI GEORGIEV, JEAN-PIERRE BILLON-GRAND EN/EL
TE/CRG : NICOLAS DELRUELLE, JOS METSELAAR
EN/STI : RICHARD CATHERALL, ANA-PAULA BERNARDES
GS/DI : CYRILLE BEDEL
TE/MSC : YANN LECLERCQ, LLOYD WILLIAMS
DSG/RP : JOACHIM VOLLAIRE, SANDRA GIRON, ALEXANDRE DORSIVAL
TE/ABT : BRENNAN GODDARD

## Slide 28
Co-activities planning HIE ISOLDE installation:

## Slide 29
Co-Activities B198

## Slide 30
Co-Activities B198

## Slide 31
Co-Activities B199

## Slide 32
Co-Activities B199 & Safety

## Slide 33
Co-Activities B170

## Slide 34
Co-Activities B170

## Slide 35
Co-Activities B170

## Slide 36
Co-Activities B170

## Slide 37
Co-Activities B170

## Slide 38
Co-Activities B170

## Slide 39
Co-Activities B170