## Slide 1: Status of the activities for LS1 and HIE-ISOLDE Design Study
Richard Catherall
EN-STI-RBS
ISOLDE Collaboration Committee
22nd October 2013
Alignment
VITO Beam line modification

## Slide 2: LS1 Activities
Target area
  Robots
  PAD/MAD
  Medicis
  Hot Cell
Hall
  REX
  TSR@ISOLDE
  RILIS

## Slide 3: Robots
Over 260 cycles performed during the CERN open days demonstration
  ~7 years of operation
  No faults
  But…
M. Vagnoni, J-L Grenard

## Slide 4
Phase III – Services modification
Overview of the situation
MAIN TASKS TO BE CARRIED OUT
Dismantling and installation of new CV pipes and ducts
Dismantling and installation of new electrical cables and cable trays
RADIOPROTECTION ASPECT
Higher collective and individual doses than expected
Main reason for higher dose rates in the area:
  Activation of certain equipment and material near the Faraday Cages on both GPS and HRS sides
    Ducts, pipes
    Concrete walls
    Cable trays
CONSEQUENCES
Major increase of the collective dose concerning phase 3 near the GPS Faraday cage
2313 H.µSv
ALARA Committee
March 2013
7181 H.µSv
New estimation
September 2013
Factor 3
Duc Duy Phan

## Slide 5
Phase III – Services modification
Overview of the situation
ADDITIONAL CONTROL MEASURES IMPLEMENTED
Use of a saber saw to reduce the time of intervention and to maintain a safe distance from the cutting points
Installation of a lift truck to allow the mechanical support of the ducts and pipes during cutting work, thus avoiding human intervention for the handling
Phasing of the work in order to dismantle the hot points first
Limitation of the individual dose to 600 μSv
Duc Duy Phan

## Slide 6: PAD/MAD Installation
Will be installed in January
  Gives more time for installation of robots
  Allows for the modification of the corridor for future hot cell
  Safety chain checks start in February

## Slide 7: Groundbreaking
September 4th 2013
T. Stora

## Slide 8: Building
New services for Bld 179 done.
Earth removal started.
“cold building” finished in Feb 2014 (1 month shift).
T. Stora

## Slide 9: Earth Removal
T. Stora

## Slide 10: External partners
External partners :
Dr. Forni (Clin. Carouge)
L. Vouga, Prof. P. Morel, Prof. L. Buehler, Prof. Y. Seimbille, Prof. O. Ratib (HUG, Geneva), Prof. D. Hanahan (ISREC-EPFL, Lausanne)
Prof. J. Prior, Dr. F. Buchegger (CHUV, Lausanne)
Prof. M. Huyse, Prof. P. van Duppen (Univ. Leuven)
Prof. S. Lahiri (SINP, Kolkata)
Prof. Piperkova (Nat’l oncology hospital, Sofia)
Prof. Dos Santos (FCUL, Lisbon)
Budget so far : (CERN+external+in-kind) : 3.2 MiCHF
New in-kind + grant requests underway
PHASE I Commissioning : No beam (end 2015)
PHASE II Start up with light targets for retour d’experience (2016)
PHASE II B Production with light targets (mid 2016)
PHASE III Extending to heavy targets up to Tantalum (tentative end 2016)
PHASE IV Collection of short lived alpha emitters (149Tb) (tentative 2017)
PHASE IVB Operation with Lasers
PHASE V Operation with Uranium targets/possible proton beam upgrade (tentative 2018)
T. Stora

## Slide 11: Hot cell layout
Production on schedule
Factory acceptance tests planned for December 2013
Modification of building 179 to start in next few weeks
A. Stadler

## Slide 12
REXEBIS and REXTRAP
1. Scheduled electron cathode tests for autumn 2013 postponed to spring 2014
  Due to lacking infrastructure (water, LHe, controls etc).
2. Repair of REXEBIS magnet cryostat initialized
Present LHe holding time 6 days and could fall abruptly (nominal 14 days).
  Last repaired 2005 by external firm Ice Oxford; this time in-house repair.
Major and risky job; complete EBIS needs to be dismantled.
Goal: EBIS re-assembled by March 2014.
3a. Incomplete and incorrect drawings of REXEBIS now redone in 3D
b. Production of spare collector (critical EBIS part), gun and inner structure
Spin-off from TwinEBIS
4. Modification of injection FC for REXTRAP Inherent design error mitigated; new version being evaluated.
F. Wenander

## Slide 13
TwinEBIS test setup
EBIS team: M. Breitenfeldt, J. Thiboud
* Labview system for DC control and vacuum readout finished.
* Bakeout system, power supplies, HV gun rack installed.
* Remaining mechanical internal parts in production. (act as spares for REXEBIS)
* Vacuum control system (FPGA) in production. Assistance P. Fernier.
* M. Breitenfeldt COAS during autumn 2013 => major push!
Long-term goals:
0. Spare for REXEBIS
Higher electron current
Better cathode lifetimes
Test-bench for EMILIE project
Optimization of extracted ion pulse

## Slide 14
Funding of EBIS development activities
1. Struggling to extend A. Shornikov’s presence at CERN. His CATHI fellowship is ending 30/6-2014.
2. Can only fund M. Breitenfeldt to Feb 2014. TwinEBIS activities
will thereafter be reduced.
* ENSAR-2 application submitted for continuation of the charge-breeder upgrade development. Approval, granted funding and starting date unknown.
* Open for external contributions and suggestions how to prolong 1 and 2 above.
Good progress thanks to excellent members at the team!
F. Wenander

## Slide 15
integration study
* Preliminary results presented at IEFC 31/7-2013
* Final report submitted to Director of accelerators and department leaders 28/8-2013
* Full presentation and executive summary can be obtained upon request (F. Wenander)
TSR elements evaluated by CERN specialists
In general a positive response and supportive response from the CERN groups
Next steps
* Awaiting feedback from CERN management
* workshop at CERN 14 Feb 2014
Two approaches 1. CERN homologation (full-fledged ‘standardization’)
2. Keep-system-as-is (low-budget option with minimal changes)
E. Piselli, E. Siesling, F. Wenander

## Slide 16
* The radiological concern of importing the ring is minimal.
* Well advanced civil engineering plan with associated infrastructure exists.
* No technical show stoppers for the implementation – standard solutions identified.
CERN integration proposal
integration study
a. The first cost and manpower estimate, should cover most/all parts of the move and are believed to be conservative. The CERN support groups claim that the cost of some WPs can be reduced if the allocated budget so requires. However, no contingency included.
b. Most CERN groups have insisted on hardware changes and CERN standardization and discourage a 3 years transition period with temporary solution as that would inflate the costs.
Total cost and manpower for transfer and integration into a CERN facility:
15.2 MCHF 27.5 FTE (man year)
Keep-system-as-is
a. Would need to keep all subsystems as they are since many are interlinked with the control system.
b. Would have limited or in some cases no support by CERN groups; longer dependence on MPIK Heidelberg.
c. Power converters, vacuum, magnets, RF and e-cooler could in principle be imported as such.
d. Improved electrical ring safety is mandatory if the ring is imported as is.
The approximate cost and manpower need for the Keep-system-as-is scenario are:
11.8 MCHF 17.1 FTE (man year)
The cost saving might appear low but it should be kept in mind that:
* The main cost drivers for a TSR at ISOLDE are the injection line, buildings and infrastructure.
* Some spares, complementing parts and replacement parts are absolutely necessary.
* Includes the mandatory electrical protection of magnets connections.
* Includes sensitivity improvement of the beam diagnostics.

## Slide 17: 5 μs beam gating test
Narrow laser-ion bunch width + micro beam gate tests
Laser-ion
time structure:
5 μS FWHM!
Ga mass
marker
High Ω cavities:
Thin graphite 
Pyrolytic graphite 
Sigradur ‘glassy’ graphite ☐
Pulsed heating for higher voltage ☐
Ga
1 μs beam gate
is possible!
= 100 x
Surface ion suppression!
RILIS
ionization
scheme
Solid-state switch
~ 500 V @ 10 kHz
B. Marsh, V. Fedosseev

## Slide 18: RILIS machine protection: built and being tested
Preparation for
‘on-call’
RILIS operation
  Hardware to control multiple laser interlocks and shutters is assembled by STI-ECE
  Laser dye leak detection
  Offline testing has begun
  Installation in January 2014
B. Marsh, V. Fedosseev

## Slide 19: Overview
Different Technical Advances
  Targets
  Front End
  Beam Quality
    REX EBIS
    Off-line
    HRS
  Infrastructure
    Ventilation
Time line
  The Design Study report
  REX-EBIS planning
  Implementation
HIE-ISOLDE workshop: The Technical Aspects

## Slide 20: Targets: RIB Intensity Increase
Separated heating and containing design: electro-thermal study, prototype and experimental tests
CATIA model
Graphite container simulations
Sigratherm screen simulations
Graphite heater with Sigratherm screen
Bare Graphite heater
CATIA model
Notes: One of the major problems connected with the actual target heater is the presence of cold spot on the extremity which cause re-condensation of the nuclei affecting the in target production. A new design has been tested: the containing and the heating functions are separated allowing a design optimized for the thermal issue. This concept was, at first tested via numerical analyses and then, prototyped and validated via experimental tests. Numerical and experimental data showed good agreement and proved the design to be successful for thermal uniformity.
The second step was the test of the new concept wrapped in a graphite solid mousse. The results proved to be even better for the thermal point of view but the assembly is challenging therefore a new rigid graphite screen has been designed and purchased.
Soon this soultion will be tested.
The use of graphite is important also in term of waster reduction considered the future increase of proton intensity.

## Slide 21: Targets: RIB Purification
Neutron spallation source design study:
Heat Shield
UCx
Converter
Container
Cooling
Pipe
Graphite Block
Online tests at TRIUMF in 2014.
Energy: 500 MeV;
Intensity: 100uA.
Notes: A new neutron converter design study is on going. It is forseen to be tested on line at TRIUMF in order to have higher power (in view of HIE ISOLDE).
The aim of this device is to have beam purification from neutron-deficient isobaric contamination. A neutron-converter uranium target largely excludes the production of these contaminants.
The main issue, for the moment, is the space constraint imposed by TRIUMF which doesn’t allow great results.
Discussion are undergoing about possible constraint release or eventual delay of the project.

## Slide 22: Front End: Pre extraction prototype
60 kV
57 kV
Ground
- Without electrode movement mechanism
- Electrode head exchanged with target unit without human intervention
- Intermediate voltage works as focalization lens
- Intermediate electrode customizable for each target unit
J. Montano

## Slide 23: Front End: Geometrical optimization
… A numerical optimization of the geometry has been performed. The criteria were mostly based on extracted beam quality and minimum losses
… prototypes have been constructed and are under experimental tests to validate the results
J. Montano

## Slide 24
Charge breeder upgrade for HIE-ISOLDE
 | HIE-ISOLDE / TSR@ISOLDE charge breeder | REXEBIS
Electron energy [kV] | 150 | 5
Electron current [A] | 2-5 | 0.2
Electron current density [A/cm2] | 1-2x104 | 100
New EBIS – High Energy Compression and Current (HEC2) EBIS
Main challenge – produce the high compression electron beam
Goal – have a reliable design of the HEC2 electron gun at earliest possible stage
Design parameters
Realization – in a joint effort with BNL, based on BNL design and infrastructure
(BNL Test-EBIS), partly funded and manned by CERN
EBIS team: CATHI fellow A. Shornikov

## Slide 25
Progress since April
Apr
May
Jun
Jul
Aug
Sep
Oct
The gun manufactured at CERN
Gun shipped to BNL
Gun mounted on Test EBIS
Conditioning EBIS
Preparing for tests
First complete EBIS simulation with high compression beam
Work at BNL
Charge breeder upgrade for HIE-ISOLDE
BNL TestEBIS
HEC2 gun chamber
Cathode
Anode
Magnetic
shielding
HEC2 gun
EBIS team: CATHI fellow A. Shornikov
HEC2 gun at TestEBIS

## Slide 26
Electron beam simulations
*Major effort benefiting: HEC2 gun design and verification
            REXEBIS current increase
* So far mainly 2D results using Field Precision software
* Complete BNL TestEBIS with HEC2 gun simulated – major feat!
* Preliminary 3D simulation results using CST Microwave Studio obtained
* Cluster simulations using up 128 cores and 1 TB memory in the pipeline
EBIS team: PhD R. Mertzig
Allows to break the symmetry (e.g. misalignments)
Classical approach
Relativistic approach
Simulation and optimization of a 10A electron gun with electrostatic compression for the HEC2 gun
Results: Limited beam scalloping >2E4 A/cm2 in full field
optimization of collector potential and geometry in process
4 mm
Electron trajectories
Drift tube
Cathode
Anode

## Slide 27: ISOLDE offline separator #2
Purpose: testbench for the validation of principles regarding the High Resolution Separator upgrade
ISOLDE offline #2 (current status)
Status on 11/10/2013 : FE and MG90 operational, RFQ under assembly
Detailed definition of experimental setup
Dipole characterization
Magnetic field mapping
Ion source characterization
Separation test
RFQCB test
Foreseen layout of ISOLDE offline #2
Courtesy of Stefano Marzari
M. Augustin

## Slide 28: High Resolution Separator (HRS) upgrade design study
Moving of Radio Frequency Beam Cooler (RFQBC) foreseen more upstream of beamline, in the separator room.
 Constraints regarding the available space in separator room and regarding the positioning of already existing beamlines upstream and downstream
Layout proposal schematic
Low beam emittance at exit of RFQBC
Beam shaping before magnetic stages with quadrupoles
120º dipolar separator magnet (including quadrupolar and sextupolar components)
90º dipolar separator magnet
Existing beamline
Existing beamline
quad.
M. Augustin

## Slide 29: High Resolution Separator (HRS) upgrade design study
© COSY simulation of HRS proposed layout : x-axis
© COSY simulation of HRS proposed layout : y-axis
Separation power computation with © Octave
Considered mass M=100
ΔM/M=2.10-4
Computation performed at 3rd order
Next steps :
Tuning for compensation of aberrations at 3rd order on MG120
Tuning of quadrupole and sextupole components on MG90 °
© Opera simulations of MG120°
M. Augustin

## Slide 30: Ventilation
Tunnel and HT Room surveys to measure existing air Leaks
Access Door
10
÷
30 mm
0.4 ÷2.5 m/s
On-field activity to measure the entities and positions of the main sources of air leaks present inside the ISOLDE tunnel. Results in terms of dimensions and air speed
200 mm
50 mm
2.2 m/s
Cable trenches
150 mm
1 m/s
Cable trenches
6 m/s
7 m/s
The measures show the non optimized leak tightness of the Tunnel.
As a conclusion: an accurate activity of gaps sealing is amended as necessary. This measure together with the:
  Stop of the air supply during beam mode
  Installation of access airlocks
  ΔP optimization
  will move in the sense of reducing the activity released in in atmosphere
A. Polato

## Slide 31: Ventilation
Tunnel and HT Room surveys to measure existing air Leaks
Verification of the correct pressure cascade between HT room and ISOLDE Tunnel, to confirm that the traces of activation in the HT Room are not caused by an air backflow (but most probably by direct radiations in the room)
Boris Tube towards GPS Faraday Cage
Boris Tube towards HRS Faraday Cage
Temporary Confinement of the HRS Boris tube. A tracing element (smoke) has been injected in it to see the direction of the flow
The test showed that the tracing element was flowing towards the Faraday Cage, hence no air backflows are present (in accordance with the initial evaluations)
As a conclusion: due to the contamination present in the room, a confinement system of the HT room vs. the Instrumental hall will be proposed in the Design Study
SMOKE TEST MOVIE
(INTERNET CONNECTION AND MOVIE PLAYER NEEDED)
H. Sabri
A. Garcia
Precious help from:

## Slide 32: The Design Study Report
Document describing all the issues addressed throughout the design study period
High Intensity
  Targets; thermal analysis, design and materials
  Front ends
  High voltage
  Operation
Infrastructure
  Beam dumps
  Radiation protection
  Ventilation and cooling
  Vacuum
Beam Quality
  HRS magnet design
  RFQ Cooler
  New REX-EBIS
Cost Summary and Planning
Report: Deliverable for the Autumn 2014

## Slide 33
 | Phase | Part | Task
A | Gun gen1 | Gun | Demonstrate >1.5E4 A/cm2 in trapping region.
B | Gun gen1 | Collector | Suppress backscattered electrons.
C | Gun gen1 | Trap | Detect low level RF that will inhibit cryogenic operation.
D | Gun gen2 | Gun | Suppress discharges at gun to allow for cw operation.
E | Gun gen2 | Collector | Extract the ion beam.
F | Gun gen2 | Collector | Suppress backscattered electrons for cw beam.
G | Gun gen2 HV | Gun | Allow e-beam acceleration to 150 keV.
G | Concept | Surroundings | Shield 5 T magnet stray field.
H | Concept | Vacuum | Attain vacuum performance with either warm or cryogenic concept.
Conditions for above: 1. Continued collaboration with BNL
2. A. Shornikov following the project
3. ENSAR2 application granted and fully funded
Tentative tasks and timeline for breeder upgrade
2013-2014
2015-2016
2015
By end of 2016 all critical items could be verified -> solid foundation for design.
Thereafter a 2 years realization phase would follow (manpower and cost tbd).
F. Wenander

## Slide 34: Implementation
2014 Final Report
2014/2015
Separation of ventilation systems.
Installation of airlocks
LS2 (2018)?
New FE’s
Beam dumps
Shielding
New HRS
…
2016/2017?
New HT power supplies/modulator
New EBIS??
Vacuum systems
Targets

## Slide 36
Quadruples
Switchyards
Range of the measurement done by SU-EXP –
quadroples and switchyards

## Slide 37
Target Zone
Parking in front of the 198, 199, 170 buildings
GPS/HRS area
Range of the measurement done by SU-EXP –
levelling travers

## Slide 38
Results: Central Line - graphs
~10mm step – already existing in 2007
See next slide

## Slide 39
Results: Central Line - numbers
Name | Horizontal offset | Vertical offset | Name | Horizontal offset | Vertical offset
 | [mm] | [mm] |  | [mm] | [mm]
HRS.MAG90.E | --- | 1.0 | CB0.QP20-30.E | 2.5 | 6.0
HRS.MAG90.S | --- | 2.2 | CB0.QP20-30.S | 2.6 | 6.6
HRS.DB470-490.E | --- | 1.4 | CB0.QP40-50.E | 3.7 | 15.3
HRS.DB470-490.S | --- | 0.8 | CB0.QP40-50.S | 2.9 | 15.9
HRS.MAG60.E | --- | 1.2 | CB0.SW.E | 2.1 | 16.1
GPS.MAG70.E | --- | 1.5 | CB0.SW.SC | 2.4 | 17.2
GPS.MAG70.E | --- | 2.2 | CC0.QP20-30.E | 1.9 | 17.5
GPS.QP520-530.E | --- | 2.1 | CC0.QP20-30.S | 2.7 | 17.4
HRS.MSW.E | -0.6 | 4.3 | CC0.QP40-50.E | 1.3 | 17.7
GPS.MSW.E | 3.8 | 5.1 | CC0.QP40-50.S | 0.5 | 17.5
GPS/HRS.MSW.S | 3.6 | 5.8 | CA0.SW.E | 0.5 | 6.2
CA0.QP40-50.E | 2.9 | 5.3 | CA0.SW.SC | 0.5 | 5.7
CA0.QP40-50.S | 1.8 | 5.1 | CD0.QP20-30.E | 0.5 | 17.6
CA0.SW.E | 0.5 | 6.2 | CD0.QP20-30.S | -0.4 | 16.1
CA0.SW.SC | 0.5 | 5.7 |  |  | 
Horizontal and vertical offsets are given to the theoretical beam line. Positive sign of the horizontal offset means that, the measured point is on the right from the theoretical beam line (looking downstream). Positive sign of the vertical offset means that, the measured point is above the theoretical beam line. Nominal position in XYccs of each line has been taken from the autocad drawing of Isolde/Hie-Isolde provided by Didier VOULOT. Nominal position in H has been determined according to the same drawing as well as the calculated slopes.
REMARK: Final values of the offsets might change slightly after recalculation according to the optic files which will be provided by Isolde Team

## Slide 40
Results: Left Lines – numbers
Name | Horizontal offset | Vertical offset
 | [mm] | [mm]
LA0.SW.SGG | -3.8 | 6.9
LA1.QP20-30.E | -1.9 | 7.6
LA1.QP20-30.S | -1.0 | 7.8
LA1.QP40-60.E | 0.6 | 8.2
LA1.QP40-60.S | 0.7 | 8.2
LA0.SW.SG | -0.7 | 7.1
LA2.QP20-40.E | -0.8 | 7.6
LA2.QP20-40.S | -0.1 | 8.6
CC0.SW.SG | 1.9 | 17.5
LC0.QP20-30.E | 1.6 | 15.4
LC0.QP20-30.S | 1.4 | 17.0
Name | Horizontal offset | Vertical offset
 | [mm] | [mm]
CA0.SW.SG | -0.7 | 5.5
LA0.QP20-40.E | -0.9 | 6.2
LA0.QP20-40.S | -0.3 | 6.6
LA0.SW.E | -0.7 | 7.9
LA0.SW.SC | 0.3 | 6.8
LA3.QP20-30.E | -1.9 | 6.7
LA3.QP20-30.S | -2.6 | 8.3
LA1, LA2, LC0
LA0, LA3

## Slide 41: Alignment
The following reasons contributed to the decision not to re-align the beam line during the LS1 period:
  Consecutive delays:
    Cleaning had to be done, Absence of J. Thiboud
  The current workload on-going at ISOLDE is already a cause for concern with respect to the start up next year.
  The clash with HIE-ISOLDE work in the hall
    Especially near the platform
  The uncertainty in improvement of beam transport
  REX
Counter measures
  Will open 1 or 2 switchyards to better understand their alignment
  Implement automatic beam tuning
    Resources

## Slide 42: Technical and Safety Review of the RB0 upgrade (VITO line) held on September 3, 2013.
Tim Giles (optics and beam lines)
Gerrit Jan Focker (beam instrumantation)
Ana Paula Bernardes (safety)
Jean Christophe Gayde (survey)
Erwin Siesling (integration)
Didier Voulot (TSO and REX compatibility)
Giovanna Vandoni (vacuum)
Joachim Vollaire (radiation protection)
Maria Garcia Borge (physics)
Richard Catherall (chairman, ISOLDE technical coordination)
  Technical review panel:
  INTC committee:
Physics cases endorsed (26 June 2013)
3 proposals, 2 LoIs submitted in September 2013
Upgrade approved by the Technical committee
Physics endorsed by the INTC committee
M. Stachura

## Slide 43: ASPIC → VITO (upgrade, not a new beam line!)
ASPIC
ViTO
M. Stachura

## Slide 44: Space around the experiment Access and escape routes (all dimensions respected)
401
3070
1598
930
1199
1128
1429
376
690
377
35°
30°
M. Stachura

## Slide 45: Radiation
“RP requests to be present when the first manipulation of the beamline takes place, in particular when the vacuum beam pipe will be opened. The standard safety file, as it is known from other ISOLDE beamlines needs to be filled in and submitted but other than that no additional steps are required before the physical start of work at the beamline. I don’t see an impact from a radiation protection standpoint in a slight modification of the beam line optics. “
8Li, 21Na, 23Mg, 31Mg, 33Mg, 33Na, 35Ar, 58Cu, 73Se, 74Cu, 77Br, 80Br, 111Ag, 111Cd, 111In, 140La, 147Ga, 172Lu
(with and without shielding and for 1ms and 1wk of cooling period).
Whenever listed in SR 814.501, accumulated amount is below 1LA.
The new monitoring system will cover more precisely this part of the hall.
Most of the accumulated activity will be removed during / after irradiation.
Very small quantities of radioactivity will be handled.
The requested isotopes and their isobaric contaminants – mostly short-lived.
  FLUKA simulations done for:
  From Joachim Vollaire:
M. Stachura

## Slide 46: Magnetic Field
Minimal influence on HIE-ISOLDE, REX, TAS, WITCH and ISOLTRAP
Local field of Max. 0.3 T
Magnetic field of WITCH: members of WITCH in VITO collaboration, willing to switch off the magnet for the time of β-NMR experiments
Magnetic field of REX: not an issue for beam transport at VITO
46
Chart: 
| 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500
0 | 9 | 0.19936 | 0.079609 | 0.032363 | 0.015432 | 0.008381 | 0.005011 | 0.003219 | 0.002185 | 0.001548 | 0.001136 | 0.000858 | 0.000663 | 0.000523 | 0.00042 | 0.000342 | 0.000282 | 0.000235 | 0.000199 | 0.000169 | 0.000145
25 | 8.3694 | 0.39401 | 0.089577 | 0.033332 | 0.015586 | 0.008416 | 0.005021 | 0.003223 | 0.002186 | 0.001549 | 0.001136 | 0.000858 | 0.000663 | 0.000523 | 0.00042 | 0.000342 | 0.000282 | 0.000235 | 0.000199 | 0.000169 | 0.000145
50 | 0.80859 | 0.28659 | 0.079476 | 0.031229 | 0.015031 | 0.008244 | 0.00496 | 0.003198 | 0.002176 | 0.001544 | 0.001134 | 0.000856 | 0.000662 | 0.000523 | 0.000419 | 0.000342 | 0.000282 | 0.000235 | 0.000198 | 0.000169 | 0.000145
75 | 0.1335 | 0.095707 | 0.048305 | 0.024122 | 0.012981 | 0.007549 | 0.004695 | 0.003087 | 0.002124 | 0.001519 | 0.001121 | 0.000849 | 0.000658 | 0.00052 | 0.000418 | 0.000341 | 0.000281 | 0.000235 | 0.000198 | 0.000169 | 0.000145
100 | 0.046334 | 0.0396 | 0.02685 | 0.01661 | 0.010206 | 0.006442 | 0.004218 | 0.002867 | 0.002017 | 0.001463 | 0.001091 | 0.000832 | 0.000648 | 0.000514 | 0.000414 | 0.000338 | 0.00028 | 0.000234 | 0.000197 | 0.000168 | 0.000144
125 | 0.021734 | 0.019837 | 0.015531 | 0.011093 | 0.007631 | 0.005227 | 0.003627 | 0.002567 | 0.001859 | 0.001377 | 0.001041 | 0.000803 | 0.000631 | 0.000503 | 0.000407 | 0.000334 | 0.000277 | 0.000232 | 0.000196 | 0.000167 | 0.000144
150 | 0.012002 | 0.011304 | 0.009564 | 0.007493 | 0.005614 | 0.004126 | 0.003025 | 0.002234 | 0.00167 | 0.001267 | 0.000976 | 0.000763 | 0.000605 | 0.000487 | 0.000396 | 0.000327 | 0.000272 | 0.000228 | 0.000194 | 0.000166 | 0.000142
175 | 0.00735 | 0.007044 | 0.006241 | 0.005194 | 0.004143 | 0.003223 | 0.002479 | 0.001905 | 0.00147 | 0.001143 | 0.000899 | 0.000714 | 0.000574 | 0.000466 | 0.000382 | 0.000317 | 0.000265 | 0.000224 | 0.00019 | 0.000163 | 0.000141
200 | 0.004836 | 0.004685 | 0.004274 | 0.003707 | 0.003094 | 0.002517 | 0.002017 | 0.001605 | 0.001276 | 0.001017 | 0.000816 | 0.000659 | 0.000537 | 0.000441 | 0.000365 | 0.000305 | 0.000257 | 0.000218 | 0.000186 | 0.00016 | 0.000138
225 | 0.003355 | 0.003273 | 0.003046 | 0.002719 | 0.002348 | 0.001978 | 0.001639 | 0.001344 | 0.001098 | 0.000896 | 0.000733 | 0.000602 | 0.000497 | 0.000413 | 0.000345 | 0.000291 | 0.000246 | 0.00021 | 0.00018 | 0.000156 | 0.000135
250 | 0.002424 | 0.002377 | 0.002243 | 0.002045 | 0.001812 | 0.001569 | 0.001336 | 0.001124 | 0.00094 | 0.000784 | 0.000653 | 0.000545 | 0.000457 | 0.000384 | 0.000324 | 0.000275 | 0.000235 | 0.000202 | 0.000174 | 0.000151 | 0.000132
275 | 0.00181 | 0.001781 | 0.001698 | 0.001573 | 0.001421 | 0.001257 | 0.001094 | 0.000942 | 0.000804 | 0.000683 | 0.000579 | 0.000491 | 0.000416 | 0.000354 | 0.000302 | 0.000259 | 0.000223 | 0.000193 | 0.000167 | 0.000146 | 0.000128
Z [cm]
R [cm]
B total[T]
Based on WITCH 9T Stray Field
(provided by M. Breitenfeldt)
9T – max magnetic field
6T – magnetic field during experiments
3T – when WITCH on standby
VITO pumping zone: 10-4 T
M. Stachura

## Slide 47: Alternative location of the VITO beam line
RC lines (behind NICOLE or RC2 → switchyard → VITO line) – possible conflict with on-going works
  Alternative location:
Setting up a new line
Large budget required
At least 8.5 m of free space required
Problems with lasers: smaller focusing on larger distances, lower laser power due to larger amount of optics, bigger vibration of the laser beam, considerable additional budget
Beam tuning more difficult ( ideally 4 mm beam at the entrance of the β-NMR setup)
RC region is currently space for low background experiments (permanent decay station), which is not compatible with PAC type of ion implantations
If moving becomes necessary then rather upstream (GLM, GHM), old control room access less critical, zone of higher background
  Disadvantages:
M. Stachura

## Slide 48: VITO Beam line
SUMMARY The panel would like to congratulate the VITO Collaboration on their excellent preparation in anticipation of this review and the quality of their presentations. It is clear that the proponents have thoroughly investigated both the installation and integration of this modified beam line. From a technical point of view, no justified objections to this installation were raised. The availability of a dedicated beam line for laser-induced nuclear orientation along with ASPIC and B-NMR set-ups can only be of benefit to the physics program at ISOLDE. The panel recommends that the ISCC and INTC support this initiative by the VITO Collaboration.

## Slide 49
Only 38 weeks to go before protons to ISOLDE!
Thank you for your attention