## Slide 1: Overview of the commissioning of the S45
Boris Bellesia

## Slide 2: Outline
1st Commissioning of S78: April-July 2007
Overview of the circuit commissioning procedure for S45
Achievements of S45 PT:
  Test progress by procedure steps
  Efficiency: PT and Cryogenics
  Results: Main circuits / Groups
  Results: energies
Main outcomes of the review of the 28th Feb 08
Conclusion

## Slide 3: From S78 to S45
Jan. ‘07
PT S78
20th April
11th Jul.
Cooldown/Warm up S78
Circuit types | Sector 78 n. Circuit | LHC
13 kA | 3 | 24
RQX | 1 | 8
Independently Powered Dipoles | 2 | 16
Independently Powered Quads | 7 | 78
600A with Energy Extraction | 27 | 202
600A Energy Extraction in the Converter | 20 | 136
600A no Energy Extraction | 9 | 72
80-120A Correctors | 37 | 284
60A Dipole Orbit Correctors | 94 | 752
Total | 199 | 1572
Minimum required - recommendations of Magnet Performance Panel (04/07) |  | 
Limited Current: RB (2 kA), RQD (6.5 kA), RQF (350 A) | 3 | OK
RD2 up to 6kA | 1 | OK
RQ4 and RQ5 up to nom. (3590A and 4210A) | 2 | Up to NOM
14 Line-N, 3 spool pieces, 2 MQTLH (600A w. EE) | 19 | DONE
Three Line-N Circuits (600A) NOEE | 3 | 2
Q4 and Q5 dipole orbit correctors | 7 | OK
60A dipole orbit correctors | 5 | OK (60)
Total | 40 | 
Jul. ‘07

## Slide 4: Outline
1st Review
Outcomes of the review implemented in the HC of the S45
Test automatization (sequencer optimization)
Organization improvement (Field and CCC)
Tools to optimize commissioning (e.g. the circuit viewer)
Procedures optimization (version released Nov.07)
Clear procedure for assure safety – equip. and people (Safety day Sep.07)
Jan. ‘07
PT S78
20th April
11th Jul.
Cooldown/Warm up S78
Jul. ‘07

## Slide 5
Commissioning of S45: circuit overlook
Feb‘08
PT S45
26th Nov.
19th Feb
Cooldown/Warm up S45
July. ‘07
Jan. ‘07
20th April
11th Jul.
Cooldown/Warm up S78
PT S78
Circuit types | Sector 45 n. Circuit | LHC | Sector 45 n. Circuit comm.
13 kA | 3 | 24 | 3
RQX | 1 | 8 | 0
Independently Powered Dipoles | 3 | 16 | 3
Independently Powered Quads | 13 | 78 | 13
600A with Energy Extraction | 24 | 202 | 24
600A Energy Extraction in the Converter | 14 | 136 | 14
600A no Energy Extraction | 9 | 72 | 2
80-120A Correctors | 35 | 284 | 29
60A Dipole Orbit Correctors | 94 | 752 | 94
Total | 196 | 1572 | 182
NOT Commissionable | 
IT circuits – RQX+ 6 DOC 600A, 1 600A, 5 120A corr. | 13
RCBYV5.R4B1 (120A DOC of Q5) | 1
Total | 14

## Slide 6: S45: Circuit commissioning procedures
Main circuits – RB/RQD-F/MS-DSquads/Separation Dipoles
Correctors – 600A w. and no EE/Dipole Orbit Correctors
Targets redefinition (W6):
  To commission all the hardware (PC,PIC,QPS,EE)
  To commission to a sufficient level that allows to reveal all the NCs

## Slide 7: Achievements S45: Circuits status
Circuit type | # | Target
Main circuits | 3 | PNO (>10kA)
IPQuads and (5) IPDipoles (3) in the MS | 8 | PNO (3.6-5.5kA)
IPQuads in the DS regions | 8 | PNO (5.3kA)
600 A circuits NOEE crowbar + NOEE | 16 | PCS (200A)
600 A EE + undulator | 24 | PLI3(200A)
120A: Dipole Orbit Correctors | 29 | PIC2 (10A)
60 A: Dipole Orbit Correctors | 94 | PCC (10A)
Comm.
3
8
6
14
16
29
94
600A EE – 24 cir. | 
16 | 100%
8 | 75%
600A without EE – 16 | 
14 | 100%
2 | 50%
60A – 94 cir. | 
94 | 100%
120A– 30 cir. | 
29 | 100%
IPQ/D – 16 cir. | 
14 | 100%
2 | 90% (PNO)
…a bit more in detail

## Slide 8: Achievements S45: Test Steps
Chart: 
w9
W8
W6
W4
W2
W52
W50
W48
Successful test steps
Cryo Starts
 | procedure | targets | done
Main Circuits | 74 | 67 | 92
IPQ-D | 221 | 221 | 232
600A | 688 | 520 | 503
120A | 300 | 210 | 216
60A | 282 | 94 | 232
Total | 1565 | 1112 | 1275
~60 test/wday
targets
procedure
7TeV
DONE
6TeV
Ack:
A. Marqueta
V. Zambrano
Ack:
M. Soubiran

## Slide 9: Achievements S45: Day efficiency
Testing_time
cryoSTART_avail_time
Eff_PT=
MR4 DFBMG
MR4 DFBML
Arc: RB
-Average Arc: 60% - Field activities
-Average MR4: 59% - Masking
Average LL5: 25% - Parallelism
Total: 70%
Ack:
Jacek Szkutnik
Arc: all
MR4 DFBMK
LL5 DFBMK
cryoSTART_avail_time
Total_time
Eff_cryo=
= 0.7
[S. Claudet]
Tot_eff= 0.5

## Slide 10: Achievements S45: time per circuit type
3d
4d
5d
6d
7d
8d
9d
10d
11d
12d
1d
2d
PCC-PLI
PNO
PCC-PLI
PNO
PCC-pcc - 24
PNO - 2
Ipq/d - 16
PCC-pcs - 14
PCc - 110
RB
RQF/D
PNO - 5
600A ee - 24
600A noee - 16
120A/60a - 110
Pli - 16
PCC-pli - 16
PNO - 16
pno - 92
Pli - 8

## Slide 11: Achievements: Main Dipoles at 6TeV (>10kA)
Main Dipoles: 10.27kA – 6.1TeV – 7.25T
Max T in A45 [K]
9500A
17R4-B
@9789 A
27L5 (C-B-A)
@9857A
22R4 (A-B-C) then 21R4 (C)
5
10
15
20
W4
@10274A
27R4 (A-B-C) then 26R4 (C-B)
W5

## Slide 12: Achievements: Main Quads at 6TeV (>10kA)
Main Dipoles: 10.27kA – 6.1TeV – 7.25T
Main Quadrupoles: 10.8kA – 6.4TeV - 185T/m
@10899 A
Q28R4
2
4
6
Max T in A45 [K]

## Slide 13: Achievements: Equivalent energy ramp 5.3TeV
Main Dipoles: 10.27kA – 6.1TeV – 7.25T
Main Quadrupoles: 10.8KA – 6.4TeV - 185T/m
Tests with Group of Circuits – PGC
  Test outline:
    Ramp to injection current (132 circuits, all high current circuits included)
      Problem found and solved on the Global Protection Mechanism for RB
      Trip of several 600A: QPS reconfigured
    Ramp to a current of 2 kA
      Circuit cross-talk investigation: selective Fast Power Abort on 600A
      Fast PA on RSD1.A45B1, and follow by RSD2.A45B1, RSF1.A45B1, RSF2.A45B1 (line N)
      NO cross-talk for the spool pieces
    Ramp to an energy that corresponds to a dipole current of 4 kA: OK
    Ramp to an energy of 5.3 TeV that corresponds to a dipole current of about 9 kA (138 circuits, all Main Circuits included @Nominal, a few 600A @200A)
      At 9 kA: ramp ok, RB trip with SlowPowerAbort after some 30 min (Fuse on the PC - repaired)
Commissioning Team
19th Feb. 2008

## Slide 14: S45: Commissioning achievements vs energy
3d
4d
5d
6d
7d
8d
9d
10d
11d
12d
1d
2d
PCC-PLI
PNO
PCC-PLI
PNO
PCC-pcc - 24
PNO - 2
Ipq/d - 16
PCC-pcs - 14
PCc - 110
RB
RQF/D
PNO - 5
600A ee - 24
600A noee - 16
120A/60a - 110
Pli - 16
PCC-pli - 16
PNO - 16
pno - 92
Pli - 8
[A. Vergara – Time Estimation for 3/5/6 TeV]
3TeV
5TeV
Sector fully commissioned for <=3 TeV
Sector partially commissioned for 5 TeV
all main circuits
large part 600A
Sector partially commissioned for 6 TeV
all main circuits
few 600A
600
400
200
-600
-400
-200

## Slide 15: HC S45 Review Outcome
Identification of the weak points:
  Procedures
  cryo-constrains
  Cryo operation
  HR
  Tracking tool
  …
[see R. Schmidt]
  Procedures
  cryo-constrains
Feb‘08
PT S45
26th Nov.
19th Feb
Cooldown/Warm up S45
July. ‘07
Jan. ‘07
20th April
11th Jul.
Cooldown/Warm up S78
PT S78
2nd Review
28th Feb.

## Slide 16: HC S45 Review Outcome: procedures
Ack:A.Siemko
W. Venturini
Powering procedures have huge influence on efficiency
Simplifications while securing a sufficient hardware qualification for operation of the LHC (increase the efficiency)
Nominal current (I_PNO) kept as a parameter. (energy?)

## Slide 17: HC S45 Review Outcome: Temperature
Ack:A.Siemko(MPP)
Not all the commissioning activities need 1.9K
Necessity to differentiate and to investigate the granularity!

## Slide 18: Conclusion
All the 182 commissionable SC circuits of S45 were tested
Total efficiency 50% - all the efforts of the review and the work now ongoing are aimed to increase it
A very important first milestone is however achieved
RECOMISSIONING of S45
  Clear strategy is being defined
  ALL interventions hardware/software (valves/ cables/ PLC/ PC modules/ cards/ updates…) must be declared to HCC.

## Slide 19: Next
Sector56 – PT: W12
Av. 3.3K
Today w10
Sector78 – PT: W17
Av. 185K

## Slide 20: Overview of the commissioning of the S45
Boris Bellesia

## Slide 21: Achievements S45: Test Steps
Chart: 
w9
W8
W6
W4
W2
W52
W50
W48
Successful test steps
Cryo Starts
 | procedure | targets | done
Main Circuits | 74 | 67 | 92
IPQ-D | 221 | 221 | 232
600A | 688 | 520 | 503
120A | 300 | 210 | 216
60A | 282 | 94 | 232
Total | 1565 | 1112 | 1275
~60 test/wday
targets
procedure
7TeV
DONE
6TeV
Ack:
A. Marqueta
V. Zambrano
Ack:
M. Soubiran