## Slide 1: VELO Upgrade Timeline
VELO Upgrade schedule almost finalised for TDR
Today we discuss suggested timelines for the electronics part
Many thanks for input to Martin, Eddy, Jan, Lars, Karol, Tony +++

## Slide 2: Module Construction & Assembly
2013
2014
2015
2016
2017
2018
Installation
commissioning
-> mid 2019
Module construction begins
Module construction
ends
Assembly onto bases begins

## Slide 3: Velopix Schedule
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix0 submission
received Q3 2014
Velopix0
verification
Velopix1 “final”
submission
(first 6 wafers can
be used for production)
Velopix1
test
Velopix1
mass production
reception Q1 2016

## Slide 4: Tile Production Schedule
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix p&p
p&p = production & prototyping
UBM processes
Dicing & thinning
flip chipping
Velopix Design

## Slide 5: Hybrid Schedule
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix p&p
p&p = production & prototyping
Tile production
Velopix Design
Hybrid design using
Timepix3 for test
Hybrid prototyping (high speed)
with Velopix0
Hybrid production starts

## Slide 6: Link, OPB, Feedthroughs
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix p&p
p&p = production & prototyping
Tile production
Velopix Design
Hybrid Design
Hybrid Prototyping
Electrical Link R&D
OPB R&D
Vacuum Feedthrough R&D
Production

## Slide 7: Firmware and ECS Development
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix p&p
p&p = production & prototyping
Tile production
Velopix Design
Hybrid Design
Hybrid Prototyping
Electrical Link R&D
OPB R&D
Vacuum Feedthrough R&D
First stage slice + selftest
Second stage slice
Commissioning
Production

## Slide 8: Proposed Dates for EDR and PRR
2013
2014
2015
2016
2017
2018
Module Construction
Assembly
Velopix p&p
p&p = production & prototyping
Tile production
Velopix Design
Hybrid Design
Hybrid Prototyping
Electrical Link R&D
OPB R&D
Vacuum Feedthrough R&D
First stage slice + selftest
Second stage slice
Commissioning
Production
Electronics EDR
Electronics PRR

## Slide 9: Resources
Production stage | Host Country
Electrical Link | UK, Spain
Vacuum Feedthrough | UK, Russia
OPB | UK
HV + LV | UK
General Electronics | UK, Brazil
Hybrid | UK, Spain
DAQ Integration + ECS | UK, Brazil
FE ASIC | The Netherlands, Switzerland
R&D, Design, Optimisation, QA, Testbeam | UK, The Netherlands, Spain, Brazil, China, Russia, Switzerland
Official production tables leave many tasks open.
e.g. ASIC wafer testing, bench and testbeam activities, production database etc.
may be led by an institute but contributions are possible