## Slide 1: Session 3 Performance Improving Consolidation and Upgrade scenario 1
Malika Meddahi, Lucio Rossi
Thanks to all speakers and contributors

## Slide 2: Setting the scene
 | PIC | Upgrade scenario 1 | Upgrade scenario 2
Initial integrated luminosity (fb-1) | 300 | 300 | 300
Integrated luminosity after 10 years of operation (fb-1) | 1000 | 2000 | 3000
Yearly luminosity target (fb-1) | 70 | 170 | 270
Which beam parameters can reach these targets?
What are the related actions on the equipment?
PIC: PERFORMANCE IMPROVING CONSOLIDATION:
Replacement or upgrade of a system justified by consolidation but with the goal of improving performance

## Slide 3: PICs in the injectors: What are we talking about? - K. Hanke
Clear PIC definition but some overlaps and grey zone with pure consolidation
and US 1 and 2.
pure consolidation
performance improving consolidation
upgrade scenario 1
upgrade scenario 2
grey area 1
grey area 2

## Slide 4: LIU PICs in short
Time drivers and minimum single block
LIU-PSB: minimum single block 12 m
LIU-PS: minimum single block 3 m
LIU-SPS: minimum single block 6 m
=> all time estimates depend strongly on available resources (manpower)
=> consequent amount of work to be done in parallel for all machine
=> to be considered with the Cons, maintenance, upgrade preparatory work
Cost of PICs
LIU-PSB: 50 MCHF (essentially LIU-PSB budget ~61MCHF)
LIU-PS: 16 MCHF (80% of total budget 20 MCHF)
LIU-SPS: 23 MCHF (30% of total budget 77 MCF)
PICs are mandatory and must be fully implemented in LS2 in the injectors regardless of which upgrade scenario is chosen

## Slide 5: Interaction region layouts
LHC
HL LHC
Aperture twice the LHC baseline (70 mm to 150 mm),
but more compact triplet layout thanks to Nb3Sn and superconductive D1
PICs in the LHC: What are we talking about? - P. Fessia

## Slide 6: LHC PICs in short
PIC actions
  Concern practically all the sectors of the machine
  They are spread between the 1st long technical stop after LS1 and LS3
Interaction region interventions in IP 1 and 5 provide safe operation for
2025->2035 years and the required luminosity capacity
Collimation interventions push down the whole machine impedance providing more robust collimators and ensure safe ion run in IP2.
Beam diagnostic interventions provide the necessary diagnostic capacity, with hardware compatible with the higher radiation dose
Sc links provide a solution to radiation electronic issues for the Power converters, but also contribute in reducing collective dose and interventions time
Cryoplant at point 4 provides flexibility in the management of the RF interventions and eliminate the 1st machine bottleneck in term of cooling capacity. All cryo installation have to be performed with a long term view in the installation/integration perspective (foresee for future needs)
High radiation dose call for radiation management and possible reconfiguration to provide the best possible reliability and access conditions. Radiation tolerant electronic development (including R&D and testing) will affect several equipment groups (costs, resources)

## Slide 7: PIC @ 6.5 TeV (Pile-up limit at 140)
 | e*n coll [mm] | Opt. Fill length [h] | h6h/hopt [%] | f6h/fopt [%] | Int. Lumi for h=50% for 6h /opt. fill length [fb-1 /y] | Max. Mean Pile-up density/Pile-up [ev./mm]/[ev./xing]
BCMS – 40/20 | 1.85 | 6.5 | 37/37 | 25/26 | 93/94 | 0.97/84
Standard - 40/20 | 2.25 | 7.3 | 40/40 | 27/28 | 87/88 | 0.79/69
BCMS – 50/25 | 1.85 | 6.8 | 39/39 | 26/27 | 89/89 | 0.77/78
Standard – 50/25 | 2.25 | 7.6 | 43/42 | 28/30 | 82/83 | 0.63/64
Goal
<50%
2012
36%
Goal > 70 fb-1
<1.3/<140
2012
6h
PICs: what do we gain in beam performance? – G. Arduini
I/b= 1.38e11/b in collision
The luminosity target can be reached with 40/20 optics
BCMS (Batch Compression Merging and Splitting): slightly higher performance but more sensitive than standard scheme to additive sources of emittance blow-up
50/25 optics provides margin in aperture and offers a reduction of the pile-up density below 0.7 events/mm
Key questions and studies required in Run 2 have been sketched - Understanding and Control of the sources of blow-up; Confirmation of the feasibility of b*-levelling as a possible solution for IP8; Confirmation of the feasibility of scrubbing the dipoles down to SEY=1.3-1.4 possibly with dedicated beams; Full understanding of the stability limits for single and two-beams

## Slide 8: Which beams in the injectors fulfil HL-LHC Upgrade Scenario 1 goals? S. Gilardoni
Large bunch intensity in LHC more important than low emittances
200 MHz RF Upgrade necessary to match the preferred requirements of LHC-US1 with unchanged longitudinal parameters at LHC injection.
LIU US1 ≣ LIU US2
 | LHC collision |  | SPS extraction | 
Standard Scheme | Int/b | Emitt* (μrad) | Int/b | Emitt* (μrad)
US1 Baseline | 1.50E+11 | 1.5 | 1.58E+11 | 1.25
US1 low emit. | 1.20E+11 | 1 | 1.26E+11 | 0.83
US1 LIU SPS LLRF 200 MHz upgrade | 1.38E+11 | 1.64 | 1.45E+11 | 1.37
US1 LIU SPS 200 MHz full upgrade | 1.90E+11 | 2.26 | 2.00E+11 | 1.88
BCMS |  |  |  | 
US1 Baseline with BCMS | 1.50E+11 | 1.5 | 1.58E+11 | 1.25
US1 low emittance with BCMS | 1.20E+11 | 1 | 1.26E+11 | 0.83
US1 LIU SPS LLRF 200 MHz upgrade | 1.38E+11 | 1.09 | 1.45E+11 | 0.91
US1 LIU SPS 200 MHz full upgrade | 1.90E+11 | 1.64 | 2.00E+11 | 1.37
Oliver analysis based on evaluation of non-crossed out cases and with variations of the beam emittance

## Slide 9
9
HL-LHC for US1? – O. Bruening
US1 flat beams; SPS with new LLRF system and with the RF power upgrade
N at collisions = 1.9 1011ppb
n = 2508 colliding pairs in IR1 and IR5 (revised BCMS filling scheme)
normalized emittance = 2.65 micrometer ( > 70% blow-up wrt SPS extraction)
flat beams with beta* = 0.4m / 0.1m
beam separation of 10 sigma -> crossing angle of 310 microrad
IBS growth rates of ca. 22h horizontally and 25h longitudinally (scaled)
Peak Luminosity = 8 1034 cm-2 s-1
Leveling time = 2.9 h; Lumi decay time = 4 h; Turnaround time = 3 hours
Total fill length (leveling + decay + turnaround) = 9.9h
Integrated Lumi per fill =1.06 fb-1; Lumi per year for perfect operation = 413fb-1
Required efficiency for achieving 170fb-1 per year = 41%
==> this case could reach the US1 goals and is OK from the IBS point of view, requiring essentially TAS and TAN upgrades

## Slide 10
10
HL-LHC for US1 – O. Bruening
Beam-Beam Wire compensator is very important for US1. Optimum position at 10s  integration aspects with Collimation System!
Small emittance beams from LIU upgrade can not really be utilized in the LHC for US1 due to IBS limitations .
US1 goals compatible with full SPS upgrade and HL-LHC PIC when operating with flat beams (40cm/20cm). Smaller b* (e.g. 40cm/10cm) can provide more performance (>20%) but requires some Matching Section upgrades

## Slide 11: COLLIMATORS
Work effort in the LHC accelerator for US1 – E. Todesco
Upgrade scenario 1 work effort
  Same peak lumi as US2 (heat loads), and 2/3 of data (radiation damage) – many unknowns to be seen with 7 TeV operation
  New triplet/D1 as defined for PIC allows to swallow larger heat loads, and radiation damage
  Matching section becomes a bottelneck for b* (not lower than 30 cm), but can swallow heat load and radiation damage
  Scenario relies on ability to increase beam intensity
Work effort
  Collimators in IR7, IR1, IR5
  Superconductive link for matching sections in IR1 and IR5
  Beam-beam long range wire compensator needed
    New piece of hardware, not yet proved for LHC
    Proof of principle for the LHC in 2017

## Slide 12: Linac4 : 15 weeks to deliver a beam to the PSB
JB. Lallement – RLIUP Workshop – 31/10/2013
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Linac2/Linac4 interface |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cool down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Line removal up to BHZ.20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DC cable path |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Emergency exit door |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Château |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chicane |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shielding wall |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Line installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L2 tunnel access door |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LBE line |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cool down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Removal of L2 LBE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation of L4 LBE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cabling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Beam commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Work Effort in the LHC Injector Complex, Including Linac4 Connection, for the Upgrade Scenarios – Jean-Baptiste Lallement, Bettina Mikulec

## Slide 13: Overall L4 Connection to PSB
Duration for the Linac4 connection to the PSB: 9.2 months
  Deliverable: LHC production beam injected into PS; coincides with injection of LHCPILOT beam into the LHC
  Other physics beams to follow at an estimated rate of ~2/week
First beam to the PS after 9 months
Ion run and CMS pixel detector installation in parallel?
  Ion beam commissioning in LHC ion injector chain end of 2016 in parallel to p run
  LHC ion run of up to 3.5 month after X-mas
  CMS pixel detector installation: 4.5 months
  Could other activities profit? (NA61/SHINE etc.)
LHCPROBE
injected into PS
LHC production beam
injected into PS
LHCPILOT
injected into LHC
LHC production beam
injected into LHC

## Slide 14: LIU LS2 Planning
LS2:
Time line driven by PSB activities (impressive cabling work to be performed -> coherent scheduling in progress taking into account the overall requests needed for other projects)
  PSB first beam (LHCPROBE) to the PS: after 17.5 months
  PS ready for beam from PSB already after 14.5 months -> need to gain 3 m in PSB
  SPS ready for beam from PS: after 16.5 months
First injection of LHCPILOT into the LHC: after ~20.5 months
Minimum time for injection of LHC production beam into the LHC: after ~22 months (scrubbing!)

## Slide 15: Summary of session 3 (1/2)
PICs
  Need to be fully implemented in the LIU regardless of the chosen Upgrade Scenario.
  PICs (new triplet+collimation upgrade+ Cryo…) are mandatory for future HL-LHC operation
  PICs provide at least 70 fb-1 / year and fulfil the 1000 fb-1 target sets for the PICs only scenario until 10 y operation to 2035
Upgrade scenario 1
  Means Full Upgrade of the injectors (identical upgrade to scenario 2)
  Allows reaching the set target of 2000 fb-1 (170 fb-1/y) using ‘smaller’ emittance beams

## Slide 16: Summary of session 3 (2/2)
Schedule
  Coordinated effort to plan all the upgrade implementation is to be started, taking into account all needed resources for LIU, HL-LHC but also CONS and other requests
  Should cover a longer time span (few LS)
  LS2: LIU implementation to be ready for post-LS3 operation
  LS2 should be at least 18 months