## Slide 1: Brief overview on Cabling and Optical Fibre activities With particular accent on Optical Fibre working method
D. Ricci, on behalf of EN-EL-CF section
EDMS 1327029

## Slide 2: What’s Cabling ?
Cabling = copper cables (CTRL+DC) + optical fibres:
  ~ 90.000 km copper cables
  ~ 35.000 km of optical fibres
The activity includes:
  Installation of cabling for CERN accelerators, general infrastructure and experiments
    Collaborate in the definition of the cable cross-sections, connectors and optical fibre types
  Operation and maintenance of the optical fibre infrastructure
    Design, reconfiguration, maintenance (all CERN users)
    Qualify and procure radiation resistant optical fibres (2400 km for LS1)
  Procure and standardise cables, optical fibres and connectors for CERN users
    233 orders in 2012 – Average investment per year: 3.5MCHF
    managing cable parc: ~4200 drums for LS1
  Operation and maintenance of the cable tray infrastructure (350 km)
  Monitor aging and steer the cable/fibre replacement campaigns
    ~1MCHF/machine point

## Slide 3: Cabling and Optical Fibre section (EN-EL-CF)
35 staff + 100 contractors during LS1 peak
Projects

same working method

## Slide 4: EN-EL-CF functional model
Work: punctual activity. Taken at charge by a Section member following from a User’s request.
Project: activity with the following characteristics:
  A “Project Leader” is assigned among the CERN’s Users
  A project “Technical Coordination” is put in place
  A project “planning coordination” is put in place
  Strong interactions with central/periferals study offices (Integration)
Interaction with ~600 users for all CERN departments/groups

## Slide 5: The LS1 challenge: the important numbers
37 main projects to carry on + day-by-day installation works
  (Some examples: R2E, LHC cabling campaigns, WCC hose consolidation, SPS campaigns & irradiated cables TS1+, new SPS fibre infrastructure (BI & others), PSS, LINAC4 & Meyrin campaigns, Computer Centre extension B513, LHC-Experiments fibre upgrade)
Overall estimated budget ~15 MCHF
~1000 km of copper and optical cables being installed during LS1

## Slide 6: The strategy
Example1: anticipate qualification and procurement of material
  Some special cables/fibres require 6 months to be procured
  Early processing of the user’s needs (deadline June 2012) orders placed
  All cables/connectors defined by Oct 2012  last orders finalised
Procurement copper cables & connectors
+ fibres…
Qualification of RRF
More than 20 irradiation tests
2400 km procured in 2012/13
LHC consolidation + upgrade
SPS new Beam Instrumentation
For more details see LSC presentation June 2013
Notes: In the case of Fibres, the procurement of material is included in the contract

## Slide 7: The strategy
Example2: anticipate contractors’ workload and optimize planning time-slots
  Negotiation of working time slot with machine & project coordinators since Sep 2012
  Optimal shaping of workload curves for contractors w.r.t. co-activity constraints
  Work organized by geographical campaigns
For more details see LSC presentation June 2013
Notes: Note: LHC dominates the planning 
critical not to change accessibility for CF,
PS and SPS load curves compensate each other

## Slide 8: Infrastructure: current situation
Overloaded areas
SPS: class1976 (36 years old)
PS: class 1959 (53 years old)
Rest of PS-complex and Meyrin technical galleries
Gallery TP9
Intersection Linac2-Linac4-PSB
Cables installed before ’80s are with halogens (risk in case of fire accidents)
PS ring centre
Galleries
Shafts

## Slide 9: Unité Fibres Optiques – Méthode de travail contrat C202/EN
EN-EL-CF
UTILISATEUR
DIF
Demande Installation Fibres
Accusé de réception
CONTRACTANT
Préparation dossier complémentaire
Vérification des données
Etude de la demande
Préparation du dossier technique
Commande de matériel
Envoi du OSVC (Ordre Service Valant Commande)
Signature
Préparation du dossier administratif
Envoi de l’OE (Ordre Exécution)
PREPARAT I ON
Fibres supplémentaires
Modifications éventuelles
Contrôle de l’installation
Remise de l’installation
EXECUT
ION
Remise de l’installation
Fiche de retour
Contrôle des métrés
Réunion de planification/présentation des travaux
Etude des passages, cheminements, etc. - VIC
Production du matériel
Estimation financière
Devis
Préparation procédures de sécurité (AOC, VIC, IMPACT, etc.)
Installation (pose tubes/câbles, terminaison, test)
Fiche de modification
Fiche de réception
Réception/reprises
Préparation chantier, transport du matériel
RECEPTION
TRANSMI SS ION
D. Ricci – EDMS 1184327
Updated: 5 Nov 2013
Remise des métrés
Métrés

## Slide 10
Backup slides

## Slide 11: The strategy
Facing technical challenges: optimize work organisation and resource distribution by working by geographical campaigns
Campaign Booster
Campaign SPS-BA1
Campaign LHC-Point1
PROJ 1 Various works for TE/ABT
PROJ 2 LIU
PROJ n Various works for BE/BI
Campaign SPS-TS1+
PROJ x Repl. Irradiated cables TS1+
Campaign LHC-Point 5
Campaign LHC-Point 8
Campaign LHC-Point 1
PROJ y R2E
Case 1
Case 2
Case 3
~700 cables/fibres work orders for LS1
Notes: All project requests are constituted for us of several work orders for installing cables in different machine ares. The concept of campaign consists of decomposing and re-organizing these works by geographical areas allowing to optimize the intervention time in that area, the necessary resources and the overall plannning to fit all campaigns.