## Slide 1
LS1 Status Report
LS1@LHCC – 117th LHCC
Frédérick Bordry
5th March 2014

## Slide 2
Physics
Beam commissioning
Shutdown
Powering tests
F
M
A
M
J
J
A
S
O
N
D
J
F
J
F
M
A
M
J
J
A
S
O
N
D
2013
2014
2015
M
A
LHC
SPS
PS
PS Booster
beam to beam
available for works
16th Feb.
5th March
LS 1 from 16th Feb. 2013 to Dec. 2014

## Slide 3
PS Main Magnets
PSB beam dump
LHC Injectors dashboards
  - Full maintenance of all the equipment being completed
  - New access system being commissioned
PS & PSB main activities:
Consolidation of the PS Main Units completed, New PS ventilation system commissioning started, PSB dump replacement being completed…
  Septum 16 External Shielding in progress

## Slide 4
LSS1 -irradiated cabling campaign
LHC Injectors dashboards
SPS main activities:
LSS1: Irradiated cabling campaign is on-going
Re-installation of the machine will start on March,
Transformers exchange complete,
TT10 vault repair completed…
TT10 vault
SPS transformer installation

## Slide 5
PSB
PS
SPS
LHC Injectors dashboards

## Slide 6
LHC-injectors … getting ready for hardware tests
  Full commissioning of the new access system is starting
  PS &PSB : hardware tests will start in April
  Beam for late spring in Linac 2  summer in PS
LHC Injectors start-up

## Slide 7
116th LHCC Meeting (4th December 2013)

## Slide 8
3
Done
Done
Done
3000
96 % done
85 % done
Opening:100%
70 % done
90 % done
40 % done
98 % done
85 % done
85 % done
Closure: 50%

## Slide 9
DFBA consolidation
  Leaks were found on the lower gimbal bellow in 2 DFBAs
    Shuffling modules were extracted and transport to surface for repair
      Both back in tunnel
  Teams reinforced – schedule is not an issue anymore
DFBAK lower gimbal bellow repair on surface
DFBAK shuffling module back
SMACC progress – report on DFBA

## Slide 10
SMACC Dashboards
Superconducting Magnets and Circuits Consolidation (SMACC).
3 weeks

## Slide 11
Last M line opening (S45)
6th of February 2014
Operator responsible : JM Hubert
Pictures by M Struik

## Slide 14
UL16 power converters
UL55 safe-room
WCC installation @ P5
TZ76
R2E progress
Point 1
  All equipment are reinstalled and reconnected
  Commissioning in progress
Point 5 & Point 7
  Major cabling campaign in progress

## Slide 15
Chart: R2E @ Point 1 Left
Chart: R2E @ Point 1 Right
Chart: R2E @ Point 5
Chart: R2E @ Point 7
R2E dashboards

## Slide 16
Before
After
18 kV & 3.3 kV circuit breakers
Vacuum
UPS-RE82
Pumping station
Cryo plant
P7 enclosure
ACS transport
The other activities
Courtesy of Katy Foraz
Helium spill test

## Slide 17
Infrastructure dashboards

## Slide 18: From
Schematic view of version 3.1, now includes
  DFBA repairs at P6 and P8
  CSCM in sectors 67 and 81
  a margin of 2 weeks after flushing for N.C. solving
  The sector test from P2 to P3
Under approval
Schedule: version 3.0 to 3.1
Courtesy of Katy Foraz

## Slide 19
Conclusion
http://cern.ch/ls1dashboard
LHC injectors getting ready for hardware tests
LHC: all signals are green for beam on January 2015

## Slide 21
Only EYETS (19 weeks) (no Linac4 connection during Run2)
LS2 starting in 2018 (July) 18 months + 3months BC (Beam Commissioning)
LS3 LHC: starting in 2023 => 30 months + 3 BC
injectors: in 2024 => 13 months + 3 BC
LHC schedule beyond LS1
Run 2
Run 3
Run 4
LS 2
LS 3
LS 4
LS 5
Run 5
LHC schedule approved by CERN management and LHC experiments spokespersons and technical coordinators
Monday 2nd December 2013