## Slide 1: Savannah to Jira Migration
Status report

## Slide 2: Savannah
Savannah is a Web-based Libre Software hosting system including:
  issue tracking
    Bugs, Tasks, Support, News and Documentation
  project member management by roles and
  individual account maintenance
…
P250
MySQL db
Savannah
Users
EXPORT
Projects

## Slide 3: More than 200 projects in Savannah
242 projects planed for migration
ACTIVE Projects | 69
NON ACTIVE Projects | 36
Archive Projects | 137
…
P250
MySQL
db
Projects
The plugin
Since there is no possibility to export data from Savannah, a plugin (of Jira) was developed in order to migrate projects from Savannah to Jira. This Jira plugin was developed by a summer student and then a fellow has continued.
Migrate in Jira using the plugin
Plugin incompatible with new version of Jira

## Slide 4: Project by type
N | Type | N-Projects
1 | ALICE | 14
2 | ARDA | 1
3 | ATLAS Computing Operations Count | 28
4 | ATLAS Detector Operations | 8
5 | ATLAS Miscellaneous | 1
6 | ATLAS Offline Software | 35
7 | ATLAS TDAQ | 21
8 | CERN IT | 32
9 | CMS | 30
10 | CMS Software | 7
11 | EGEE | 30
12 | HEP Applications | 5
13 | LCG Application Area | 8
14 | LCG Grid deployment | 8
15 | LHCb | 21
16 | Other Grid Projects | 10
17 | Other Physics | 7
18 | Savannah portal | 7
 | Total | 271

## Slide 5
Plugin not working
dev and production again not the same version
Workaround:
Import into old version, upgrade JIRA and migrate between JIRA instances
Using workaround procedure
Plugin fixed in dev instance
Problem with the custom fields ; (those associated to tasks ) data were not migrated
Most of the Problems fixed by Rene
Some problems in Jira 6.1 and some others related to custom fields
Code development for static web pages
December
January
Created a few test migrations in the dev instance
February
1st Migration of Aliroot
March
Testing for errors and methods to solve the issues related to custom fields
Start
A Series of actions
Aliroot
Dashboard
GGUS sh. list
Atlas Trigger Software
Persistency Framework
Atlas Central DCS
ATLAS Panda distributed production and analysis system
Atlas Distributed Comp. Operation Support
cernVM migrated successfully in production instance of JIRA
The code is being developed using python .
Can generate static web pages of any Savannah project
The plugin was fixed and runing in the development instance of Jira which was not the same version of the jira production instance.
In order to have an alternative solution there were conducted tests running the plugin in 6.0 and then upgrade to 6.1 ….
A Bug was found in the plugin code

## Slide 6: Custom fields
There are in total 236 Custom fields for the projects that we have scheduled for migration
  3 “Date” type
  108 “Selective box” type
  225 “text” type
Some of the custom fields may have similarities and it would be possible to associate them in multiple projects or even use global fields.
It will not be possible to avoid having all custom fields of “Selective box” type because each list has different values

## Slide 7: Looking forward
Solve a few issues related to custom fields
Refine the schedule (better time estimation and project priorities)
Implement the plan according to the schedule
  Coordinate with IT
  Contact users and exchange information
  Perform the migrations

## Slide 8
Migration of Savannah projects to Jira development instance
Jira Production
Create a draft mapping of fields and values
Agree on the result with the user
Check the project in Savannah
Export the project in Jira development instance
Migrate the project in Jira Production instance
Migration terminated
Best efforts to minimize the number of Custom fields in Jira
A1
A2
A3
A4
C
D
B
Short procedure

## Slide 9
Migration of Savannah projects to Jira development instance
Jira Production
Create a draft mapping of fields and values
Agree on the result with the user
Check the project in Savannah
Export the project in Jira development instance
Import from Savannah to Jira 6.04
Upgrade to Jira 6.1
Export db data in Jira 6.1 (dev)
Import data in Jira Production
instance
Schema reproduction (adding custom: fields etc)
modification of the issues redirection table in Savannah
Migration terminated
Best efforts to minimize the number of Custom fields in Jira
A1
A2
A3
A4
B1
B2
B3
C1
C2
C3
D
Long procedure

## Slide 10: The procedure
Inform all project leaders in Savannah about the procedure and the schedule.
Eventually reschedule after feedback
Execute a test migration and inform the project leaders to give feedback
Eventually take note of the feedback and do the necessary modifications (e.g. mapping field values)
Proceed with the migration in the production instance of Jira.

## Slide 11: The schedule
Thank you
111 projects to be migrated
  About 10 weeks time for completion
  Going through a test migration and interaction with the users before final migration
    Currently 8 in progress
  Coordination with IT
Static web pages for the remaining 137 projects