## Slide 1: ALICE USA Computing Project Proposal
ALICE-USA Resource Review
Apr 7-8, 2014

## Slide 2: Outline
Run 2 Project Proposal Context
Complications
  NERSC Move
  LLNL/LC  ORNL/CADES
Requirements & Deployment plans
  CPU
  Disk Storage
Summary

## Slide 3: ALICE-USA Computing Project
Goal: supply cost-effective Grid-enabled computing resources to ALICE
  Fulfill MoU-based ALICE USA obligations for computing & storage resources to ALICE
  Based on ALICE USA participation at about 7-8% of ALICE
2009 Project Proposal
  Operate facilities at two DOE labs
    NERSC/PDSF at LBNL
    Livermore Computing (LC) at LLNL
    3-year procurement plan
  LBNL as the host lab
  Fully operational since Summer 2010
Operations defined in “Project Execution & Acquisition Plan”: PEAP
  Organization structure
  Procurement strategy
  Deliverables & Milestones
Project due for a 3 year DOE Review
& originally planned for 2/2014

## Slide 4: Recommendation for Two Facilities NERSC/PDSF and ORNL/CADES
NERSC/PDSF + ORNL/CADES
  Scientific Computing strength
  High-bandwidth connection: ESNet
  Favorable cost structure
  Proximity to HPC Resources
    Oak Ridge Leadership Class Facility
    NERSC Flagship facility
    Strategic alignment with O2 project
ESnet
ORNL
NERSC
LLNL
ESnet Monitoring
LLNL/LC  ORNL/CADES
demands a new proposal

## Slide 5: Proposal Timeline
Develop a new Project Execution and Acquisition Plan (PEAP)
  Schedule new resources for NERSC/PDSF and ORNL CADES to:
    Adequately meet new ALICE requirements in FY15
    Fill all ALICE-USA obligations estimated through Run 2
  Establishes operational milestones
    Stable grid operations @ORNL CADES
      AliEn VO box & SE
      OSG Services (TBD)
    WLCG MoU with ORNL CADES
Aggressive timeline:
  Draft in progress - working document by end of April
  April 7th-8th: host ALICE Offline at LBNL to review proposal and plan
  DOE Chaired External Review of project proposal is being scheduled ~ June 2014
ALICE Run-2 Requirement Estimates

## Slide 6: Additional Complication
NERSC new building in early 2015
  More details Tuesday, in NERSC Report
  No new hardware will be installed in the current building
  Operate in both buildings for ~1 year
    Most of PDSF CPU nodes will move
      Duration of move/downtime is unclear
      Will attempt to mitigate with other cpu
    Storage will remain in old building
    New storage new building
LLNL/LC will continue into 2015
  Allows us flexibility to meet obligations

## Slide 7: Timing Constraints
Target next heavy ion run  Fall 2015
  Both NERSC and CADES meeting all ALICE-USA obligations
LLNL/LC should assumed to be decommissioned  Oct 2015
  Regardless of flexibility
NERSC CRT building ready for new HW  Spring 2015
  NERSC Oakland Facility assumed to be decommissioned  Fall 2015
ORNL/CADES ready for deployment as needed
  Current target for new hardware is by April 2015

## Slide 8: ALICE-USA Obligations (preliminary)
ALICE PhD & ALICE-USA PhD Counts are estimates
Columns are US FY:
  By DOE request
ALICE Disk puzzle:
  63% jump in 2015
  21% increase in 2016
  10% increase in 2017
  Data rate 2015 = 2016 ?

## Slide 9: Deployment plan by site

## Slide 10: Preliminary summary plan
Meets CPU targets at ~100%
Falls well short of disk obligation
  Need to better understand year-to-year requirements
  Expect that we will catch up ~FY17 or if need arises from ALICE
Does not
include LLNL/LC

## Slide 11: CPU Deployment Profile
Apr ‘14
Apr ‘16
Apr ‘15
ORNL
LBNL
LLNL
ALICE-USA
ALICE Req

## Slide 12: WLCG Resource Pledge Guidance
LLNL/LC will operate for ½ of RRB 2015
  Assume to continue with current pledge & then remove pledge mid-year
    should verify with WLCG
ORNL/CADES available to make pledges after MoU
  Targets MoU signed by Oct 2015
LBNL/PDSF will lose resources mid-2015 RRB year
  Will pledge to the lower value

## Slide 13: Storage replacement
Storage is or will be out of warranty:
  LLNL/LC
    680TB ended ~Aug 2013
  NERSC/PDSF:
    144TB ended June 2013
    288TB ends Apr 2014
    288TB ends Oct 2014
  Project plans to operate ~1.4PB storage at LLNL & LBNL into 2015
Replacement storage will be new SE at both LBNL and ORNL
  Requires migrating >700TB data between new and old SEs
    LLNL::SE  ORNL::SE --- WAN transfer
    LBL::SE  LBLEOS::SE --- local high bandwidth transfer
  Migration will take time
    How to operate during migration?
      Do we make source SE readonly?
    Does ALICE know how to do this?

## Slide 14: Disk Deployment Plan
Apr ‘14
Apr ‘15
Apr ‘16
LLNL
ALICE-USA
LBNL
ORNL
ALICE Req

## Slide 15: Summary
New ALICE-USA Computing project proposal required for Run 2
  Two US based ALICE Tier-2 facilities, ORNL/CADES & LBNL/NERSC
  Subject to DOE review in early June
Hardware deployment plan is preliminary
  Will satisfy CPU requirements
  Needs to understand disk requirements, year-to-year changes
The project plan is made complicated
  Movement of NERSC to new building in 2015
  Replacement LLNL/LC resources with new resources at ORNL/CADES
    Particularly transfer of ~400TB of data over WAN