## Slide 1: Wafer Procurement, Sensor Post-processing and Interconnect R&D

## Slide 2: Wafer procurement and QA
Choice of starting wafer material
Used different high-res epi wafers in ER2013
Final choice will depend on test results of prototype chips:
  Select epi thickness
  Select resistivity
Procurement of the wafers for the production should start end of 2014/beginning of 2015
Goals for 2014:
Finalize choice of high-res wafers by end 2014
Finalize QA by end of 2014

## Slide 3: Wafer procurement and QA
Epi thickness | Resistivity | # wafers | Status
20 µm | >1kΩcm | 12 | Delivered 9/6
25 µm | >1kΩcm | 6 | Delivery ~ 25/6
30 µm | >1kΩcm | 12 | Delivered 9/6
30 µm | >2kΩcm | 25 | Delivery ~ 31/6
Ordered new set of wafers to be available for the next engineering runs.
Partially delivered (will be completed July 31, 2014)

## Slide 4: Wafer QA before processing
Data supplied by vendor for custom wafers: epi thickness, resistivity
QA activities with TMEC on sample basis:
SEM cross-section inspection
Surface resistivity measurement
SRP measurement of resistivity profile in the epi layer
  Ordering reference samples
TMEC
TMEC

## Slide 5: Wafer Post-Processing List
 | # wafers | Ni/Au plating | DBG | Status
ITS2 - I | 2 (high res) | PacTech | tbd | At PacTech
ITS2 - II | 5 (high res) | PacTech | tbd | At PacTech
ITS_pad (50c) | 7+1 (setup) | PacTech | tbd | At PacTech
ITS_pad (50c) | 16 | PacTech | tbd | At PacTech
Total | 31 |  |  | 
Processing after delivery of CMOS wafers from the foundry:
Plating (Ni/Au)
Thinning&Dicing
Several wafers presently in the pipeline for post-processing:

## Slide 6: Pad wafers with 50 contacts
To be used for assembly tests

## Slide 7: Pad wafers with 50 contacts
M6+Passivation
Produced by TowerJazz
Scribeline (and test structures) as on full CMOS wafers  can be used for thinning and dicing tests

## Slide 8: Post-Processing Schedules
Turn-around time is not negligible for complex DBG and Ni/Au plating  requires careful planning not to delay subsequent activities.
Ni/Au plating
(mask generation, processing ~ 4 weeks)
Dicing and grinding
~ 1 week (if slot is available)
Transport time
3-4 days
Transport time
3-4 days

## Slide 9: Ni/Au plating
1 ITS2 pad wafer (8”) returned from plating at PacTech
Mask was applied to cover all areas except pALPIDEfs contacts, visual inspection before DBG:

## Slide 10: Ni/Au plated ITS2 padwafer
Wafer sent for DBG – partially lost due to mishandling at the grinder.
Remaining dies will be delivered beginning of the week.
QA of this processing step needs to be defined, e.g:
Visual inspection
Solder test
Height control (5 um Ni, 50 nm Au)

## Slide 11: Ni/Au Plating – Next Steps
1. Solder test of chips from first wafer plated by PacTech
2. Next 2 wafers (ITS2 CMOS) expected to be delivered back from PacTech end of June  visual inspection, DBG, solder tests
3. Preparing market survey for Ni/Au plating:
Pre-meeting with purchasing officer (June)
Aiming to complete market survey by the end of summer
Should be completed before receiving new wafers later this year

## Slide 12: Thinning & Dicing
Definition of the criteria for thinning and dicing:
Thickness: 50 um +/- 5 um
Max. extent from seal-ring: +/- 30 um (20 um?)

## Slide 13
ER2013 wafer
Diamond wheel dicing
(2000 mesh wheel)
Blank wafer
Laser diced by STARS
(front view)
Blank wafer
Laser diced by STARS
CMOS wafer
Blank wafer

## Slide 17
Laser dicing from the front will require free dicing lanes
Laser dicing from the back will require grinding to 50 um first  handling of thin wafer

## Slide 18: Thinning & Dicing Status and Next Steps
STARS is preparing a pick-up tool: news beginning of July  test dicing of real CMOS processed pad wafer?
Asked offers from DISCO for blade and laser dicing: die picking not provided – evaluating
Rockwood investigated grinding accident with ITS2 pad wafer: origin found
Need to prepare market survey as for the plating: meeting with purchasing office in the next weeks.

## Slide 19: Wafer QA after processing
Main task: Basic visual inspection on the wafers, i.e. the connection pads, prior to
Post-processing and/or
Thinning and dicing
Rockwood carried out visual inspection on recent wafers following SEMI standard: provide pictures and summary report for each wafer.
Need to define procedure for production
(cost, time, etc. ).

## Slide 20: Transport and Storage
Planned transport test involving a number of institutes: i.e. IPHC, Pusan, Liverpool, …
Prepared gel-pak boxes with 50 um dummy chips and 50 um thick STAR HFT pixel chips

## Slide 21: Chip Transport
Used identical large gel-paks to return pad chips (TMEC) from Rockwood (2 x 24 chips)
Chips cannot be removed applying vacuum
Cut out chips freed from gel by using HF-acid – limited use due to oxidation on the pads

## Slide 22: Chip Transport
Discussion with Rockwood ongoing to identify whether the problem is due to one of the processing steps.
Short term solution: ordered and received foam boxes
Alternative solutions:
Foam box: needs improvement (flakes, dust, counter-pieces)
Waffle packs: requesting offer, investigating how to fix chip in the compartment

## Slide 23: Interconnect R&D
Direct flux-free laser soldering on silicon chip
Solder balls (diameter 200 um)
50 um thick silicon chip

## Slide 24: Interconnection R&D
Number of single chip assemblies soldered with very good yield:
 | Sample | Flex | Poly thickness | chip | contact | gas | daisy-chain resistance
1 | 04022014-SA1 | Test 15, new Ni/Au | 75 µm | TMEC new Ni/Au | 50/50 | N/H | 125 Ω
2 | 04022014-SA2 | Test 15, new Ni/Au | 75 µm | TMEC new Ni/Au | 50/50 | N/H | 115 Ω
3 | 07022014-SA1 | Test 15, new Ni/Au | 75 µm | TMEC new Ni/Au | 50/50 | Vacuum | 160 Ω
4 | 10022014-SA1 | Test 15 | 75 µm | TMEC new Ni/Au | 50/50 | Vacuum | 84 Ω
5 | 10022014-SA2 | Test 15 | 75 µm | TMEC new Ni/Au | 50/50 | Vacuum | 80 Ω
6 | 12022014-SA1 | Test 11 new production | 50 µm | TMEC new Ni/Au | 50/50 | Vacuum | 94 Ω
7 | 12022014-SA2 | Test 11 new production | 50 µm | TMEC new Ni/Au | 50/50 | Vacuum | 74 Ω
8 | 13022014-SA1 | Test 11 new production | 50 µm | TMEC new Ni/Au | 50/50 | Vacuum | 60 Ω
9 | 13022014-SA2 | Test 11 new production | 50 µm | TMEC new Ni/Au | 50/50 | Vacuum | 46 Ω
10 | 13022014-SA3 | Test 11 new production | 50 µm | TMEC new Ni/Au | 50/50 | Vacuum | 59 Ω
11 | 19022014-SA1 | Test 11 new production | 50 µm | TMEC new Ni/Au | 48/50 | Vacuum | 
12 | 24022014-SA1 | Test 11 new production | 50 µm | TMEC 3 produc | 50/50 | Vacuum | 39 Ω
13 | 26022014-SA1 | Test 11 new production | 50 µm | TMEC new Ni/Au | 49/50 | Vacuum | 
650 solder contacts
3 failures (understood)
Can correlate good soldering quality with integrated laser power value  no need to cut the sample  first step in defining quality procedure

## Slide 25
2 IB modules built with 50 contact pad chips (TMEC)
Alignment done fully manually
Vacuum box leaking (missed 7 contacts out of 450 due to oxidation)
Daisy chain resistance value ok
Next: waiting for plated chips to assemble pALPIDEfs and pad chip modules
Interconnection R&D

## Slide 26: Al-FPC design
1 mm
0.4 mm
1 mm
0.4 mm
1 mm
1 mm
Openings for chip position measurement
Di Mauro
A. Junique

## Slide 27: Al-FPC manufacturing
Al coating | Etching | Status
LERMPS (F) | Chemical etching (CERN - R. De Oliveira) | Al quality OK: roughness 0.39 mm, surf. index 1.06, resistivity ~ 0.22 Ω/cm Machine capability (guaranteed Al layer homogeneity): 0.1x1 m2 Delivered 2 samples (9-chip): 1 daisy chain + 1 with signal tracks
DEPHIS (F) |  | Al quality not OK: too porous (roughness 0.62 mm, surf. index 1.2) and too high resistivity ~ 0.7 Ω/cm Investigation is ongoing, setting up of machine to reproduce LERMPS parameters (machine capability: 0.5x1.5 m2)
FHR (DE) |  | Best Al quality: roughness 0.14 mm, surf. index 1.007, resistivity ~ 0.16 Ω/cm Issue with presence of fibres and particles embedded in Al layer under investigation Machine capability: 0.5x1.6 m2 Delivered 2 samples (9-chip): 1 daisy chain + 1 with signal tracks
IREIS/HEF (F) |  | Leader “surface engineering” French company Machine capability 4 x 1x0.30 m2 Al coating tests this week
LERMPS baseline solution, mass production affordable ( ~ 18 batches of 6 FPC)
Tests with other companies driven by R. De Oliveira to find alternative supplier, very often LERMPS delivery time quite long

## Slide 28: Laser etching (Swiss Micro Laser)
Optimized laser parameters
Delivered 9-chip FPC prototype (on old DEPHIS foil)

## Slide 29: Mass Test – Probecard Preparation
Probecard for the pALPIDEfs prepared by Youngil Kwon (Yonsei):
Double needles for the contacts to check contact quality automatically
Complex probecard needle matrix with double needles reaching into the contact window from 4 sides.
Card was delivered at CERN early May:
Mechanical test on prober
Contact test on ITS2 CMOS wafer (pad wafer and real CMOS wafer)
Now: connecting to pALPIDEfs test system – work ongoing

## Slide 30
EQ Eng
2.1 Probe card Contact
2. Probe Card Pin Contact Analysis
206pin Top/Bottom
Youngil Kwon

## Slide 31
EQ Eng
2.2 Probe card Contact
2. Probe Card Pin Contact Analysis
Pin 數 | 206pin(1Pad 2Pin) | 
Pad Size | 224*224um | Pad Pitch 874um
Needle thickness | 80um | 
Band Length | 290~310um | 
Wafer 우측 하단向 Position
Wafer Center 우측向 Position
Youngil Kwon

## Slide 32
Pictures from mounting test at CERN

## Slide 33: Summary
Blank wafer status: wafers for next runs procured, work on QA ongoing
Interconnect R&D: spTAB bonded pALPIDEfs assembly in preparation, waiting for plated chips for laser soldering of modules
Ni/Au plating of present wafers ongoing
Dicing and thinning of plated wafers in the next weeks
Probe-card installed at CERN prober; connection tests with pALPIDEfs test system ongoing
Investigations and alternatives for chip transport boxes ongoing

## Slide 35: Assembled prototype of the FPC
viatcheslav.borshchov@cern.ch
View from FPC side
Assembled FPC prototype was electrically and visually tested -results are OK!
(all 60/60 TAB joints are OK, chip is OK).
View from chip side
Top layer-to -chip
Bottom layer-to-chip
Interlayer connection
Different types of bond joints
FPC prototype with mounted chip in
TAB-70 technological frame