## Slide 2: SMACC Twenty-first report [15? min] 11/04/2014
Jean-Philippe Tock (TE-MSC)
On behalf of the SMACC project

## Slide 3
Activities since last LSC (28/03/2014)
  Arc splices installation
    By Activities
    By sectors
  SIT
  DFBA
Dashboards
Specials
  Update on overheated splices
  Logistics, maintenance and mechanics
Activities for the next 3 weeks
Conclusions

## Slide 4
Sector 56 :
  Final leak test and reconnection of DFBAK
Sector 67 :
  Final leak testing
Sector 78
  Work on NC
  Reconnection of DFBAO-SHM
Sector 81
  Pressure test on 8.04.2014
Sector 12 (Priority)
  Reclose last ICs
  Progress on insulation vacuum leak test
Sector 23
  Complete all M lines rewelding
  Complete M-lines leak testing
  Progress on reclosure of ICs
Sector 34
  Complete work on overheated splices
  Progress on M lines rewelding
Sector 45
  Complete installation of shunts but overheated splices
  Progress on electrical insulation
  Progress on consolidation of Q diodes
SMACC Main activities for the last 2 weeks

Completed

All ICs are reclosed


> 90% ICs reclosed

Completed yesterday



Completed, one K hose to be replaced
Completed except in Q7/DFBAO IC
 Successful

From last LSC (28.03.2014)
17thCC/DFBA: Shunts resoldered, spool pieces busbars ready for reconnection // Last subsector to be leak tested
Completed


 4 repaired  a new one appeared
9/14 subsectors successfully leak tested, remaining ones under LT


>98 % of the insulations installed
All validated, ready for cool-down for SMACC

> 95% rewelded

3 ICs remain to be shunted

## Slide 5
SEQUENCE AND STATUS
OK to open
Open ICs
Install DN200
Open M sleeves
ElQC (old splices)
Undo / Redo splices
ElQC (new splices)
Machine Cu
ElQC after Cu mach.
Install shunts
3 ICs to do
ElQC after shunt
3 ICs to do
Insulate splices
6 ICs to do
Weld M
≈ 7 sectors
Leak test M
≈ 6.5 sectors
Close IC
≈ 6 sectors
Final LT
≈ 4.5 sectors
Consolidate Q diodes
Cancelled
Completed
Completed
Completed
Completed
Completed
Non-conformities (Before P Test)
Non-conformities (After P Test)
2 completed
≈ 5 sec-eq
Completed in 1st sector (67)… so far
Completed
Completed
Completed
Completed

## Slide 6
SMACC Progress report by activity
Shunts are installed in 1692/1695 ICs
Completed in 6 sectors
4 equipped in the last 2 weeks
Only 3 ICs remains in the whole LHC, only linked to overheated cables
Last shunt forecasted for end of April 14
Courtesy H Prin

## Slide 7
SMACC Progress report by activity
Insulation box: Installed in 1689/1695 ICs
Courtesy H Prin / G Maury
On the baseline
Won’t be on critical path
Only 6 ICs left for LHC [Was 7 in 7 first sectors 2 weeks ago] (<0.4 %)
(4 weeks sliding average)
*Estimate for W15

## Slide 8
SMACC Progress report by activity
Consolidation of Q Diodes: Completed
Courtesy L Grand-Clement
10.04.2013 : Consolidation of the last quadrupole diode
Work optimised despite the lack of components
Impact on other activities was minimum

## Slide 9
SMACC Progress report by activity
M Welding : Done in ≈ 7 sec-eq:
Routinely 60 ICs/week
Work concentrated in 1 sector, starting in 45, the last sector
No major disturbance
Exactly on the baseline presented on 4.10.2013
As presented LSC 4.10.2013
11 weeks @ 34
18 weeks @ 51
Slightly ahead of revised schedule
Courtesy S Atieh

## Slide 10
SMACC Progress report by activity
Excluding S45 welding , all remaining activities up to M welding fit on 12 lines !
Activities in production mode (other ones are targeted interventions):
M lines rewelding
M lines leak testing
Checks before closure
IC reclosure
Insulation vacuum leak testing
ElQA

## Slide 11
SMACC Progress report by activity : LMF-QA Main Splices consolidation

## Slide 12
SMACC Progress report by activity
M sleeves leak testing : Completed in ≈ 6.5 sec-eq
Following the M lines rewelding, less regular by nature (sectorization)
≈ 2 weeks behind schedule, tendency to reduce
Under recovery as for the M welding
See next presentation (P Cruikshank / TE-VSC)
Courtesy P Cruikshank / L Mourier

## Slide 13
SMACC Progress report by activity
Reclosure of interconnections : ≈ 6 sec equivalent are reclosed
Baseline rate achieved despite openings for special interventions
Courtesy A Chrul / A Musso

## Slide 14
SMACC Progress report by activity
Final leak test: ≈ 4.5 sec equivalent
About 10 days behind schedule, reducing
See next presentation (P Cruikshank / TE-VSC)

## Slide 15
SMACC Sector 67
All ICs reclosed and validated; Ready for cooldown from SMACC point of view
  Cooldown planned on 5-7.05.2014
SMACC Sector 12
All ICs are reclosed
>75% ICs finally leak tested (9/14 vac subsectors)
Some issues to be fixed after pressure test:
  Thermometer
  Leak(s)
Pressure test on 13.05.2014

## Slide 16
SMACC Sector 81
Successful pressure test on 8.04.2014
Courtesy O Pirotte (TE-CRG)
10 leaks to be treated after flushing (W21)

## Slide 17
SMACC Progress report by sector
Sectors 56 & 78:
  Only activities linked to DFBA-SHM reconnection
  56: Leak to be repaired with a resin next week
Main activities are :
  Reclosure of Ics
  Preparation for insulation vacuum LT

## Slide 18
SMACC Progress report by sector
Main activities are :
  One NEW overheated splice to redo
  Leak test of M lines
  Start of reclosure of IC
Main activities are :
  Work on overheated splices
  Start of M lines rewelding

## Slide 19
SMACC Dashboards
Shunting is nearing completion (3 ICs, < 0.2 %)
The installation of insulation boxes is nearing completion (6 ICs, < 0.4 %)
Welding and M leak test rates are recovering the baseline schedule in parallel
Reclosure: On baseline, nominal rate achieved
Insulation vacuum leak test : RECOVERING
Attention to put on facilitating the work of leak test teams
For activities linked directly to splices, only targeted interventions remain

## Slide 20
 Completed
 Completed
New
New
New
New
New
New
 Completed
New
New

## Slide 21
SMACC Progress report SIT
Team is reduced but can be remobilised very quickly
Activities linked to NC, leaks and overheated splices
Installation of the last RQF/D return on-going (L5)
Installation of the 2nd cryo BLM in L5
Leak in S56 : Test next week at the surface then in-situ
Courtesy N Bourcey, S Le Naour

## Slide 22
SMACC DFBA
Courtesy A Perin, E Vergara
100% of splices consolidated, 96% of sleeves welded
10/16 DFBAs re-closed, insulation vacuum leak tests to be done
4 DFBAs (sect. 6-7 & 8-1) pressure tested

## Slide 23
SMACC Dashboards
Baseline: 92.0 % (87.3 %)
Completed: 90.5 % (87.1 %)
Delay 3 (1) days
Baseline: 82.9 % (78.6 %)
Completed: 84.9 % (79.5 %)
Delay -20 (-3) days
 On schedule
 Ahead of schedule
Arc splices: Just on schedule
SIT Reactive Ahead of schedule
DFBA: All splices consolidated Recovering
Baseline: 93.1 % (89.7 %)
Completed: 87.1 % (74.6 %)
Delay 1.5 (2.5) months
 Recovering

## Slide 24
SMACC Dashboards
Progress:
Baseline: 91.0% (86.6 %)
Completed: 89.3% (85.5 %)
Delay 4 (3) days

## Slide 25
SMACC Overheated splices (1/2)
Courtesy C Scheuerlein, F Savary
From LSC of 28.03.2014
13 + 1 on-going
1 + 1 NEW
0
6 5
Confirmed as is
Thanks to team reinforcement and learning effect, should not impact the overall schedule
Reminder: Very delicate operation

## Slide 26
SMACC Overheated splices (2/2)
Courtesy C Scheuerlein, R Ostojic, F Savary
Magnetisation result of sample extracted at the cable extremity shows a strong degradation.
Will be repaired with new cables, coherently with other cases
Normally the last one
Quality > Schedule

## Slide 27
SMACC: Logisitcs, Maintenance, Mechanics (1/3)
Courtesy Ph Canard, R Faes (CSI)
Pts
5
6
8
1
2
4
Gestion Bases de chantier les sites
P2 June 2013
Thx EN-MEF
P6 Nov 2013
P6 Apr 2013
Thx GS

## Slide 28
SMACC: Logisitcs, Maintenance, Mechanics (2/4)
Courtesy Ph Canard, R Faes
Usinages, entretien materiel mecanique et electrique

## Slide 29
SMACC: Logisitcs, Maintenance, Mechanics (3/4)
Courtesy Ph Canard, R Faes
Logistique Livraisons
Plus de 16000 kms parcourus
Plus de 1200 livraisons en surface et dans le tunnel

## Slide 30
SMACC: Logisitcs, Maintenance, Mechanics (1/3)
Courtesy Ph Canard, R Faes

## Slide 31
SMACC Summary on progress
Main 13 kA Splices:
 On schedule
 Q Diodes consolidation : COMPLETED
 Overheated splices : should be just OK within present schedule
Special Interventions:
 Ahead of schedule  Almost all planned interventions are completed
 Focus on NC
DFBA:  Activities are back in the shadow of arc splices
SMACC:
 About 4 days of delay, wrt schedule defined > one year ago !!

## Slide 32
Sector 56 :
  Final leak test and reconnection of Q7/DFBAK
Sector 67 :
  Ready for cool-down for SMACC
Sector 78
  Work on NC
  Final leak test
Sector 81
  Purge, ElQA, flushing,…
Sector 12
  Complete insulation vacuum leak test
  Pressure test for 13.05.2014
Sector 23
  Complete reclosure of Ics
  Insulation vacuum leak test
Sector 34
  Repair (hopefully) last splice
  Complete M lines rewelding (except NC)
  M lines leak test
  Start ICs reclosure
Sector 45
  Complete repair of overheated splices
  Start rewelding of M lines
SMACC Main activities for the next 3 4-days weeks
Easter
Thursday 1st of May

## Slide 33
Conclusions
Project is almost back on schedule (4 days delay)
  Mind the last X % effect
  Leak on vac vessel in S56 to be fixed and validated
Overheated splices : Two more to do but still in the shadow of other activities
DFBA consolidation is nearing completion 
S67 is ready for ElQA before cool-down
S81 successfully pressure tested (8.04.2014)
But known leaks to be treated after
Activities directly linked to splices are in targeted interventions mode
Activities in production mode are mainly welding, leak tests, checks before closure, ICs reclosure, ElQA