## Slide 1: BI.SMH 2014 leak
M. Hourican, J. Borburgh

## Slide 2: Latest Saga…
On 8th April during the final leak testing of the PSB a high pressure was noticed in the vicinity of the injection septa
Leak test on cooling circuit gave the bad news,
  PHe at 3 bar gave leak rate of 2.5x10-5 mbar ltrs s-1
  Possible causes
    Cooling circuit leak, insulator cracked, leak on electrical feedthrough,..other

## Slide 3
BI.SMH
A brief history of time..
Stack #1 failed May 2009, “stored“ in blg 151 (“condemned”)
Stack #2 Renovated with unused isolators, but 2 brazes per magnet were not redone. Currently installed in PSB and leaking (to be replaced when..?)
Stack #3, currently being renovated, (estimated ready for 29/4)
Refurbished 4 kA spare feedthrough spring 2013 (SI.3.47.1238.1)
4 spare coils available (upgraded to ‘77 spec in 2010), but brazes and ceramic insulators are still original (from 1973!)
New insulators delivered 10.04.2014
Note: strategy presented in LSC meeting on 24th January 2014

## Slide 4
Potential fault locations
coil drawing 1972 !
ceramic insulator
Under-vacuum brazes
septum side view
top view
septum
cross-over made from braid
cooling circuit
cooling circuit
rear conductor

## Slide 5
Planned Intervention for faulty BISMH in PSB
Replace feedthrough
(Note: this has never been performed by current staff and this procedure is being investigated)
Transport stack #2 to 867
Dismantle and renovate
Leak test magnets
Magnetic measurements
Leak test complete stack
2. Install either the original Stack (#2) or install the newly renovated stack #3
3. Leak test BISMH
Feedthrough OK
NO
YES
Open tank and leak test stack in-situ to try to determine the fault location
Remove stack and leak test electrical feedthrough in-situ

## Slide 6: Stack No. 3 renovation
Impact has been created (45141)
WDR Work dose planning established and being followed up

## Slide 7: Proposed strategy Stack #3 in blg 867
1. Remove each magnet from stack and perform leak test (Diagnostics)
2. Replace ceramic insulators, redo brazes and verify leak tightness of each magnet individually
3. Reinstall magnets on stack
5. Magnetic measurements
6. Vacuum testing of complete stack
7. Transport to PSB
Vacs

## Slide 8: Outstanding
Failure cause/location to be determined to assure reliable repair.
Which stack to use in case of feedthrough failure?
Feedthrough replacement procedure to be determined.
After PSB intervention, prepare operational spare stack.

## Slide 9: Initial Planning
  Refurbishment of the spare in bldg 867.
  Aim for repair first half of 2014, for spare to be operational once PSB starts up ( 30 May 2014 with beam).
  WDP to be prepared:
    For stack #1 (2009)
      https://espace.cern.ch/rpps/wdp/docs/PS%20Complex/Booster/2013-2014_LS1/2014_Renovation_stack-1_(2009)_BISMH.xlsx
      working time estimated: 11.4 man.hours
      collective dose estimated: not done (needs handling to establish dose rates)
      radiation Dmoy=250 µSv/h @ 40 cm
    For stack #3 (2013)
      https://espace.cern.ch/rpps/wdp/docs/PS%20Complex/Booster/2013-2014_LS1/2014_Renovation_stack-3_(2013)_BISMH.xlsx
      working time estimated: 2.6 man.hours
      collective dose estimated : 1.2 mSv
      radiation Dmoy=100 µSv/h @ 40 cm

## Slide 10: October 2013 BISMH exchange
Fault indication on magnet stack
Stack #3 removed from tank and stack #2 installed
Work Dose planning anticipated collective dose: 1.9 mSv (worst scenario foresaw 3.1 mSv)
collective dose measured for intervention: 2.1 mSv
  Misalignment of electrical connection → additionally 148 µSv
  Transport container too big for truck → additionally 62µSv
For info:
collective dose taken for the first exchange in 2009: 4.8 mSv.