## Slide 2: SMACC Twenty-second report [20 min] 06/06/2014
Jean-Philippe Tock (TE-MSC)
On behalf of the SMACC project

## Slide 3
Activities since last LSC (11/04/2014)
  Arc splices installation
    By Activities
    By sectors
  SIT // DFBA
Dashboards
Specials
  DN200 painting
  Overview
Activities for the next 4 weeks
Conclusions

## Slide 4
Sector 56 :
  Final leak test and reconnection of Q7/DFBAK
Sector 67 :
  Ready for cool-down for SMACC
Sector 78
  Work on NC
  Final leak test
Sector 81
  Purge, ElQA, flushing,…
Sector 12
  Complete insulation vacuum leak test
  Pressure test for 13.05.2014
Sector 23
  Complete reclosure of Ics
  Insulation vacuum leak test
Sector 34
  Repair (hopefully) last splice
  Complete M lines rewelding (except NC)
  M lines leak test
  Start ICs reclosure
Sector 45
  Complete repair of overheated splices
  Start rewelding of M lines
SMACC Main activities for the last 3 weeks
Completed

All ICs are reclosed



Completed



All interconnections reclosed
1 vacuum subsector (Including DFBAO) to be finally leak tested
Interventions after pressure test & before cooldown on-going

From last LSC (11.04.2014)
DFBAK: All lines reconnected // IC closed // Last subsector to be leak tested
Completed


 All repaired
Successful pressure test, to be flushed

< 60/212 ICs to close
Under cool down

Completed

8
Just pressure tested
Completed
Completed
Completed
≈ 1/2 vac subsectors finally leak tested



## Slide 5
SEQUENCE AND STATUS
OK to open
Open ICs
Install DN200
Open M sleeves
ElQC (old splices)
Undo / Redo splices
ElQC (new splices)
Machine Cu
ElQC after Cu mach.
Install shunts
ElQC after shunt
Insulate splices
Weld M
Leak test M
Close IC
≈ 7.7 sectors
Final LT
≈ 6.4 sectors
Consolidate Q diodes
Cancelled
Completed
Completed
Completed
Completed
Completed
Non-conformities (Before P Test)
Non-conformities (After P Test)
4 completed
≈ 6 sec-eq
Completed in 1st sector (67)… so far
On-going in S81
Completed
Completed
Completed
Completed
Completed
Completed
Completed
Completed
Completed

## Slide 6
Last overheated splices consolidated
Courtesy H Prin, N Dalexandro
16 were repaired

## Slide 7
SMACC Progress report by activity
Courtesy H Prin, M Pozzobon

## Slide 8
SMACC Progress report by activity
Note the small size of the team …
A lot of work was necessary to give access to splices and reclose

## Slide 9
SMACC Progress report by activity
Courtesy H Prin / G Maury

## Slide 10
SMACC Progress report by activity
Courtesy H Prin / G Maury

## Slide 11
Courtesy F Savary

## Slide 13
SMACC Progress report by activity
As presented LSC 4.10.2013
11 weeks @ 34
18 weeks @ 51
Courtesy S Atieh
Completed on schedule
Regular rate, not because it was easy but because it was well prepared

## Slide 14
SMACC Progress report by activity
Courtesy S Atieh

## Slide 15
SMACC Progress report by activity
Courtesy S Atieh

## Slide 16
SMACC Progress report by activity
Courtesy P Cruikshank / L Mourier
Last M sleeve leak tested one week after the last weld
Followed the rewelding rate

## Slide 17
SMACC Progress report by activity
Courtesy P Cruikshank / M Pojer
Excellent collaboration between the teams and a very good team spirit
Positive atmosphere
Celebrated in a BBQ co-organised with CSI

## Slide 18
SMACC Progress report by activity
Reclosure of interconnections :
Baseline rate achieved despite openings for special interventions
< 60 ICs to reclose
≈ 1 week ahead of schedule
Last «first» reclosure before the end of June … other ones will follow after local interventions
Courtesy A Chrul / A Musso

## Slide 19
SMACC Progress report by activity
Final leak test: ≈ 6.4 sec equivalent
About 1 week behind schedule, reducing
Subsectors under pumping in last sector (S45)
Recovering the baseline

## Slide 20
SMACC Sector 67
  Magnet T ≈ 20 K, ElQA at cold to be done

## Slide 21
SMACC Sector 81
ElQA after flushing completed, no fault on the cold side
Thermometer issue solved
External leaks repaired and under pumping for validation
Internal leaks solved or accepted «as is» except
  C’K leak in A23R8 : Required IC opening and cutting of cryogenics circuit On-going with SIT
  COOLDOWN planned for W26

## Slide 22
SMACC Sector 23 : Successful pressure test on 5.06.2014
Courtesy O Pirotte
Pressure in lines C&D
(Cold masses)
25 bars during 1 hour
Cryomangnet Insulation Vacuum pressure
QRL Insulation Vacuum pressure

## Slide 23
SMACC Progress report by sector
Sectors 12 & 23:
  Pressure tested succesfully
  Interventions to be planned before cooldown: (Leaks [internal in A27R1 E line «clapet type»] , [Ext in 25R2 and internal A23R2]
Leak between DFBA HCM/LCM on DFBAK external envelope
Internal leak on LCM header C, presence of a 2nd leak under investigation
VSC clapet to be consolidated in A31L6 after P Test
Internal leak on C-K circuit to be repaired after P Test
Sectors 56 & 78:
  Only last vac subsector to be leak tested
  Pressure tests before end of June
  Interventions to be done before cooldown

## Slide 24
SMACC Progress report by sector
Final leak test on-going
8/14 vac sec tested
3 leaks under invetigation
Main activities are :
  Reclosure of Ics
  Final leak test

## Slide 25
SMACC Dashboards
Everything is completed but:
  Reclosure: Ahead of schedule, < 60 ICs to reclose; priority given to repair interventions
  Insulation vacuum leak test : Recovering, < 2 sectors to test

## Slide 26
Two activities are on-going :
* Reclosure in S45
* Ins Vac LT in S56, S78, S34
One activity to start:
* Ins Vac LT in S45
Four sectors are succesfully pressure tested for SMACC (S67, S81, S12, S23) so production activities are completed in these sectors

## Slide 27
SMACC Dashboards
Baseline: 98.2 % (92.0 %)
Completed: 98.3 % (90.5 %)
Delay -1 (3) days
Baseline: 89.4 % (82.9 %)
Completed: 92.5 % (84.9 %)
Delay -8 (-20) days
 On schedule
 Ahead of schedule
Arc splices: On Schedule
SIT Reactive Ahead of schedule
DFBA: Depending on progress on last leak tests
Baseline: 97.7 % (93.1 %)
Completed: 92.1 % (87.1 %)
Delay 1.5 (1.5) months
 Recovering

## Slide 28
SMACC Dashboards
Progress:
Baseline: 97.1% (91.0 %)
Completed: 96.9% (89.3 %)
Delay 3 (4) days

## Slide 29
DN200 painting
Courtesy A Musso / A Chrul
Done after final leak test
Progress:
  S81 : Completed
  S78 : 85% done, waiting OK from LT
  S23 : Just started
  S45 : To start
Collaboration between
PAEC-NCP (Pakistan) and
DUBNA (Russia)

## Slide 30
LHC Overview
(*) Some lines with minor repair are not tested to the test pressure, following derogations asked to and granted by HSE

## Slide 31
SMACC Summary on progress
Main 13 kA Splices:
 On schedule
 Overheated splices : COMPLETED
    Activities still in production mode :
    Inspection before closure, Closure of ICs, Final leak test
    Other activities :
Resolution of NCs (leaks, ….)
Special Interventions & DFBA:
Progress according to final leak test
SMACC:
 About 3 days of delay (stable) wrt schedule defined > one year ago !!

## Slide 32
Sector 56 :
  Complete final leak tests
  Pressure test
Sector 67 :
  ElQA @ cold
Sector 78
  Complete final leak tests
  Pressure test
Sector 81
  Comlete interventions on NC
  Start cooldown
Sector 12
  Interventions on NCs
Sector 23
  ElQA, flushing,…
Sector 34
  Complete final leak tests
  Ready for pressure test from SMACC point of view
Sector 45
  Complete reclosure of ICs
  Progress on final leak tests
SMACC Main activities for the next 4 weeks

## Slide 33
Conclusions
All ICs will be reclosed for the first time for Mid of June
The good quality and progress (so far) should be attributed to the commitment of the whole team but also to the thorough preparation. Investment pays off.
Working mode has evolved for most of the activities from a production mode towards specific interventions requiring a high reactivity and coordination of all teams
The baseline for insulation vacuum leak tests (last activity) is under recovery