## Slide 1: Powering & DSO Tests
J. Wenninger for the LHC-CSAP and the LHC-OP sector test and checkout teams.

## Slide 2: Overview of major LS1 Access System modifications
Task Name | Where | Description | ECR
Sectorisation Changes | TI2 | Displacement of Door PPG2145 separating the LHC and the SPS in TI2 tunnel | 1253832
 | LHC1 | Displacement of PADs from UJ14/16 to UL14/16 | 1218906
 | LHC4 | Displacement of PAD UX451 | 1346280
 | USC55 | Creation End-of-Zone Door for Material Transfer Between USC55 and the Bypass | 1236542
Interlocking PM32 | PM/TZ32 | Creation of an Interlocked Service Zone PM32 | 1254796
Access Point Maintenance Doors | LHC | LACS/LASS Top of the Pit Maintenance Doors | 1317397
New Radiation Veto | LHC2,6,8 | New Radiation Vetoes for the Injection Lines and Beam Dump Transfer Galleries | 1254007
Monitoring of Helium Conf. Doors in LASS | TI2/TI8 | Interlocking of Injection Tunnel Upstream Areas with LHC Powering | 1257949
 | LHC | Monitoring of pressure resistant doors in LASS | 1288596
Access – Powering Interlock | CCR, LHC | Change of the Interlocking of Powering and Access systems | 1246780
Monitoring of Doors Important for Control of Activated Air | US32/US76 | Add the following ventilation doors to LASS: YCPV01=US32, YCPV01=US76 | 1288596
 | UP53 | Add the following ventilation door to LASS: YCPV01=UP53 | 
 | LHC2,4,6,8 | Monitor the ventilation doors between Service and Tunnel areas in even points | 
Point 7 Collimation | LHC7 | LHC Point-7 Collimator Region Enclosure and Ventilation Bypass | 1303048
Upgrade of LASS IT Infrastructure | CCC/CCR | Exchange of LASS servers and client computers, upgrade of Siemens PCS7 | 
LACS | CCC | New tool for video, TIM views replace Evolynx LASS ones, upgrade from XP | 
T. Ladzinski

## Slide 3: Test planning - powering
Many access system modifications during LS1 – implementation well on track.
Powering-Interlock tests in June-July:
  validate the functioning of the access-powering interlock
  validate the patrol and EIS-access position signals
Powering-Interlock test dates (Fridays).
  6 June LHC8-LHC1-TI8 (ECX4,TAG42) powering of sector 8-1
  13 June LHC6-LHC7-LHC8 powering of sectors 6-7 & 7-8
  20 June LHC1/1.8-LHC2-TI2 (SPS also) powering of sector 1-2
  4 July LHC2-LHC3-LHC4 powering of sectors 2-3 & 3-4
  25 July LHC4-LHC5-LHC6 powering of sectors 4-5 & 5-6
Access only for GS/ASE to Tunnel and Service Zones
Will be patrolled the evening before – restricted mode!

## Slide 4: DSO test planning
In march two DSO test dates were requested.
  Weekend 4/5 October
  Weekend 11/12 October – BACKUP
With the large number of modifications introduced during LS1, it will be very difficult to compress all tests in a single weekend.
Both weekends will be required for the tests (machine and experiments closed).
  Weekend 4/5 October – Beam Mode Tests by GS/ASE (exhaustive test for new equipment/functions)
  Weekend 11/12 October – the DSO Test (sampling)