## Slide 1: R2E relocation & shielding activities: status report
Anne Laure Perrot EN/MEF- LE
On behalf of the R2E coordination team
LS1 Committee – meeting #48, 27th June 2014

## Slide 2
A. L. Perrot, EN-MEF/LE
2
Points 1 & 4
Michael Jeckel (EN/MEF)
Point 5
Bertrand Lefort (BE/OP)
Point 7
Oscar Andujar (BE/OP)
Point 8
Bettina Mikulec (BE/OP)
Planning &
General coordination (deputy)
Maria Barberan Marin (EN/MEF)
The R2E coordination team
General coordination
Anne Laure Perrot (EN/MEF)

## Slide 3
Contents
Advancement status of the R2E activities in points 1, 4, 5 & 7
Safety
Summary

## Slide 4
Main critical areas
UJ76
UJ14/16
RR13/17
UJ56
RR53/57
US85
UX45
US85
completed
13rd Dec. 2013

## Slide 5
Mitigation activities – general
Phase I: dismantling
Phase III: equipment relocation / installation
    (equipment owners, EN/HE)
Phase IV: equipment commissioning
(equipment owners, GS/ASE, EN/EL, EN/CV, IT/CS)
- equipment removal/storage (equipment owners, EN/HE),
- services removal (mainly EN/EL, EN/CV)
- civil engineering (GS/SE)
Phase II: infrastructures
- civil engineering (GS/SE)
- services installation (mainly EN/EL, EN/CV, IT/CS)
In progress

## Slide 6
Point 1 – advancement status
R2E @ Point 1
completed
UJ14
UJ16
Water Cooled Cables (WCCs) installation
WCC installation
Commissioning QPS, current lead heaters, collimators,
Commissioning QPS, current lead heaters, collimators,
WCCs tests and power converters commissioning
(change of one WCC)
WCC tests and power converters commissioning
Short Circuit Tests (SCTs)
WCC orientation and then tests
Short Circuit Tests (SCTs)
WCC orientation and then tests
April
June
May
end June
Shielding activities (reinstallation, painting)
Shielding activities (reinstallation, painting)
PAD/MAD reinstallation
PAD/MAD reinstallation
Today
Completed with
2 weeks advance
vs baseline
Courtesy M. Barberan
EN-MEF survey
in all areas

## Slide 7
Today - UL16
Point 1 – photos
Before LS1 - UJ16
Today - PAD/MAD in UL16
Today – UJ16
Courtesy M. Jeckel

## Slide 8
Point 1 – photos
Before LS1 – UL16
Today – UL16
Today – RR13
cast iron shielding wall
Courtesy M. Jeckel
Before LS1 – RR13
concrete shielding wall

## Slide 9
First constraint: completion of the QURCA/B for flushing in adjacent sectors scheduled beginning of July (baseline)
Second constraint: cryogenics special cable delivery
Third constraint: manpower availability for cabling
campaign (327 cables)
Window of 15 weeks for cable campaign
Parallel interventions of TE/CRG and EN/EL
Point 4 – advancement status
Main constraints towards completion
Start of the relocation activities in January 2014
Start cabling campaign not before March

## Slide 10
Point 4 – advancement status
Today
TE/CRG:
RF reconnection activities
postponed by 2 weeks due to priority for CD activities
EN/MEF:
Final survey scan
End: 11st July
with 1 week delay
vs baseline
TE/CRG: AMB-MECOS commissioning to be finalised in nominal cryogenic operation condition (week 34 and weeks 40-42 in accordance with the LHC general planning)
no impact on other LHC activities
cables campaign: 3 ½ months
R2E @ Point 4
End foreseen in 2 weeks
Courtesy M. Barberan
Courtesy M. Barberan

## Slide 11
Point 4 – photos
Before LS1 – UX451
Today – US45 PAD
relocated from US451
Today– UX451
Courtesy M. Jeckel

## Slide 12
Point 4 – photos
Before LS1 – ULs 46
Today– ULs 46
Courtesy M. Jeckel

## Slide 13
Point 5 – advancement status
Today
EN/EL cables campaign
(started in December 2013)
EN/CV activities for Safe room
technical issues/complexity,
material delivery => delay
cables corrective actions
WCC & power converters
installation
EN/CV activities
UTAs and control cabinet in UL557
Safe room activities
Commissioning activities
by equipment owners
GS/ASE - Fire detection relocation
EN/HE shielding activities
EN-MEF survey
in all areas
Courtesy M. Barberan

## Slide 14
UL557- Safe room
UL557-
chilled water pipes
UL558 – structure for AHUs (safe room)
UL557- EYC
Cool-down S56
Point 5 – advancement status
Today
Forseen end:
1rst August
Safe room CV activities
Commissioning activities
Short Circuit Tests
under LHC general coordination
on critical path
R2E @ Point 5
End foreseen in 5 weeks
Courtesy M. Barberan

## Slide 15
Point 5 – photos
Today– UJ561
Today– UP56
Today– UP56& UL558
Today– UL558
Courtesy R. Bihery, B. Lefort

## Slide 16
Point 5 – photos
Today– UL557
Today– UL557
Today– UL557
Today– UL557
Courtesy R. Bihery, B. Lefort

## Slide 17
Point 5 – photos
Today– UJ561
Today– UL56
Today– RRs new shielding wall
(cast iron)
Courtesy R. Bihery, B. Lefort

## Slide 18
Point 7 – advancement status
EN/EL cables campaign
(started in November 2013)
cables
corrective actions
EN/EL optical fibers
IT/CS Ethernet installation
EN/CV activities
(UTAs, control cabinets)
TE/CRG activities
(t.b. completed to start CD)
TE/VSC activities
(part t be completed to start CD)
Commissioning by equipment owners
TE/EPC
power converters installation
TE/EPC, TE/MPE
power converters, WIC commissioning
Courtesy M. Barberan
Today =
baseline end

## Slide 19
CSCM tests
NO ACCESS
Point 7 – advancement status
Power converters
commissioning
& warm magnets tests
under LHC general coordination
Today =
baseline end
Forseen end:
25th July
False floor installation
in UJ76 level 1
(procurement issues)
R2E @ Point 7
End foreseen in 4 weeks
BE/BI- BLM
Fast BLMB: relocated beginning of June
Fast BLMED: new readout system ordered in June; installation in October- November; commissioning afterwards.
not included in
the interlock system
Courtesy M. Barberan

## Slide 20
Point 7 – Photos
TZ76 before LS1 and after 235 m wall demolition & 534 m ducts dismantling
UJ76 level 1 before LS1 and today
Courtesy O. Andujar

## Slide 21
Point 7 – Photos
Courtesy O. Andujar
TZ76 level 1 before LS1 and today

## Slide 22
Advancement status - summary
Very efficient preparatory works by all groups
Point
Baseline
Duration
[weeks]
Actual / foreseen
end date
Delay (D)
Advance (A) vs baseline end date
[weeks]
1
61
58
21/06/2014
A:2
Effective
Duration
[weeks]
4
26
26 + 2 =28
11/07/2014
D:1
5
68
66
01/08/2014
A:2
7
57
1+1+57+3+1= 63
27/06/2014
D:6
8
43
43+6=49
13/12/2014
D:6.5
Comments
-
-
1 week delay due to French holidays; 1 week ELQA delay, 3 weeks CSCM tests (no access), 1 week delay false floor and postpone of PC commissioning
2 weeks delay due to additional cables request, 4 weeks delay linked to change of priority by EN/CV
2 weeks delay linked to change of priority by TE/CRG
Very good match between the estimated durations
and the effective durations of R2E activities in situ during LS1

## Slide 23
Safety
Inspection type | Point 1 | Point 4 | Point 5 | Point 7
Electrical security | Done on 03-04/06/2014 Inspector= J-P Julien | Done on 24-25/06 Inspector= J. P. Julien | To be scheduled begining of July Inspector= t.b.c. | To be scheduled after the CSCM (21rst July?) Inspector= t.b.c.
General security | Scheduled on 26/06/2014 Inspector = T. Gilles | Scheduled on 29/07/2014 Inspector= G. Fontana | To be scheduled in July Inspector= M. Renard | To be scheduled after the CSCM (21st July?) Inspector= M. Renard
No safety problem during the R2E activities
Safety inspections:
Safe room point 5: performance tests mid July

## Slide 24
Safety – point 5
Safe room implementation (ECR/ edms: 1334832)
Safe room performance tests by EN/CV scheduled on weeks 30- 31
Filling the holes (services areas / tunnel and machine / CMS)
under the supervision of C. Gaignant & S. Grillot
R2E provided list /images of holes/ducts performed within the project

## Slide 25
R2E Mitigation activities - summary
UJ76
UJ14/16
RR13/17
UJ56
RR53/57
US85
UX45
US85
UJ14/16
RR13/17
UJ76
UJ56
RR53/57
UX45
completed
completed
Still 1 week work
towards completion
Still 2 weeks work
towards completion
Still 5 weeks work
towards completion
Safe room by EN/CV
on critical path

## Slide 26
R2E Mitigation activities - summary
R2E activities are within schedule
Safe room implementation at point 5 is very challenging (CV activities are on critical path)
Very good preparation (started in 2010) and efficient work of all groups during the LS1 allow to stay within schedule
Many thanks to all the groups
Last but not least => safety inspections to be scheduled and carried out by HSE colleagues
Continuous follow-up, weekly Friday’s meetings (#103), carefull preparation/planning and contribution of all teams were crucial for the success
Testing & commissioning: in progress; for the moment only few minors problems detected