## Slide 1: Injectors & LHC report
K. Foraz
on behalf of OSS members

## Slide 2: AD & LEIR
AD
Hardware tests in progress
Access wk.28 (ionic pump replacement)
LEIR
Hardware tests complete
Cold check out in progress

## Slide 3: SPS
BA1:
  QDA11910 repaired & re-installed
  TIDGV re-installed, aligned and connected this week
  Few water leaks found -> punctual access next week – agreed with OP
Other Areas:
  LS1 for the SPS will end this evening!!!!!!!
  Control will be handed back to the CCC this evening.
  OP will conduct a patrol of the SPS this evening.
What’s next
  ABT plan to start conditioning of the Kickers next week.
  EPC will start from next week 8 weeks of hardware tests in preparation for start-up.
  informal morning meetings everyday at 09:00 in the CCC
  Impact – new intervention periods :
    LS1-HWT-SPS (valid from 28th June to 31st August)
    LS1-BA80-SPS (valid from now to 30th September)
    TAG41- AWAKE (Valid from now until October 2016)

## Slide 4: LHC – Sector 12
LSS1R
  Complete: R2E, sealing, bake-out
  What’s next
    Warm magnet tests next week
    Cleaning wk. 28
    IT survey from wk. 28
    ALFA re-installation in Roman Pots: wk. 30
    Safety painting (bis): wk. 35
Arc 12
  Flushing in progress, ELQA after flushing on June 30th and July 1st
  nQPS racks from next week
  Leak status – Repair from July 2nd
    QRL, vacuum subsector B, 1.7* 10-5 mbar l/s @10 bar; leak on header C- localized on 14L2, Spare compensator type C, available and validated by VSC.
    Leak A27R1- line E – 4*10-7 mbar l/s @10bar – 2.5*10-6 @ 19 Bar
  Warm bus bars measurements postponed to July 17th and 18th
LSS2L
  In progress: Short circuit tests, Survey of IT
  What’s next
    Safety painting wk. 27
    Warm magnet tests: wk. 28
    Cleaning wk. 29
  Around Vacuum 

## Slide 5: LHC - Sector 23
LSS2R
  In progress: Short circuit tests, Survey of IT
  What’s next
    Safety painting wk. 27
    Warm magnet tests: wk. 28
    Cleaning wk. 29
  Around Vacuum: TCTP installed 
Arc 23
  Leak status
    External leak on jumper 25R2
    Internal leak
      A23R2: residual 3 . 10-7@ Pa, 3.2*10-4 @ 10bar,now 10-4, suspicion on header E
      11L3 and 19R2 leak on header E
      A7R2: internal leak to be investigated
  ELQA in progress
  Helium spill test in progress
  Flushing from July 3rd
  Painting next week
LSS3
  Raising pump consolidation in progress
  Warm magnet tests wk. 30

## Slide 6: LHC – Sector 34
LSS3
  Raising pump consolidation in progress
  Warm magnet tests wk. 30
Arc 34
  W leak test done
    1 Leak on magnet foot cell 19L4, repair by VSC in progress.
    A11L4: internal leak, 10-7 mbar l/sec, under investigation
  UPS replacement almost finished
  Pressure tests wk. 28 (DFBA) & wk.29 (arc)
LSS4 & P4
  SF and UW, cryogenic, RF maintenance in progress
  R2E: cabling campaign complete, relocation of cryo equipment w. 27-28
  Short Circuit tests wk. 29
  Around vacuum 

## Slide 7: LHC – Sector 45
LSS4R
  Around vacuum: BQS, BCTD, BCTRF installed
  Painting next week
  Short Circuit tests wk. 29
Arc 45
  Closure complete
  W leak tests:
    5 sub-sectors validated
    9 sub-sectors being pumped
  UPS replacement in progress
P5 & LSS5L
  R2E
    UTAs installation, Fire detection commissioning in progress
    Cryo relocation & Commissioning from next week
  600A IST done
  Around vacuum: XRP installed
  Short Circuit tests on IT: wk. 29

## Slide 8: LHC – Sector 56
LSS5R
  600A IST done
  Survey and alignment - Q2 next week
  Around vacuum: XRP installed
  Short Circuit tests on IT: wk. 29
Arc 56
  Pressure test done
  Leak status:
    External leaks: A31L8, A8L6
    Internal leak: A8L6, A1R5, A19R5
  Purge and safety valves installation in progress
  ELQA from July 2nd
LSS6L
  TCDQ IST done
  Safety painting done, but to repeat (wk.38)
  LBDS tests in progress
  Around vacuum

## Slide 9: LHC – Sector 67
LSS6R
  LBDS tests
  Around vacuum – complete
  Safety painting done, but to repeat
  Warm magnet tests wk. 31
Arc 67
  Survey measurements complete
  Stabilization at 20K complete
  CSCM will start on Monday
  Cleaning from wk. 30
  Magnets smoothing from wk. 30
LSS7
  Cleaning in progress
  Chilled water pipes removed
  Doors commissioning wk. 31
  Safety painting: wk. 30

## Slide 10: LHC – Sector 78
LSS7R
  Cleaning in progress
  Chilled water pipes removed
  Doors commissioning wk. 31
  Safety painting: wk. 30
Arc 78
  Pressure test in progress
  Cleaning in progress
  Survey alignment
  Leak identification end of next week
    A27L8 (4*10-8 mbar l/s) internal leak on c’k circuit.
    A11L8 internal leak, evolving from 10-7 to 10-8
    DFBAO internal leak repaired, being pumped
    External leaks: the 2 external leaks on the magnet (“pied”) will be repaired
  Purge and safety valves installation from wk.28
LSS8L
  Short circuit tests finished ?
  IT survey, wk. 29
  Around Vacuum

## Slide 11: LHC – Sector 81
LSS8R
  Around vacuum
  Warm magnet tests wk. 29
  Clenaning wk. 31
Arc 81
  Cool down starting today
  Leak status
    A15R8 – solved
    A23R8, use as is
    Q4R8 – solved
  Cleaning wk. 30-31
  CSCM wk. 33-35
LSS1L
  Survey IT in progress
  Around vacuum - complete
  What’s next
    Cleaning wk. 30
    ALFA re-installation in Roman Pots: wk. 30
    Safety painting (bis): wk. 35

## Slide 12: Conclusions
Injectors
  AD hardware test in progress
  LEIR Cold check out in progress
  SPS: LS1 works finish tonight- Hardware tests from next week (short accesses agreed with OP)
LHC
  SMACC complete !!
  Around vacuum: 22 vacuum sub-sectors to be baked (28%  26%)
  LHC entering in tests phase – Beware of access constraints
SO FAR SO GOOD
See you at LMC for following reports on LHC

## Slide 13: Impact of CSCM on schedule
First draft

## Slide 14: Schematic V3.1 (the official version)
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
Cool-down
ELQA
PT  1
PT  2
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics

## Slide 15: Issues
Leaks = Non Conformities
  Duration depends on type and location of leaks
  Cost: we saw that 2 weeks is a minimum
Sec34 & 45 1 week planned. W.r.t to experience on 3 sectors it seems not enough !!

## Slide 16: V3.2 adapted with delays and NC
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
Cool-down
ELQA
PT  1
PT  2
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics
PT  1

## Slide 17: V3.2 - cleaning
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
Cool-down
ELQA
PT  1
PT  2
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics
Can’t be done with LHe
Preferably before Cool-down
During NC, but logistics might be an issue

## Slide 18: V3.2 – Sector tests
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
Cool-down
ELQA
PT  1
PT  2
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
Cool-down
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
Cool-down
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics

## Slide 19: CSCM
CSCM will cost 4 weeks per sector

## Slide 20: 4.0 : CCSM impact on schedule
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
ELQA
PT  1
PT  2
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics
Cool-down
CSCM
Cool-down
CSCM
Cool-down
CSCM
PT  1
Cool-down
CSCM
Cool-down
CSCM
PT  2
Cool-down
CSCM
PT  1
CSCM & powering tests
PT67 // CSCM in sec.12
PT81 // CSCM in sec. 56 & 78
PT12&23 // CSCM in sec. 34 & 45

## Slide 21: V4.0: CCSM impact on schedule (with survey)
Pressure test
Cool-down
Flushing, nQPS, ELQA
NC
ELQA
PT  1
PT  2
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics
Cool-down
CSCM
Cool-down
CSCM
Cool-down
CSCM
PT  1
Cool-down
CSCM
Cool-down
CSCM
PT  2
Cool-down
CSCM
PT  1
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Slide 22: V4.0: shifts
The nightmare of co-activities and access matrix, between ELQA, BLM, Survey and Powering tests
We all know, the program will be different, but just to warn you that Shifts will be needed !!
Already agreed with Survey & ELQA & BLM
Tentative schedule

## Slide 23: V4.0: Sector tests
Pressure test
Flushing, nQPS, ELQA
NC
ELQA
PT  1
PT  2
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
Pressure test
Flushing, nQPS, ELQA
ELQA
PT  1
PT  2
NC
ELQA
CSCM
PT  1
PT  2
ELQA
CV maintenance
ELQA
PT  1
PT  2
NC
Flushing, nQPS, ELQA
ELQA
CV maintenance
Cool-down
CSCM
PT  1
PT  2
ELQA
Pressure test
Machine Check-out
Beam Commissioning
Physics
Cool-down
CSCM
Cool-down
CSCM
Cool-down
CSCM
PT  1
Cool-down
CSCM
Cool-down
CSCM
PT  2
Cool-down
CSCM
PT  1

## Slide 24: CSCM impact on schedule
4 weeks (minimum) impact on beam ON
   Physics Week. 19
nPQS & mQPS to be closely followed
Shifts organization will be challenging !!