## Slide 1: Evolution of LARP
Giorgio Apollinari, Fermilab
LARP Director
KEK, HiLumi/LARP 4th Meeting – Nov. 17th-21st, 2014

## Slide 2: A Cambrian Ocean …

## Slide 3: HEP Strategy
European Strategy for Particle Physics - Update 2013
Europe’s top priority should be the exploitation of the full potential of the LHC, including the high-luminosity upgrade of the machine and detectors with a view to collecting ten times more data than in the initial design, by around 2030…
US Prioritization for Particle Physics (P5) - May 2014
Complete the LHC phase-1 upgrades and continue the strong collaboration in the LHC with the phase-2 (HL-LHC) upgrades of the accelerator and both general-purpose experiments (ATLAS and CMS). The LHC upgrades constitute our highest-priority near-term large project (Recommendation to HEPAP).
HL-LHC from a study to a PROJECT
300 fb-1 → 3000/4000 fb-1

## Slide 4: New IRs
4
L. Rossi @Kick-off Meeting 11 Nov 2013
Q1-Q3 : R&D, Design, Prototypes and in-kind USA
D1 : R&D, Design, Prototypes and in-kind JP
MCBX : Design and Prototype ES
HO Correctors: Design and Prototypes IT
Q4 : Design and Prototype FR
CC : R&D, Design and in-kind USA
CC : R&D and Design UK
ATLAS
CMS
G. Apollinari – Evolution of LARP

## Slide 5: Where does US LARP come in ?
More Luminosity: increase squeeze at interaction region
  Increase magnet aperture, therefore increase field.
  Use Nb3Sn Technology as Baseline
More beam: larger beam-beam interactions in region where they are brought close together.
  Solution 1: keep beam as separated as possible increasing crossing angle from 300 mrad to 600 mrad. Use Crab Cavities as Baseline
  Solution 2 (Plan B): If solution 1 does not work, reduce crossing to 300 mrad and mitigate beam-beam interaction with Long Range Beam Beam Wire or hollow e-lens (R&D effort).
  Control possible transverse instabilities or e-cloud effects with Wide Band Feedback System (R&D effort).

## Slide 6: Anomalocaris
First rule: survive !
  that is: know the law of the land and live by it !

## Slide 7: DOE Critical Decision
A DOE construction project is governed by DOE Order 413.3B
  https://www.directives.doe.gov/directives-documents/0413.3-BOrder-b
  Applies to capital assets projects having a Total Project Cost greater than or equal to $50M
DOE projects typically progress through five Critical Decision (CD) gateways, which serve as major milestones
  Each CD marks an authorization to increase the commitment of resources by DOE and requires successful completion of the preceding phase or CD
We call the construction project US-HiLumi, to distinguish it from the LARP “R&D” Program
US-HiLumi: What, How and How Much

## Slide 8: The “What”: Key Performance Parameters (KPP)
Note: preliminary status of CC “baselining”
Beyond SPS test makes for difficult estimates

## Slide 9: KPP (2)

## Slide 10: The “How”: Schedule View
“CERN” HL-LHC PDR Milestones
  2015 Release of Technical Design Report
  2017 Testing of Prototypes
  2017-2021 Construction
  2021-2022 Inner Triplet String Test (not covered by US-HiLumi, LARP2 ? )
Frozen Baseline

## Slide 11: US-HiLumi Magnets Timeline
Plan requires CD-3 approval by January 2018
Plan requires two years of production preparation funding
  Tooling, materials, parts, and personnel must be in place to start coil series production in two lines by CD-3

## Slide 12: The “How Much”: Project WBS and Cost Estimate
Preliminary WBS
  Created for Magnets, Crab Cavities, Electron Lenses, and Wideband Feedback System
  Responsibilities assigned down to Level 3 (L3s)
  Decomposition into WBS activities in progress
  Basis of Estimates (BOEs) at the Activity Level (Working Package Level) in most cases
    BOE Template was created and distributed to estimators
Target is to have an updated cost estimate completed before the end of the year
  Previous rough estimate end of CY2012
Possible input/supporting documentation to CERN Cost & Schedule Review in February 2015
Input to DOE/CERN agreement and needed budget funding profile

## Slide 13: BOE Template
Excel Workbook with automated features

## Slide 14: Standard Contingency Tables

## Slide 15: Example of assumptions: Magnet Production Throughput
Plan requires 2 MQXF magnets every ~ 5 months
  Need two production lines for:
    Coils
    Coil Pack Insert
    Yoke/Shell Assembly
    Quadrupole Assembly
  One set of tooling will be available from LARP, but need more. For example:
    Coil throughput requires multiple tooling in each coil production line:
      1 Additional Mandrel Assembly per line
      3 Additional Reaction and Impregnation Tooling per line

## Slide 16: Cost Slide with all caveats
Extremely preliminary output as of Nov 15th, 2014
L2/L3 inputs taken without critical examination. Not all inputs of same maturity level
Individual labs rate for SWF, 1FTE=1,768h
Escalation included at 2.8%/y
Cost Profile to be matched to DOE Funding profile (still unknown)

## Slide 17: Cost Slide with all caveats (2)
Close to expected ~200 M$ US contribution to LHC, but cuts to this list might be necessary (assuming Cost Estimate is robust)
Approximately 300 FTEs effort in US
SWF-to-M&S close to 1-to-1
“Escalation” is a bitch

## Slide 18: Pikaia
Possible precursor to Cordata (all “superior” life forms)

## Slide 19: MQXF Main Parameters
140 T/m in 150 mm coil aperture
Q1/Q3 length: 8 m
Q2 length: 6.8 m
Max outer diameter: 630 mm
1.9 K operating temperature
Radiation strength: > 33 MGy
Field quality: < 1 unit (https://espace.cern.ch/HiLumi/WP3/SitePages/Home.aspx)
ATLAS
CMS

## Slide 20: HQ as Risk Reduction
Accelerator Quality
Order of magnitude reduction of dynamic effects (ramp rate, field quality) with cable core
Quench performance
HQ02a: operational gradient (80% SSL) with no training
HQ02b: fast training to 95% level with 200 MPa pre-load
Quench protection
380K quench temperature without degradation
Successful first test of the CLIQ system in Nb3Sn
250K
320K
380K

## Slide 21: Feedback from MQXF Winding
No popped strands during winding
Flexible features of end parts are working well

## Slide 22: MQXF schedule
Short model program: 5 CERN-LARP models, 2014-2016
  Coil fabrication starts in 02-03/2014
  First magnet test (SQXF1) in 07/2015 (3 LARP coils, 1 CERN coil)
Long model program: 2 (CERN) + 3 (LARP) models, 2015-2018
  Coil fabrication starts in 2015: 02 (LARP), 10 (CERN)
  First magnet test in 08/2016 (LARP) and 07/2017 (CERN)
Series production: 10 (CERN) + 10 (LARP) cold masses,2018-2021
  Coil fabrication starts in 01/2018
  First magnet test in 10/2019

## Slide 23
MQXFL plan @ LARP
| 2015 | 2016 | 2017 | 2018
MQXFL mirror
MQXFL1
MQXFL1b
MQXFL2
MQXFL3

## Slide 24
Conquest of Earth
Tiktaalik (Neil Shubin) - 400 MY ago

## Slide 25
  “This significant milestone (i.e. MQXF for HL-LHC) will open up the route to much higher energy accelerators than the LHC using for the first time superconductors beyond Nb-Ti in its main magnets.”
Evolution through series of critical design reviews for MQXF design
  November ’14: Conductor and Cable
  December ‘14: Magnet Design
  2015-16: Final Tech. Des. Rev & Production Review
Int. Conductor and Cable Review (CERN Nov 5-6, ’14)
  Reduce keystone angle of PIT cable and support PIT R&D
  Consider same change for RRP cable
  Optimize margin & Confirm strand/Cable specs by model program
Plan to address Cable and Design review recommendations by beginning of 2015.
  US Baseline timing is unlikely to allow further changes in the future
Conquest of HEP by Nb3Sn

## Slide 26: Marella
“Lace Crab”, belonging to the arguably most successful phylum on Earth (Arthropods)

## Slide 27: Crab Cavities
Larger Crossing angle (~300 mrad in HL-LHC vs. ~150 mrad in LHC) calls for a correction of individual bunches orientation
Qc
Qc

## Slide 28: (Another) Inverted Evolution Tree
Lot of Different ideas
28
DQW
RFD
UK-4-rod
Int. Review on May 2014:
Concentrate on two designs (RFD & DQW)

## Slide 29: Bare cavities with interfaces

## Slide 30: DQW HOM Filter
Chart: Freq [GHz]
| 0.56870709686724 | 0.57662996178479 | 0.57806670256427 | 0.59002529779941 | 0.68516485293209 | 0.70120038013562 | 0.72974372341798 | 0.73047943990307 | 0.73081336024214 | 0.74718520807784 | 0.85470303358891 | 0.926925874873 | 0.95902803140808 | 1.0391015385447 | 1.045694272717399 | 1.0554573085624 | 1.0583134144115 | 1.0846257523799 | 1.1421399228415 | 1.1725002778857 | 1.2162745478914 | 1.2607917932463 | 1.295598388609 | 1.3641787931634 | 1.384376197681 | 1.4375654481416 | 1.4546392633666 | 1.4998569418595 | 1.4998617742447 | 1.5089246481762 | 1.5118928908409 | 1.5515122688688 | 1.5851073325589 | 1.6187247099214 | 1.6207643966273 | 1.6393967272209 | 1.659807765418 | 1.6643476269325 | 1.6645196193438 | 1.6648578500534 | 1.6657053755232 | 1.6661065152191 | 1.6839297316235 | 1.7422875807156 | 1.7460400559627 | 1.7497176636761
Vert | 3740.6496 | 5.923 | 58.2153 | 72.7111 | 4.3159 | 1360.0834 | 32445.568 | 0.090696 | 8.7298 | 4328.2954 | 89.0427 | 21.9114 | 8915.452 | 3591.487 | 1065.8631 | 4.0858 | 85.5209 | 2176.2125 | 5.2823 | 14783.1435 | 52.5031 | 92110.5975 | 751024.1401 | 1.2495 | 68322.2127 | 2.4794 | 103822.3551 | 367.2718 | 459.7716 | 2.4551 | 23695.716 | 28835.507 | 1408.5845 | 2.9662 | 271123.2397 | 27.2109 | 57.874 | 896.1641 | 42.4971 | 8.9387 | 11306.1732 | 973.3438 | 4.4816 | 561847.6342 | 109.9533
Hori | 207.6009 | 2993.4979 | 2267.6552 | 67.4368 | 1040460.0477 | 1257.508 | 19.1063 | 15.7586 | 0.91988 | 0.1058 | 18994.5516 | 2587508.461 | 297.9276 | 4.9172 | 1.5625 | 598.6908 | 15.0565 | 0.95345 | 650.0934 | 10.9708 | 179354.1441 | 972.3952 | 178.131 | 2337.518 | 5.2502 | 886.8711 | 49715.8338 | 6313.0609 | 3.5547 | 520.3103 | 1.9889 | 1356.5298 | 39.2809 | 27844.3416 | 921.4025 | 526661.2612 | 20697.5625 | 4078.6305 | 17706.7652 | 4755.199 | 59.9612 | 71.1518 | 93753.1898 | 6.3189 | 155565.5311
Longi | 74721.5767 | 451.6295 | 469.2739 | 80154.2564 | 0.012889 | 4626.6952 | 45.2358 | 0.082079 | 2.0308 | 1.0121 | 0.012766 | 0.12062 | 62473.4596 | 90.4243 | 14.4899 | 0.39843 | 20.0417 | 1.595 | 0.00061484 | 260.2971 | 0.64508 | 53615.42 | 20133.3507 | 0.0035702 | 224.4747 | 0.0025041 | 501.676 | 1.4194 | 66.9636 | 0.45506 | 21.1645 | 23933.9117 | 1442.1554 | 2.4915 | 12642.4981 | 0.73043 | 48.1905 | 2243.3533 | 76.6417 | 1.9611 | 22709.9488 | 1083.1806 | 0.14745 | 462.2497 | 1.2332
Impedances are calculated considering the assembling errors. Tables are generated and sent to CERN for verification.
HOM power is about 69 Watts per cavity. Power of transverse modes estimated based on 5mm offsets.
In the worst case the power increased to 86 Watts if HOM frequencies shift in ±2.5 MHz range.
HOM induced heat on the Cu gaskets and Cu pins are in mW range.
Thermal analysis is on-going
Machining study is on-going
Machine from thick sheet
HOM filter with He vessel
Thermal analysis
Machining study
HOM Impedance

## Slide 31: Goals for CC-LARP
Complete SPS Cavities
  Challenges: M&S funding for HOM and tuning mechanics in FY15.
Complete set of International Reviews a-la-MQXF
  HOM design review in early ’15 (?)
Planning beyond SPS Test
  Do we need an LHC Prototype ? YES
  What will LARP or US-HiLumi provide to LHC Prototype ?
  ? 3-V and 3-H Cavities ?
    Aggressive timing (start by 2016) a challenging resources allocation problem within LARP for LHC Prototypes
  Defensible baseline by late‘15 is a must to allow inclusion of CC in US-HiLumi deliverables in a FY18-FY23 Project
    Plans for “Parametric” baseline in January ‘15

## Slide 32: WBFS for Stability Control
Control of Ecloud and Impedance-driven transverse instabilities in the SPS as HL-LHC Injector - Demo system achieved closed loop control November 2012 before LS1
GHz Bandwidth Digital Signal Processing via reconfigurable architecture
Optimal Control Formalism - allows formal methods to quantify stability and dynamics, margins
Research Phase uses numerical simulations ( HeadTail), Reduced Models, technology development, 1 bunch Demonstrator, SPS Machine Measurements

## Slide 33: Stripline kicker & Power Amp.
CERN, LNF-INFN, LBL and SLAC Collaboration. Design Report SLAC-R-1037
Stripline fabricated by E. Montesinos et al , Installed with 3 kicker support system.
New wideband power amps evaluated. Selection of 1 GHz amps for Dec. 2014
Slotline Kicker design in optimization ( S. Verdu) - fab in 2015

## Slide 34: MD Studies in FY15 & FY16
The Demo system is being upgraded for MD studies, and technology development through the end of 2016
  Explore scrubbing fill control - MD November 2014, closed-loop December 2014
  Explore Q20 control methods ( New filters? Multiple pickups?) - optimize system performance
  Validate multi-bunch control Spring FY2015
  Diagnostic and beam instrumentation techniques to optimize feedback parameters and understand system effectiveness
  Evaluate Stripline and Slotline wideband kickers and RF Amplifiers with beam
  We benefit from synergistic combination of simulation models, machine measurements, and technology development
Technology Development and system estimation for 4 -8 GS/sec Full-function system
  lab evaluation and firmware development
  estimation of possible bandwidths, multiple pickup/kicker architectures, technology options
WBFS has been estimated and budgeted within the LARP system for future production decision

## Slide 35: Hollow e-beam Collimation
Electron Beam stability provided by strong axial magnetic fields
protons
antiprotons
electrons
5-kV, 1-A electron gun
thermionic cathode
200-ns rise time
conventional solenoids
0.1–0.4 T
superconducting solenoid
1–6 T
collector
6 m total length
Stancari et al.: CERN-ACC-2014-0248, arXiv:1405.2033

## Slide 36: LARP Goals (FY15-FY17)
Overall goal: minimize the risk of Project in FY18-FY23
  Build 5 QXF Magnets
    2 1-m long SQXF
    3 4-m long LQXF (including 2 Mechanical Structures)
    Develop/Commission 2 production lines (FNAL/BNL)
  Deliver Four Dressed Crab Cavities for SPS Test
    2 QWR
    2 RFD
  Support Toohig Fellowship
  Support R&D on Acc. Science (if possible)
    Deliver Fully Functional WBFS for SPS Test
    Support studies on e-hollow lenses

## Slide 37: LARP funding Evolution: FY14 to FY15
Good News (~Aug ‘14):
  Guidance for LARP-FY15 increased to 14M$ from 12.6M$ in FY14
  Good hope for additional funding at ~1M$
Recent News (~Nov ‘14):
  FY15 started in Continuing Resolution until Dec 11th 2014
  Fears of year-long CR (no new FY15 Budget approval, support based on ~previous year level)
    Rely on DOE internal allocation to maintain LARP at healthy level.
Some tough decisions in FY15:
  Allocate funding in FY15 to much needed M&S procurements
    Nb3Sn for MQXFL1, mechanical structure for MQXFL1
  Decreased support for SWF, maintain FY15 personnel at FY14 levels by total use of Carry-over funds. FY16 will be critical year !

## Slide 38: Toohig Fellowship Evolution
Commitment to maintain program in LARP and US-HiLumi to facilitate the involvement of PostDocs in the US to work at the leading Energy Frontier Machine for the next ~2 decades
New Toohig Fellow:
  Trey Holick (U. Texas A&M)
Given present uncertainty on existence of a “LARP 2” (i.e. an R&D program in parallel to US-HiLumi Project to support R&D efforts and a generic fellowship) it is necessary to “evolve” the Toohig fellowship toward direct support of US-HiLumi deliverables:
  I. Pong: QA/QC on SC Strand/Cables
  T. Holick: QA/QC on Coils/Magnet Construction
  S. Verdu: CC Construction and Testing

## Slide 39: Picture I tried to provide….

## Slide 40: …and what I probably achieved

## Slide 41: Joint Spring LARP/HiLumi CM
Also LARP-CM24
Where
  Fermilab, IL – USA
When
  May 11th-13th, 2015
  Monday-Wednesday after IPAC15 in Richmond, VA -USA
What
  2 ½ - 3 days format to avoid excessive compression
  No satellite meeting foreseen at this time. If necessary, will be run on May 14th/15th.

## Slide 42: Summary
Constant progress toward Projectization of US-HiLumi
Challenge in prioritizing activities clearly related to US-HiLumi deliverables without over-damaging “R&D” activities
QXF Strand/Cable Review has provided a very strong renormalization point for quadrupole design
  Margin Issue & Lessons from decade-long LARP experience
  Decision following QXF Design Review in Dec ‘14
Support of CC in US-HiLumi might be challenging and a strong proposal for the US contribution can only benefit from proper planning post-SPS test.
Funding is never enough, but nevertheless is not zero !