## Slide 1: Hi-Lumi Conductor Procurement
Ballarino, B. Bordini, L. Oberli
HL-LHC/LARP International Review of
Superconducting Cable for the
HL-LHC Inner Triplets Quadrupoles (MQXF)
Ballarino, TE-MSC-SCD
6th November 2014

## Slide 2
Outline
Quantity of conductor procured
    Procurement of wire for series production
    Cable production plan

## Slide 3
Conductor for MQXF quadrupole
Double sourcing
  Procurement of PIT and RRP Nb3Sn wire
  Needed: (520 + 230) km of RRP
    (520 + 230) km of PIT
    1500 km (8.4 tons) in total
    Procured: 1000 km (4.54 tons) of RRP (+ option for 500 km)
    1000 km (4.54 tons) of PIT (+ option for 500 km)
    The option enables to act in case of problems from one supplier
Notes: 32 km of wire per cable

## Slide 4
Procurement –Nb3Sn Wire
Procurement strategy as presented at the Hi-Lumi/LARP Conductor Internal Review, CERN, October 2013
Procured
Ordered
Planned
Short Model Program
Planned
Long Prototypes
2012
2013
2014
2015
2016
Cabling trials: 5+5 km
SMP: 35+35 km
SMP: 20+20 km
LP: 200+200 km
2017
Conductor
for series
6+6 SMCs
6+6 LMCs
5+5 SMCs (May 2015)

## Slide 5
Procured
Ordered
Planned
Short Model Program
Planned
Long Prototypes
2012
2013
2014
2015
2016
Cabling trials: 5+5 km
SMP: 35+35 km
SMP: 20+20 km
LP: 200+200 km
2017
Conductor
for series
6+6 SMCs
6+6 LMCs
5+5 SMCs (May 2015)
Procurement – Nb3Sn Wire
Ordered in
February 2014
Received
Internal Process Launched
IT Committee 7th Nov. 2014
FC March 2015

## Slide 6
Short Models (UL = 400 m)
5 km (RRP 132/169) + 5 km (PIT 192) – Cabling trials
45 kg delivered from December 2012 to March 2013
35 km (RRP 132/169) + 35 km (PIT 192)
318 kg delivered from November 2013 to October 2014
20 km (RRP 132/169) + 20 km (PIT 192)
182 kg to be delivered in the first trimester 2015
Nb3Sn Wire for MQXF Prototype Program
545 kg of Nb3Sn for MQXF ordered
Long Models (UL = 800 m)
200 km (RRP) + 200 km (PIT)
1.8 ton to be delivered in 2016 (18 months)
Tot = 2.35 tons of Nb3Sn for MQXF Prototype Program

## Slide 7
Procurement of Nb3Sn
Short Model Program
Long Prototypes
2012
2013
2014
2015
2016
5+5 km
35+35 km
20+20 km
200+200 km
2017
Series
6+6 SMCs
6+6 LMCs
5+5 SMCs
2018
2019
1000+500 km
1000+500 km
45 coils
2020
Notes: One coil=30 km of wire

## Slide 8
Strand delivery and cable production
2017
2018
2019
2020
2016
FC March 2016
Adjudication of contracts
Wire delivery (series)
Jan 2017-September 2019
Cabling activity
April 2017-December 2019
Coil winding
Jan 2018-Nov 2020
Cables ready for insulation
Oct 2017-Sept 2020
2021
Preparation
(IT Committee,…)
Delivery
200 km +200 km
Options

## Slide 9
Wire delivery
(32+32) km in Jan 2017
(32+32) after 4 months
(43+43) km after 3 months
(80+80) km every 3 months
(96+96) km every 3 months
Maximum delivery rate  100 km (450 kg) every 3 months
Notes: For the 400 km order: 30 km every 2 months
For the 1500 km order

## Slide 10
Wire delivery and cables production - Series
Delivered to magnet team: 2 months before coils assembly (for electrical insulation)
Available: availability of cables according to wire delivery schedule
Series (32 coils)
Oct 2017
Dec 2017
March 2020

## Slide 11
Wire delivery and cables production - Series
Delivered to magnet team: 2 months before coils assembly (for electrical insulation)
Cables ready for characterization : 3 months before delivery to magnet team
Available: availability of cables according to wire delivery schedule
July 2017
Dec 2019

## Slide 12
Cables production - Series
Delivered to magnet team: 2 months before coils assembly (for electrical insulation)
Cables ready for characterization : 3 months before delivery to magnet team
Available: availability of cables according to wire delivery schedule
Max cable production rate:
2 cabling runs/month
Buffer of 4 cables
March 2020
Series
December 2019
Series
December 2019
August 2019
Series

## Slide 13
Cables production - Series

## Slide 14
Total quantity: 45 cables to be produced during 3 years – 32 for series production
From April 2017 till December 2017: production of cables for earlier deliveries plus buffer of 4 fully qualified cables – to compensate for unforeseen stop of production (cabling machine, QC equipment, delay in measurements…)
Cable production rate: one cable every two weeks. Three months have been taken into account for measurements before delivery of cables for coils winding
Cable production

## Slide 15
Conclusions
A wire procurement strategy has been established in accordance with requirements for cable production
A cable production plan has been established in accordance with requirements for coils assembly
Cabling activity will be performed at CERN. Production of unit lengths of cables will be launched sufficiently early to assure cables need for coils assembly – also in case of late delivery from one wire manufacturer - and availability of a buffer of cables