## Slide 1: MQXF Q1/Q3 Conductor Procurement
A. K. Ghosh
MQXF Conductor Review
November 5-6, 2014
CERN

## Slide 2: Outline
Introduction
MQXFS and MQXFL Magnet Strand and Cable
  Strand procurement for the prototype magnet (qualification phase or pre-production phase)
MQXF Strand Production/Procurement Plan
    Phase I followed by Phase II production
    QA/QC plan at vendor and within the project
MQXF Cable
  Cabling,
  Insulation and Testing
  QA
Summary

## Slide 3: Introduction
For the MQXF Q1/Q3 Magnets we will likely use RRP® wire from Oxford Superconducting Technology
Strand diameter 0.85 mm
  Ti-Ternary Nb3Sn
Cable is a 40- strand Rutherford Cable with stainless steel core
The 1st Short model MQXFS magnet is using coils made with 108/127 strand.
Subsequent Short and Long MQXF magnets will use 132/169 design wire (smaller filament diameter)
Final Specification Documents for the MQXF magnet strand will be released in June’2015.
  It will be a performance based specification as is currently being used for LARP strand procurements.

## Slide 4: LARP-MAG-M-8004-Rev. B (Present spec.)
Ds sub-element diameter
Ic Critical Current
RRR residual resistivity ratio
Process |  | Ti-Ternary RRP® Nb3Sn | 
Strand Diameter, mm |  | 0.85 ± .003 | 
Ic(12 T) at 4.2 K, A |  | ≥ 684 | 
Ic(15 T) at 4.2 K, A |  | > 361 | 
n-value |  | > 30 | 
Ds, µm (sub-element diameter) |  | < 60 | 
Cu-fraction, % |  | > 53 | 
RRR (after full reaction) |  | ≥ 150 | 
Twist Pitch, mm |  | 14 ± 2 | 
Twist Direction |  | Right-hand screw | 
Minimum Piece length, m |  | 750 | 
High temperature HT duration, h |  | ≥ 48 | 

## Slide 5: MQXF Strand Specification
Process | RRP® or PIT Nb3Sn
Strand Diameter, mm | 0.850 ± .003
Ic(15 T) at 4.2 K, A | > 361
n-value | > 30
Ic(12 T) at 4.2 K, A (Reference Only) | (> 632 )
Ds, µm (sub-element diameter) | < 50
Cu : Non-Cu volume Ratio | 1.2 ± 0.1
RRR (after full reaction) | ≥ 150
Twist Pitch, mm | 19 ± 2
Twist Direction | Right-hand screw
Strand Spring Back, deg. | < 720
Magnetization Width at 3 T, 4.2 K, mT | < 300
Minimum Piece length, m | TBD

## Slide 6: LARP-MAG-M-8007 Rev.0 (TBR)
Ds sub-element diameter
Ic Critical Current
RRR residual resistivity ratio
Process | Ti-Ternary RRP® Nb3Sn | 
Strand Diameter, mm |  | 0.85 ± .003
Ic(15 T) at 4.2 K, A |  | > 361
Ic(12 T) at 4.2 K, A (for reference) |  | (≥ 632)
n-value |  | > 30
Ds, µm (sub-element diameter) |  | < 50
Cu : Non-Cu volume Ratio |  | 1.2  0.1
RRR (after full reaction) |  | ≥ 150
Twist Pitch, mm |  | 19 ± 2
Twist Direction |  | Right-hand screw
Strand Spring Back, deg. |  | < 720
Magnetization Width at 3 T, 4.2 K, mT |  | < 300
Minimum Piece length, m |  | 550
High temperature HT duration, h |  | ≥ 48

## Slide 7: Procurement Plan for MQXF RRP-132/169 strand leading up to the Prototype magnet
Require 6 coils for short MQXF; cable unit length 150 m
Require 16 coils for Long MQXF; cable unit length 450 m
Assuming 12% loss in strand from cable mapping
Total length of strand for MQXFS: ~ 50 km (250 Kg)
  55 km of strand is in inventory
Total length required for MQXFL: 350 km (~ 1750 Kg)
  12 km in inventory
  17 km awaiting delivery pending all tests
  A total of 320 km has to be procured in FY’15 & FY’16
Present specification LARP-MAG-M-8004 Rev. B
  Is being replaced by LARP-MAG-M-8007
Notes: Cable in MQXFS coil is 126 m, need minimum 136 m. fabricated length 150 m
Cable in LQXFL coil is 407, need minimum 420 m, fabricated length 450 m
Cable mapping loss 12 % based on actual delivered lengths

## Slide 8: Procurement Plan for MQXF Q1/Q3Magnets
Require 90 coils for Q1 and Q3
Unit length of cable : 450 m
Assuming 12% loss in strand from cable mapping
Total length of strand for UL of cable: 22.4 km
Total length required for project: 2016 km (~ 10,000 Kg)
  ~ 225-250 billets depending on yield
  Present billet size is 45 Kg
Coil production start: Jan’2018
Cable Production start: June 2017
  Final Strand Specification set June’2015
  RFP sent out Oct’2015
  Contract placed Apr’2016
  Phased Production
    Phase 1 : First delivery of 500 Kg May’2017
    Phase 2 : Production Phase July’2017 through Oct’2018
  Delivery complete Oct’2018

## Slide 9: Strand Delivery Schedule
First delivery after 12 months of placing of contract
Cable mapping using first 500 Kg of wire
1 UL will use wire from at least 3 billets

## Slide 10: Strand Delivery Schedule
OST (most likely vendor for RRP wire) has sufficient capacity to handle both CERN and US orders in the same time frame. Production rate ~ 1 metric ton/month. During ITER the production rate was ~ 2 tons/month.

## Slide 11: Cabling and Insulation Plan
Cabling at LBNL
Cabling to start 5-6 months in advance of start of coil winding.
Cabling Start June 2017
  Unit length is fabricated within 1 week.
Cabling throughput required 2 UL’s / month at start, ramping to 3 UL’s/month by July’2018
S2 glass Insulation braided directly onto cable
Vendor: New England Wire Technology (qualified)
  Sufficient capacity to keep up with cabling rate, 2 braiders available.
  Unit length insulated within 5 working days.

## Slide 12: QA-Plan Conductor Qualification - 1
Billets from OST
Cable fabrication
Coil Winding & HT
QC Tests at OST
Cable Qualification
Strand Delivered
HT Witness Sample Test
Cold Mass Fabrication
Billet Qualification
= Hold point
Cable Mapping

## Slide 13: Conductor Qualification -2
Billet Qualification
  Primarily based on vendor QA/QC
  Apply SPC to track uniformity of strand production
  QC tests on a smaller subset of samples at a US lab
  Phase I will have more extensive checks than Phase 2
  OST data will be verified periodically with measurements at a US lab.
Cable Qualification
  This is important and needs to be completed prior to coil winding.
  Mechanical tests, metallographic test, insulation thickness
  Ic and local RRR electrical test: minimum 3 extracted strand and one round wire
    Heat Treatment schedule (HT) as specified for coil reaction

## Slide 14: Strand QC Tests and Reports
QC Tests and Reports
  Cu/Non Cu
  Twist Pitch and Twist Direction
  Ic, n-Value, RRR
  Magnetization Width
  Wire Springback
  Surface Cleanliness Certification
    Eddy Current Certification
  Final Wire Diameter
  Piece Length
Material Certifications:
  Tin Rod
  Niobium Rod
  Niobium/Titanium Rod
  Niobium Sheet
  Copper Tube
Ian Pong will elaborate on the QA/QC plan

## Slide 15: Cable QC Tests and Reports
QC Tests and reports
  Cable dimensions from CMM
  Cable 10-stack measurements
  Cable cross-section microscopy
  Cable Residual Twist
  RRR of Extracted strand
  Ic, n value of extracted strands
  Cabling Report
  Cable Piece Length
  Insulation thickness
Material Certifications:
  Insulation fiber
  Stainless Steel core

## Slide 16: Summary
Strand procurement has been planned to meet coil winding schedule.
  Strand production will last for 30 months
  Phase I used to assess vendor QA/QC and set control limits on full production
Cabling start is planned for 5 months before coil winding
  Goal is to be well ahead of cable required for coil winding
Peak cabling rate of 3 unit lengths/ month during production can be handled at LBNL
  Cable throughput ramps up after one year of operation.
Final Specification documents and Strand and Cable production QA plan to be released in time for strand RFP (Request For Proposal) solicitation in Oct’2015.

## Slide 17: End of Presentation

## Slide 18: Cable Insulation
Insulation is braided directly on cable
  New England Wire Technology (NEWT)
Using S-2® glass (from AGY) with 933 Silane sizing
6 lengths of MQXF cable (170 m long) has been insulated
  Using braiding parameters to yield target specification of 0.145  0.005 mm thickness
  10-stack measurements at 5 MPa are used to determine insulation thickness
  Thickness can be readily adjusted to meet any change to present specification.