## Slide 1
AIDA Governing Board meeting
11 Dec 2014
Final Project Reporting

## Slide 2
Final Reporting Exercise
2
Preparation of the PR3 and Final Reports to the EC
  Period 3 of AIDA (12 months) ends on 31 January 2015
  PR3 Report and the Final Project Report to the EC due on 31 March 2015
  The S&T reporting and the financial reporting of the PR3 report will be similar to the previous reports
  Templates for S&T and financial reports will be provided by the Coordination Office
  Task Leaders and WP Coordinators may use the 1st and 2nd periodic report as a reference (length and content)

## Slide 3
Schedule of S&T reporting for P3
3
WP Periodic Report for P3
WP Coordinators assemble and send to the Coordination Office the P3 Periodic Report for their WP by 25 Jan 2015.
Summary of activities in P3 only
 9
The Coordination Office prepares the P3 Periodic Report, sends it to the StCom for approval and then the report should be submitted to the EC by 20 Mar 2015.
StCom
EC
Task Leaders summarise the activities in their task for P3 only (1 Feb 2014 to 31 Jan 2015) and send them to the WP Coordinator by 15 Jan 2015.
Project Periodic Report for P3 (S&T sections)
GovB

## Slide 4
Schedule of financial reporting for P3
4
Periodic Report for P3 (financial section)
EC
39 Financial Statements (Form C)
+
Consolidated man-power and total budget utilisation for P3 (per WP and partner).
39 Resource Justifications (for the costs reported on the Form C)
+
IRUS for P3 from partner 1
IRUS for P3 from partner n
IRUS for P3 from partner 39
Each beneficiary to provide the official financial reports for P3 (fraction of the full costs!) by 10 Mar 2015
Produced by Coordination Office by 15 Mar 2015
P3 Periodic Report to be sent to the EC by 20 Mar 2015
Each beneficiary to provide the Resource Utilisation Summary (full costs) for P2 by 28 Feb 2015
Produced by Coordination Office

## Slide 5
EC contribution for AIDA (max. 8.0 MEUR)
5
Status of payments to beneficiaries after P1

## Slide 6
Use of resources for P1 + P2 (M1-M36)
6
At Consortium level: 84% of the budget and 97% of the p-m have been used
At Beneficiary level: large variations
Beneficiaries with low use of resources until M36:
ULB (51%), INRNE (38%), NTUA / IASA (50%), UiB (54%), AGH (49%), UU (1%), UCAM (61%), UNILIV (23%), UNIMAN (48%)

## Slide 7
Final distribution of EU funding
7
Final payment to the Consortium expected in summer / autumn 2015
  In case some beneficiaries underspend significantly their estimated budget,
  In case some beneficiaries do not use all EC funding
  → The GB may take a decision for redistribution of the EC funding foreseen in Annex 1
  The need for such redistribution will be assessed only after the P3 financial reports of all beneficiaries have been received (i.e. ~ in April 2015).

## Slide 8
Final Project Report
Consists of 2 main parts:
1) Final publishable summary report (40 pages max)
  Executive summary (1 page in total)
  Project context and objectives (4 pages)
  The main S&T results (foreground) (25 pages)
  Potential impact, dissemination, exploitation of results (10 pages)
2) Plan for use and dissemination of foreground (table format)
  List of scientific (peer reviewed) publications
  List of dissemination activities (e.g. academic dissertations, scientific/technical notes, presentations, conference/workshop papers, posters, press articles, publications other than peer reviewed)
  List of applications for patents, trademarks, registered designs etc.
  Exploitable foreground (table + explanation : purpose, how the foreground might be exploited, when and by whom, IPR exploitable measures taken or intended, further research necessary if any, potential/expected impact)
2,3 lines per WP, no figures
1/3 of a page per WP
2-4 pages per WP, including images, figures
For the project as a whole: expected impact (including the socio-economic impact and the wider societal implications of the project), dissemination activities (e.g. number of PhD students, conferences / workshops, events organised, publications or TA user access)

## Slide 9
Final Report vs. PR3 Report
 | Final Project Report | Period 3 Report
Executive Summary | For the whole duration of the project (48M) | For the reporting period (12M)
Project objectives | For the whole duration of the project (48M) | For the reporting period (12M)
Specific sections | Main S&T results Potential impact, dissemination, exploitation of results | Key performance indicators Deliverables, Milestones Project management
Exploitable Foreground  new section in the Final Project Report :
Publications
Dissemination activities
Patents
Exploitable foreground (table + explanation)