## Short Term
Short Term Actions
Action Number | Description | Responsible | Status | Notes
01.06 | Link to the naming portal from the BE/CO website | Z. Zaharieva | Completed
01.07 | Review and correct the documentation referred to in S. Knoops slides from meeting 01, concerning coding schemes and machine codes | T. Birtwistle / S. Chemli | Completed | Transferred to long term tasks
01.08 | Prepare a Doodle to determine a suitable and regular meeting slot | T. Birtwistle | Completed | Thurs mornings
02.03 | Create an e-group for the naming sub-committee members | T. Birtwistle | Completed | naming-conventions-members
02.04 | Discuss representation from TE/MSC | P. Bonnal | Completed | Rosario Principe to be included for information
02.05 | Present the process for requesting and assigning names | Z. Zaharieva | Completed
03.02 | Include R. Principe and B. Puccio in the egroup for information | T. Birtwistle | Completed | naming-conventions-info
02.07 | Investigate the HSE coding (codes starting with CR) - do guidelines/conventions exist? | G. Perinic | Completed
01.03 | Invite Y. Robert & Jan Janketo a sub-committee meeting to represent the conventions for buildings | P. Bonnal | Completed
03.03 | Present the coding of EL equipment for Linac 4 | J-C. Guillaume | Completed
01.01 | Re-work the Naming Conventions sub-committee mandate (incl. 8 character eq codes) | P. Bonnal | Completed
06.01 | G. Perinic to circulate coding officer roles documentation/presentation | G. Perinic | Completed
01.04 | Discuss with Ch. Delamare the inclusion of an EDMS representative in the committee meetings | P. Bonnal | Completed | Stephan Petit
06.02 | S. Bartolome to present the current situation with naming in projects, and suggest how it should be handled. A date for this presentation is to be defined. | S. Bartolome | Completed | 7th October
01.02 | Identify all naming conventions and sub-naming schemes | All | In progress
02.02 | Collect all convention documentation on the naming portal | Z. Zaharieva + others | In progress
06.06 | Prepare a definition and mapping of different objects | All | In progress
01.05 | Check with the directorate if it is acceptable to allow non-CERN IP addresses to access the naming portal website. Z. Zaharieva to prepare some reasons and submit them to IT. | Z. Zaharieva | Not started
02.01 | Investigate adding a link to the naming portal from the CERN directory. It shall be referred to as Accelerator and Technology Naming Service to avoid confusion with the physics teams | Z. Zaharieva | In progress
02.06 | Re-format the view of naming conventions on the naming portal (LHC and SPS Complex, Parent documents, child documents) | Z. Zaharieva | In progress | Completed - email from ZZ
03.01 | List of groups with and without Group Coding Officers to be prepared | TBD | Not started
05.01 | Zory to upload the documents presented by Y. Robert to the naming portal (they are available on the Indico Page) | Z. Zaharieva | Completed
05.02 | Process for handling location change requests | TBD | Not started
05.03 | Y. Robert to present infrastructure naming needs to the QAC in October / November | Y. Robert | Not started
06.03 | BPMN process to be prepared describing the creation of equipment codes | Z. Zaharieva, G. Perinic | Not started
06.04 | Survey team to prepare a document describing their naming conventions | J-C. Gayde | Not started
06.05 | Link Geode DB to naming portal for naming searches | Z. Zaharieva, J-C. Gayde | Not started
07.01 | Roles of naming service and configuration manager to be defined | TBD | Not started
07.02 | Analyse the potential effectiveness of a forum for group coding officers | TBD | Not started
07.03 | Prepare a BPMN for the naming process, considering different project types and requests | G. Perinic | Not started
07.04 | Update the group coding officer list and seek approval from group leaders. Add GS and RP representation | G. Perinic | Not started

## Mid Term
Mid Term Actions
Action Number | Description | Responsible | Status
01.09 | Produce a glossary of terms related to naming conventions, including their meanings (equipment codes, functional codes etc.) | TBD | Not started
01.10 | Prepare guidelines for assigning equipment codes | TBD | Not started
01.11 | Carry out a feasibility study on the use of 8 character equipment codes | TBD | Not started
01.12 | Prepare role description sheets (group coding officer, naming service etc.) | TBD | Not started
01.13 | Map all existing conventions from a central document / website | TBD | Not started
02.07 | Ensure that machine codings and coding schemes are included and explained in any convention documents | TBD | Not started
03.01 | Investigate the merging of HSE codes into standard equipment codes | TBD | Not started