## Slide 1: CALET Development Status & On-orbit Checkout Plan
JAXA CALET Project Team
Oct. 17, 2014

## Slide 2
SGM
MDC
GPSR
CHD
ASC
HV-BOX
HXM
IMC
TASC
CALET Development Status
All components of CALET were assembled in/on CALET’s structure.

## Slide 3: CALET Development Status
©JAXA/IA
©JAXA/IA
CALET system Integration and initial performance test had been completed on Oct. 10, 2014.
CALET PFT will be continued in JAXA/TKSC from Oct. 20 to Feb. , 2015.
CALET will be launched by HTV5, which is now targeted in summer of 2015 (still under coordination w/NASA).

## Slide 4
Acoustic Vibration Test
Acoustic Vibration Test Room
Acoustic Level : 141.3dB (O.A.) @PFT level
Duration : 60sec
©JAXA/IA
※Test condition is according to HTV Interface Control Document
(JHX-2010085B).

## Slide 5
Thermal Vacuum Test
φ13m Space Chamber
Temperature : -20degC to +50degC
Vacuum Condition : Less than 1x10-5Torr

## Slide 6
EMC Test
Anechoic Chamber
EMC (Electro-Magnetic Compatibility) Test
To verify:
CALET has enough tolerance against radiation noise & conductive noise.
Noise emitted by CALET is less than Interface Requirement.
※Test condition is according to ISS standard requirement
(SSP30237, 30238).

## Slide 7
Functional Tests
During T/V, EMC and after each environmental test, following functional tests will be performed to check CALET system.
MDC activation
Activation of Mission Sensors (CAL, CGBM) and Support Sensors (GPSR, ASC) and heaters
Experiment data and H&S data from each sensors will be checked.
Muon observation tests with CAL will be performed.
Deactivation of the sensors and MDC
These tests will be also performed after shipment to the launch site.

## Slide 8: On Orbit Activation & Checkout Plan
Scheduled to obtain “minimum mission success” observation result in 90days after launch
Constraint for HV activation to wait more than one month for sufficient vacuum condition
Starting routine observation operations 90 days after launch

## Slide 9: On Orbit Activation & Checkout Summary (1 of 3)
Activation
Coolant supply from JEM-EF
Power supply from JEM-EF: MDC activated in stand-by mode
Heater activation
MDC C/O
Data communications (low-rate[1553], midium-rate[ethernet], FTP)
Macro file command
Scheduled(Time-tagged) command
GPSR C/O
GPS time
“Cold start” (GPS satellite acquisition with no almanac data)
ASC C/O
Attitude determination
Raw Image & Jpeg Image acquisition
CHD-FEC C/O
Observation mode transition
LD function
noise & offset measurement
test pulse
IMC-FEC C/O
TASC-FEC C/O
[ditto]
[ditto]
non-HV checkouts

## Slide 10: On Orbit Activation & Checkout Summary (2 of 3)
GBM E-BOX
C/O
CIRC* C/O
[*Infrared earth observation camera; piggy back payload]
HV-BOX C/O
“HOT”part/”COLD”part activation
All LR_PMTs set upto 30V
All APD_DCDCs on with no HV
SYSTEM C/O
CAL event trigger trial
HV protection to regional high density radiations
HV protection to extreme count rate
ASC imaging in GRB event
CGBM C/O
Observation/Diagnostics modes transitions
LD function
noise & offset measurement
test pulse
TH/PH data
Pseudo GRB & event data
non-HV(or very low HV)
checkouts
HV application
HV protection to regional high dencity radiations
noise & offset measurement
test pulse
GRB trigger & event data
HV checkouts

## Slide 11: On Orbit Activation & Checkout Summary (3 of 3)
CHD C/O
IMC C/O
TASC C/O
CAL C/O
HV application on all CHD/IMC/TASC
noise & offset measurement
event data filtering for single event
Single event obaservation trial
HV protection to extreme count rate
CALET ALL LOAD C/O
HV application
noise & offset measurement
test pulse
LD function & trigger & event data
PMT(MaPMT/PD/APD) signal measurement
zero surpression on event data
HV checkouts
All H/W activated & configured
CAL single event obaservation trial
CGBM TH/PH data
CGBM GRB trigger
[ditto]
[ditto]
72hrs(TBD)
run
“nominal” H/W & S/W configuration for observation
Starting CAL calibration for “minimum mission success”
calibration& observation trial
CAL calibration & observation for “minimum mission success”
CGBM calibration & observation trial to establish routine process