## Slide 1: Update on SuperFRS Procurement and Construction
M. Winkler, H. Müller, E.J. Cho, P. Schnizer
5th CERN-GSI Committee Board Meeting

## Slide 2: Outline
Status SC Dipoles (including updated schedule)
Status SC Multiplets (including updated schedule)
Status on Energy Buncher Magnets
Status on other components (examples)
  Radiation Resistant Magnets
  Focal-plane Chambers, Beam Diagnostics and Instrumentation
Status on Civil Construction
Summary
Notes: In-Flight  energies as high as 1500 MeV/u

## Slide 3: SC Dipole Magnets
Overall Status:
Collaboration agreement with CEA/Saclay signed (11/2013):
Technical Kick-off 1/2014
IMP Visit 04/2014 (CEA & GSI)
PDR July 3, 2014 (includes external advisor)
FDR Dec. 11, 2014 (excluding branching dipoles)
Tender by FAIR starts 01/2015
(option on special dipoles)
Pre-Serie unit ready for testing: Q4/2016
Series testing: Q4/2017 – Q4/2019 ( Q3-Q4/2020)
3 dipole units 11°
21 dipole units 9.75°
  3 times modified cryostat
Iron dominated
Warm iron
SC coil, (LHe ≈ 30 l)
Aperture ±190mm x ±70mm
Weight: 50 to 60 ton
Prototype built and tested (FAIR China Group)
Branching Point
cryostat & yoke
modification
small yoke
modification

## Slide 4: Collaboration with CEA/Saclay Status on SC Dipoles
Procurement Strategy:
  several coordination meetings FAIR, GSI, CEA; next will be Dec. 12, 2015
  tender for 1 lot (i.e. complete magnet)
  branching units as option
  9 ‘pre-bidder information meetings’ be done
  qualifying phase starts Jan. 2015
  Wire is under procurement separately (qualifying phase finished)
Time schedule updated
Focus so far on the short dipole version
Project includes
Magnetic design
Cryogenic Design
Quench Analysis
Mechanical Design (including
cool down, magnetic forces)
Protection & Quench Detection
Instrumentation
Interfaces (cryogenics, PC, DMU, ...)

## Slide 5: Collaboration with CEA/Saclay Status on SC Dipoles
Starting Point: IMP CAD model
Magnetic design adopted and finalized
Modification of cryo/mechanical design
  motion of the cryostat during ramp
  no any more support collision between successive magnets
  cryo-interface on both sides
  common cryo-interface multiplets/dipoles
  pressure request 20 bar
Instrumentation, QP/QA
IMP
PDR
towards FDR

## Slide 6: Overall Manufacturing and Testing Schedule for SC Dipole Units
next steps:
  finalize of the 11° units
  design of branching units (2015)
  interfaces (cryoline, mechanical), CERN review planed for 07/2015 (external support)
  floor loading (GSI)

## Slide 7: SC Multiplets
7 m
iron dominated, cold iron (≈40 tons)
common helium bath, LHe ≈ 1.300 l
warm beam pipe (38 cm inner diameter)
per magnet 1 pair of current leads
max. current <300A for all magnets
Overall Status:
Tender opened in Q3/2013
Tender was running regularly including 2nd round negotiation (Q2/2014)
Tender needed to be interrupted and re-initalized during 3rd round negotiation
  change of lot distribution required
  establishing and assessment of revised tender documents
  process supervision by a specialist solicitor
  processing along a revised and agreed time line
  new documents are sent out
  offers expected CW 3/15
  bidder interest still very high (they are calling frequently)
contract signing expected Q1/2015
FAT of first short multiplet Q2/2017
FAT of first long multiplet Q3/2017
Series testing: Q2/2018 – Q1/2021
25 long multiplets (mainly MS)
8 short multiplets (PS)
Quadrupol triplet / QS configuration
up to 3 sextupoles and 1 steerer
Octupole coils in short quadrupoles

## Slide 8: Overall Manufacturing and Testing Schedule for SC Multiplet

## Slide 9: Summary Schedule for SC Magnet Testing at CERN
probably, if bidder 2 will be awarded

## Slide 10: Magnets for Energy Buncher
Magnets are Indian in-kind
VECC colleagues finalizing magnetic design
3 dipole units with 30°deflection angle
    superferric, warm iron, SC coils
    challenging: required field quality
    new design: weight ≈67 ton + cryostat
    Multiplet: identical magnet parameters like used in the separator, but different configuration required
    Indian representative indicated interest to test these magnets at CERN during IKRB

## Slide 11: Radiation Resistant Magnets (at the Target Area of Super-FRS)
Normal conducting magnets using MIC cable
3 dipole units, 3 quadrupoles, 2 sextupoles
Prototype dipole built (95 ton) and tested by BINP
Handling tests at GSI in 08/2014
Remote alignment under revision
Remote connectors under revision
Specification in preparation,
Tendering via FAIR Q1-Q2/2015

## Slide 12: Focal Plane Installation / FMF2
3) Include it into DMU
Chamber design
1.860 mm
8 inserts
Instrumentation scheme
new NUSTAR sub-collaboration requires more flexible focal-plane arrangement
moving and precise re-alignment under investigation

## Slide 13: Beam Diagnostics
    Full isotope identification (x, y, x', y', DE and TOF)
    Operation modes: fast- and slow-extracted beams
    Various detector systems
      GEM-TPC (Finnish in-kind)
      SEM-GRID & ladder system (Finnish in-kind)
      Silicon detectors (Russian in-kind)
      Diamond detectors (Russian in-kind)
      MUSIC detectors (EoI Finland)
    Various test beam-times during summer 2014 at FRS
GEM TPC
prototype
Diamond strip
detector

## Slide 14: Beam Instrumentation (slits, degrader, secondary targets, ...)
x/y Slit-systems
  Overall 18 slit pairs required
  Remote handling foreseen
  Specification established
  Collaboration contract with KVI-CART
  Kick-off done 01/2014
  PDR done 08/2014,
    Pre-design existing
    thermal simulation / cooling issues considered
  Pre-Series slit-system expected Q3/2015
Media pannel,
robot operated
x-slit system:
block size: 200mm x 200 mm
y-slit system:
Block size: 400mm x 90 mm
Material: Densimet

## Slide 15
FAIR Civil Construction
Super-FRS Area
E. Mahner, 2nd Joint Meeting of the
FAIR & GSI Scientic Council, Oct. 23, 2014
Super-FRS and NUSTAR Experiments
Q2/2018:
Super-FRS Buildings & Tunnel
expected ‚ready for installation‘
Q2/2021:
Super-FRS expected
‚ready for beam‘

## Slide 16: Super-FRS Buildings (MSV)
Tunnel 103
(Separator tunnel, supply tunnel)
Build. 006a, Service building
3 floors (~2000 m2)
Technique (PS, controls, ... )
Experimental preparation
Control room, electronics
Gas supply, gas mixing station
Main tunnel access
Build. 006
(High-Energy cave)
On top: Build. 17.2
(FAIR service building)
100 m
Basic evaluation completed
Preliminary planning completed
Approval planning completed
Execution planning under approval
Running: route planning (crane cable, pipes, cryo)
Formwork planning & Tendering
Establishing cable data bank → tender of cables
FLF2
Experimental Area
FHF1
(End Focus HEB)
Build. 018, Target building
5 floors
Target area, shielding
Technique (PS, controls, ... )
Hot Cell complex
Focussing system
To CR

## Slide 17: Target Building (Build. 018)
DB 2
Shielding planning, including details
  input for radio-protection approval
Decission: FAIR will get one common cryo-plant
new connection to cryo-plant – DB 2
cryo connection DB2 – TFS
Media planning TFS and target maintenance area
Hot Cell planning
FAIR Cryo-Plant
Target Focussing System
SIS 18 / SIS100

## Slide 18: Super-FRS Tunnel Cross Section
Von Christina Will
Tunnel height: 6.5 to 7.0 m
(partly slewing cranes
@ focal plane stations)
Service Tunnel
W: 2.5 m, H: 4 (7) m
Access side:
~3 m
beam axis height
Cable feed through
Media side
Cryo-Lines
beam
Notes: 18

## Slide 19: Summary
FDR on dipole design next week, start of tender in Jan. 2015, pre-series unit expected for CERN testing in Q4/2016
Tender of SC Multiplets was interrupted; now running again, contract award expected for Q1/2015, (1st) pre-series unit expected for Q2/2017
Series test of dipole/multiplet units expected between Q4/2017 – Q1/2021
Development of various other items (EB magnets, NC magnets, beam diagnostics and instrumentation) in progress
Civil Construction
  FAIR combined schedule (buildings, accelerators, experiments) proposed
  Super-FRS buildings ‘ready for installation’ expected in Q2/2018
  in the moment concentrating on target building (shielding issues as well as media- and cryo-supply)