## Slide 1: BRAN installation
BRAN Point 8 test installation (Sune follows up):
  Point 8L after 17 November W47
  Point 8R: Thursday or Friday W44
BRAN Point 1 (Sune follows up):
  Point 1L: Re-installation: 18th November (W47) if the installation team is available.
  Point 1R piping and electrical connection: already done
BRAN Point 5 (Gerhard follows up):
  5L: W48 (~24 November)
  5R: W47 (~18 November)
  TESTS?
Courtesy: Gerhard Schneider, Sune Jakobsen

## Slide 2: LHCf – Takashi Sako
Recently we LHCf fixed our detector installation dates with a help of Julie Coupard. As we think it is better recognized by TREX,
I summarize our plan below. If you know any conflict especially with ATLAS ZDC or BRAN, please let us know.
week 47 (17 Nov.-) installation of LHCf Arm1 at the IP8 side (1L)
week 48 (24 Nov.-) installation of LHCf Arm2 at the IP2 side (1R)
1L – same week as BRAN

## Slide 3: 2014 Q4
LHCf 1L
BRAN 1L
BRAN 5R
BRAN 8L
LHCf 1R
BRAN 5L