## Slide 1: LHCf 2015
Questions from LMC:
  LHCf run scheduled shortly after initial commissioning – can it be delayed?
  Present plan below. LHCf to removed at first opportunity after run – i.e. TS1 in present planning
Following discussion with Hiroaki MENJO – 29th August 2014

## Slide 2: Requirements
Pilot run to qualify DAQ sometime before main run (pile-up not an issue)
11 m is OK – unsqueeze not needed for LHCf
1.5e29 cm-2s-1, mu = 0.01, Nb < 40, half crossing angle 140 microrad
Integrated luminosity: 10 nb-1
Delivery rate about 0.5 nb-1/hour – need 20 hours Stable Beams – say 2 days plus set-up

## Slide 3: Note
If LHCf is exposed to the high radiation levels in the TAN associated with high luminosity – it will be damaged – 2 weeks maximum at high luminosity
Installation time:
  1 working week
  1 to 2 days physical installation plus cabling and electronics tests
Removal time:
  1 to 2 days for both sides

## Slide 4: Delay run?
If the run is not performed initially, the detector will have to be installed and tested during a later technical stop
The run will have to take place reasonably soon after the technical stop to avoid damage
1 – 2 days within 2 weeks of the run will be required to removed the detectors
Both installation and removal will have to take place in an irradiated area – this will not be the case if the run takes place during the initial period
ALARA strongly favours doing the run as scheduled.