## Slide 1: Update on LHC commissioning
5 February 2015
E. Bravin

## Slide 2: Powering tests
Latest news and statistics at
  http://hcc.web.cern.ch/hcc/
2 Sectors trained up to 6.5 TeV (+100A)
Sector 5-6 being trained (already trained in 2008). Looks like memory of firm 3 magnets is very short 

## Slide 3: Activities
RF start cool down today
  No access until Monday, then to be agreed with CCC and RF
Dry runs on going since a while
  https://wikis/display/LHCOP/Dry+Runs+2014
Sector tests foreseen for last two WEs of February (?)
Cold checkout and beam commissioning preparation

## Slide 4: Dry runs
05 Feb 2015 Timing system: LHC mastership, dynamic destination, injection request.
06 Feb 2015 MKQA and AC dipole (new PLCs and FESA 3): trigger, OASIS, multiturn acquisition.
  Experiments (ALICE, LHCb and CMS):
  Beam modes, Handshakes - PM reception (if not done during DR 21.02.2015), SMP flags - Internal to LHC Clock switch, RF ramp - Injection permits - New DIP variables for automatic scan application
16 Feb 2015 Transfer Line equipment and instrumentation
  TED TT40/TT60 movement (in chain) - TED TI2/TI8 movement (in chain) - SPS MKE - Power Converters: heat run, logging and interlocks - Collimators - BLM, BPM, BTV, FBCT: application and logging - LHC-SPS synchronization
17 Feb 2015 Repeat DR2 (27 Jan 2015) with relevant sector test user inputs to BIC
  Triggered acquisition of the BI systems: BPMs (continuous (not yet possible) SYNC and FIFO) and BLMs (BLMs: continuous acquisition, XPOC, PM, IQC and 1 Hz) -Timing system (repeat Dry Run 1) -LBDS+MKI+Inject and Dump
  LBDS: Arming sequence (LBDS only user of BIC) - BETsim @450 GeV
  MKI: Settings - Load settings from sequencer and MKI application - Change state from sequencer and MKI application - Trim from MKI application - MCS settings - OASIS triggering and signals- Inject and dump sequence
18 Feb 2015 ADT (+ EMC measurements) + Experiments (at least ATLAS)
26 Feb 2015 WS and BRANS

## Slide 5: Dry runs and sector test plan

## Slide 6: Preparing for beam
Rossano is organizing the cold check-out
  Need input from our side: Access, special conditions etc.
  So far only info from Thibaut (yestarday)
Beam commissioning
  Need to make a plan for each instrument asap and then discuss the plan with OP
MDs
  Need to prepare MD requests by mid February

## Slide 7: LHC BI status
Web site created to track the situation
  https://be-bi-lhc-mon.cern.ch
  Need to be part of be-dep-bi-lhc-comm@cern.ch e-group to access
Regular meeting will be organized on Friday afternoon
  can we start tomorrow?