## Slide 1: LHCb Infrastructure meeting SciFi- installation
R. Walet on behalf of SciFi group
2015-02-19/20 Rev_01

## Slide 2
Introduction
The SciFi group is starting looking into the installation procedure
What I present in next slides is very preliminary
The goal is to provide timely input to the LHCb technical team rather than to give a definite installation scheme
DISCLAIMER
Remind you how the Outer Tracker installation went
Sketch the main lines of SciFi installation
PLAN OF THE TALK

## Slide 3
Prepared C-frames transported to CERN
@Nikhef, 4 FTEs + 1 student for 9 months
(2 C-Frames in parallel)
OT Installation steps
Produce and assemble C-Frames
Equip them with cables and pipes
Install patch panels for all cables and pipes
Installation modules on C-Frames
Testing
Move C-Frame + Modules to nominal position
In the cavern, 4 FTEs + 3 phys. + 4 st. for 1 year
(2 C-Frames in parallel)
In situ, 3 FTEs + 1 phys. for 1 year
Alignment & Survey
Installation cables and pipes in rolling ducts
Installation FE Boxes

## Slide 4
Pre-assembly C-Frames
~8 x 12 m in Nikhef assembly hall
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 5
C-Frames to CERN
prepared C-frames transported to CERN
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 6
Modules on C-Frames
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 7
C-Frame to Bridge
(1)
(2)
(3)
(4)
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 8
Alignment & Survey
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 9
Rolling Ducts & Cabling
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 10
FE Installation
Done in situ, because FE production was late
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 11
So what about SciFi Installation?
…but also many differences:
  time constraints tighter (Q3 2018 – Q3 2019)
  no space available to install a “C-cage” in the cavern
  pre-assemble C-Frames at CERN
In many respects similar to OT installation (shares same location, Bridget, Table, etc.)
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 12
Above ground
It could go like this
Preparation Work area
Underground
Assembly C-Frame Jigs
Installation C-Frames on Jigs
Installation cables & pipes on C-frames
Installation modules on C-Frames
Adding rolling duct and piping,cabling
Testing
Dismantling existing Detector
Preparation Work area
Transport complete C-frames with modules and cabling
Installation of the complete
C-Frames, including cable tray and cooling
Installation (Q3 2018 – Q3 2019)
Preparation
Installation transfer lines and all open connections
TESTING AND COMMISIONING

## Slide 13
Requests to Technical Team
Assembly hall(s) at ground level
  scaffolding and mobile work platforms
  Test Facilities for C-Frame system tests (cooling, power, control & DAQ)
Lab space (maintenance and repairs)
Help in design and construction of jigs
    e.g. safety issues
usage of cranes and transport
etc.
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 14
11[m]
4.2[m]
8[m]
6.3[m]
Storage
C-Frame, cabling and cooling assembly
Module installation on C-Frame
Test and commisioning
Storage
30[m]
5[m]
8[m]
6[m]
6[m]
5[m]
Assembly Hall

## Slide 15
Space Requirements
large assembly hall 11  30 m2 h=8m
  alternatives?
  high ceiling and doors
  cranes
Lab space (maintenance and repairs)
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 16
C-Frame System Test
Overview
212 Modules, this contains 46 ROBs
Needed interfaces
power (SiPM and FE bias)
water cooling
SiPM cooling
  already have? Buy new one?
    Nikhef would like to borrow it for next 2 years?!
control & mini-DAQ
environmental monitoring
compressed air and dry gas
usage of radioactive sources
nearby lab to repair broken parts
etc.
cooling
power
control
data
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 17
Dismantling OT
RE-USE; Bridge
RE-USE; Table
NEW;
C-Frames
Detector
Cable tray
Etc.
re-use parts?
  e.g. rollers
keep the rest for ~1 year…
  where?
…then dispose of it?
  how?
5 [m]
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 18
Move to Position
Lower fully assembled frame
move next to detector
insert
insertion beam/concept (re-use?)
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance

## Slide 19
Outlook
SciFi installation will in many respects be similar to OT
  re-use Bridge and Table
  insert fully assembled C-Frames connecting to Bridge rails from A side
main difference is that SciFi C-Frames will be fully assembled at the surface
  space requirements at the surface
  define procedure to lower fully-assembled C-Frames
we sketched first ideas, obviously preliminary
interact with technical team to define boundary conditions
  update SciFi infrastructure document
Notes: Scintillating Fibre Tracker, 2.5 m long fibres read out by silicon photomultipliers at the edge of the acceptance