## Slide 1: SPS update on LS1
David Mcfarlane
SPS Technical coordinator
FOM (08/10/2013)

## Slide 2: SPS LS1 schedule
General maintenance
Vacuum
Ions to NA61
General
Maintenance
General
Maintenance
General
Maintenance
General maintenance
General Maintenance
General Maintenance
General Maintenance
UA9 works
RF upgrade works
EPC works
EPC works
Civil Engineering
RF upgrade works
RF Upgrade works
RF Upgrade works
Survey
Horizontal
Vertical
smoothing
Cables
Cables
Irradiated Cables
Cables
Re-route Cabling
Cables
Cables
Cables
Cables
Cables
EL Studies
Remove
Install
Survey
Survey
Survey
Survey
Survey
Survey
Survey
Survey
Beam on
Cool down/RP survey and Magnet tests
Protons to the North Area
EPC Commissioning tests
Cold check out & Start-up
DSO tests/HV tests
Protons to LHC
Cool down
NO ACCESS
Cool down
Limited ACCESS
Magnets
Magnets
Magnets
Magnets
Magnets
Magnets
Magnets
Magnets
Beam off : 11/02/13
Beam on: 13/10/14
Open Access : 25/03/13
Close Access : 27/06/14
RAL
Fibres
Fibres
Fibres
Safety valves
CV works
CV studies
CV Controls upgrade
Vacuum
Vacuum
TT10 Consolidation
18 KV
18 KV
18 KV
18 KV
18 KV
Septa
replacement
Septa works
Septa tests
Kicker
Septa works
Kicker
TT20 pipework
Magnets
Magnets
18 KV
Civil Engineering
Civil Engineering
Civil Engineering
Civil Engineering
Ring-main
Ring-main
Ring-main
Ring-main
Ring-main
Ring-main
Ring-main
Cooling tower 863
Vacuum
Vacuum
Vacuum
Vacuum
Vacuum
Cables
RAL
Civil Engineering in TT10

## Slide 3: Where are we now?
Chart: Progress curve - machine SPS - 08/10/2013
| 50 | 52 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50
Forecast | 0 | 0 | 0 | 0 | 0 | 1.875 | 3.125 | 6.5 | 10.8125 | 13.8125 | 18.0625 | 23.875 | 25.625 | 27.6875 | 32.875 | 35.5625 | 37.625 | 41.25 | 43.9375 | 48.8125 | 49.9375 | 52.9375 | 53.5 | 55 | 58.6875 | 62.375 | 64.1875 | 66 | 67.1875 | 69.9375 | 70.5 | 72.3125 | 76.3125 | 76.875 | 79 | 80.1875 | 81.375 | 86.375 | 90.75 | 93.875 | 94.0625 | 94.25 | 94.4375 | 96.5 | 97.3125 | 97.5 | 99.375 | 100 | 100 | 100 | 100 | 100
Actual | 0 | 0 | 0 | 0 | 0 | 1.875 | 3.125 | 6.5 | 10.1875 | 12.25 | 15.875 | 20.75 | 22.1875 | 26.75 | 32.875 | 34.9375 | 36.375 | 40.9375 | 43 | 48.1875 | 49.3125 | 52.625

## Slide 4: Main works to watch
TT10 Civil Engineering works
Replacement of “coated” magnets in BA5
Irradiated cable campaign in BA1

## Slide 5: TT10 Civil Engineering works
The beam line and all associated equipment was removed from the areas where the structural integrity of the TT10 needs to be repaired.
Work from Civil engineering will continue in this area until the end of 2013.
The beam line and all associated equipment will be re-installed in January 2013.

## Slide 6: Replacement of “coated” magnets in BA5
16 main dipoles and 4 main quadrupoles were removed from sextant 5- at the beginning of LS1
These magnets will be put back into the machine in February 2014

## Slide 7: Irradiated cable campaign in BA1
All of the beam line and associated equipment has been removed from LSS1 and is being stored in ECX5.
  This was done to reduce the radiation levels in this area and improve access for EL.
The cable campaign has started today and will continue until the 26th March 2014.
All of the beam line and associated equipment will then be put back in place and re-comissioned in time for the closure of the SPS on Friday the 27th June 2014.

## Slide 8: Start-up of the SPS

## Slide 9: Closing comments
LS1 in the SPS is progressing according to the schedule.
All main works will be completed by end of May 2014 (except BA1)
We are on-target to close the SPS on Friday the 27th June 2014 and be able to give beam to the North area on the 13th October 2014. (as per the schedule)