## Slide 1: Injectors start-up
EN-MEF-OSS
Nov. 5th, 2013

## Slide 2: Baseline
Baseline assumptions
  If EIS not available, there will be shunt for access commissioning
To be confirmed - Services availability: EL, EPC, CO

## Slide 3: Change requests
PS magnet tests
  1 week due to pre-LS1 tests- tests not done
  All durations x2 !! 2 weeks  5.5 weeks !!
  POPs connection and tests + MPS tests = 2 weeks !!
PSB
  Additional activities to be scheduled: cranes, civil engineering for LIU…

## Slide 4: What can be done
To be confirmed,
  After discussions with Serge Deleval, he is confident that end of cooling maintenance for the PS magnets can be put backward to April 1st, but this is still to be confirmed

## Slide 5: Schedule..so far

## Slide 6: Access system commissioning
Access commissioning vs cooling availability (in 14’)
Area | Access com. | Cooling avail.
L2 | 11/02 - 12/02 | 28/02
Booster | 13/02 – 14/02 | 21/03
LEIR | 17/02 | 28/02
PS | 18/02 – 21/02 | 21/04
TT2 - TFP | 24/02 – 25/02 | 24/02
TFT | 26/02 – 27/02 | Running
EA | 28/02 | 05/05
AD target | 03/03 – 04/03 | 02/06
AD ring | 05/03 | 13/01
Isolde | 06-03 – 07/03 | ?










## Slide 7: Access commissioning
As proposed by Rende, and thanks to CV
  1st test with shunted signals from wk7-wk13
    Areas tests wk7-wk10
    Global test wk 11
    NC solving wk12-wk13
  Wk14 – Global test with DSO tests wk 14

## Slide 8: To be confirmed / detailed
End of maintenance of the cooling for PS magnets
Availability of all services per area
PSB
  Access possible until wk 13 (except Wk 11)
    Additional activities
  Impact of Global access & DSO tests on hardware tests (co-activity possible ?)
  Reduce Hardware tests by 1 week in order to give more time to cold check-out

## Slide 9: Conclusions
Meetings will be organized by MEF, in partnership with OP
Detail plan will be available end December/ beginning January