## Slide 1: MEDICIS : status, plans, interlocks and coactivity with ISOLDE ISOLDE ISCC 13 February 2015
Stefano Marzari EN-STI-RBS

## Slide 2: Outline:
Introduction
Time line
    Up to now
    Next steps
Conclusions

## Slide 3
ISOLDE experimental hall
ISOLDE Target area
ISOLDE Class A laboratory
CERN-MEDICIS project
ISOLDE Area
Swiss – French border

## Slide 4
Isotopes for ISOLDE
Beam dump
CERN-MEDICIS principle:
Use protons (~90%) normally lost into the Beam Dump
ISOLDE Target station
Protons 1.4 GeV
Radio Isotopes production
MEDICIS Target station
ZOOM

## Slide 5
D=20 / L=200
D=50 / L=100
Simulations from R.Augusto EDMS 1289889

## Slide 6
MEDICIS general layout
Existing ISOLDE buildings
Extension for MEDICIS
ISOLDE and MEDICIS irradiation points
Laboratory
Monorail transport
Robot
Hot cell
Mass separator
Chemical lab
Quality control and shipping
Radioactive target storage
New nuclear ventilation
Additional shielding
Fire doors (new fire sector)

## Slide 7: What we already did in this time…
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
2. Time line (up to now):
Building
Shielding
Irradiation point
Ventilation
Integration

## Slide 8: Ground breaking ceremony 4.9.2013
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 9: Earth works: earth samples analysis, move electrical services & 4000 m3 earth removal
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Drilling machine for soil analysis by RP

## Slide 10: Building: concrete foundations & walls
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 11: Building: Magnetite concrete walls for shielding
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Magnetite ore
Preparation
Magnetite concrete high density 3.9 kg/dm3 (normal concrete 2.2 kg/dm3)

## Slide 12: Building: Concrete roof , technical room for CV (ventilation) & laser for MEDICIS
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
CV & laser

## Slide 13: Building: Earth recover ~3000 m3
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 14: Internal: irradiation point and RCS (rail conveyor system)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Proton Beam
60 kV
Cover earthed
Tests with protons:
Done successfully !
Design by M. Vagnoni
Test

## Slide 15: Internal: shielding (temporary and permanent)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
22m3 blocks (magnetite, iron, concrete and barite).
Shielding Fluka optimization by Ricardo Augusto
42m3 of Magnetite ore temporary (by blowing)
<0.5 uSv/h during 2014/15 Isolde operation

## Slide 16: Building: external finishing and doors (fire, ventilation & sound insulation for CV technical room)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Many thanks to:
GS-SE-DOP

## Slide 17: Next steps in this time period
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
2. Time line (next steps) :
Ventilation
Handling (Robot & monorail)
Integration
Shielded doors
Off-line separator

## Slide 18: Ventilation, airlock SAS, access & connection
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Airlock SAS creation
Ventilation design & optimization EN-CV by A.Polato and A.Broche.
Coring & connection
Piping…

## Slide 19: Robot, shielded doors and storage shelves (for 112 Targets)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Rail mounting
Robot Rail mounted (J-L. Grenard)
Storage shelves (V. Barozier & Y. Garvrikov)
Shielded doors:
Delivery starts in March (K. Kershaw)

## Slide 20: Frontend, separator, collection box and services (HT, control, vacuum)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Power supply & HV
Vacuum &
Gas storage
Controls
FE & separator

## Slide 21: Rail Conveyor System and shielding completion & 2nd air lock SAS
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Radiation Hard
Design by M. Vagnoni
Recovery shuttle & camera inspection
HRS line and MEDICIS
GPS line
STATION
Conveyor
Wagon

## Slide 22: Laboratory equipment
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Glove boxes
Fume hoods

## Slide 23: Final commissioning & start up…
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Tests:
Handling (robot & conveyor)
Off line device (Frontend, separator, collection)
Access system
Safety monitoring (environment, radioprotection)
General safety (power cut, fire, ventilation…)
Start up in 2016 !

## Slide 24
Civil engineering schedule in LS1 was extremely tight
=> but we achieved it on time !
This shut down is also challenging with the new ventilation system and building integration
The 2015 schedule is also extremely tight !
Luckily for this project we benefit from previous experience:
  Industrial Kuka robots and failure risk analysis (like ISOLDE)
  Storage shelves and movable shielding (like ISOLDE)
  Front End and separator design (like ISOLDE)
    ISOLDE operation and maintenance (50 years of operation)
3. Conclusion :

## Slide 25
What are the ISOLDE benefits from MEDICIS ?
Upgrade of the nuclear ventilation system (safety)
Upgrade of the access system (safety)
Use of the RCS like a “RABIT” (for irradiation samples)
Use of the RCS for camera inspection (during handling and recovery operations)
Use of the RCS for ISOLDE targets handling (in and out)
New hot target storage 112 targets (80% for ISOLDE, more flexibility for reusing old targets)
Connection between new storage and new ISOLDE hot cell for target dismantling (remote handling without human intervention)
Use of the buffer area 37 m2 (80% for ISOLDE)

## Slide 26
Acknowledgements !
Roland Arnoul, Ricardo Augusto, Roger Barlow, Vincent Barozier, Michele Battistin, Ana-Paula Bernardes, Michel Bonnet, Francesco Canepa, Richard Catherall, Michal Czech, Mathieu Deschamps, Alexandre Dorsival, Jean-Louis Grenard, Keith Kershaw, Ielyzaveta Kobzeva, Camille Lemesre, Roberto Losito, Christophe Loup, Christophe Mitifiot, Rene Necca, Julien Parra-Lopez, Eliseo Perez-Duenas, Andrea Polato, Giacomo Potuto, Silvain Samson, Eva Sanchez, Christelle Saury, Alexander Stadler, Thierry Stora, Matteo Vagnoni, Francesco Venturini, Joachim Vollaire, Thijs Wijnands
THANKS for your Attention !

## Slide 30
Last integration view

## Slide 31
Ventilation network