## Slide 1: Safety in LS1
Thomas Otto, TE DSO

## Slide 2: Contents
Safety Performance in LS1
Technical Preparation
Safety Training
Coordination and Follow-Up
Management and Communication
Clean-up and Waste
Summary

## Slide 3: Safety Performance: Accidents
Approximately 3.4 million hours of LS1 work
64 minor accidents (no absence)
31 accidents with 273 days of absence

## Slide 4: LS1 Accidents
Facility | Total | Minor | With absence | Total days
PS | 2 | 1 | 1 | 6
SPS | 7 | 6 | 1 | 3
LHC | 30 | 20 | 10 | 93
Surface | 50 | 34 | 16 | 151
Exp. Areas* | 6 | 3 | 3 | 20
Total | 95 | 64 | 31 | 273
 | ENTC | STAFF | COAS/ USAS | FELL/ TRNE | Total
Minor | 49 | 10 | 4 | 1 | 64
With absence | 24 | 5 | 1 | 1 | 31
Total | 73 | 15 | 5 | 2 | 95
* (Only A&T personnel)
Near misses included:
Electrical lock-out
Unauthorised crossing of safety barriers

## Slide 5: Safety Performance: Personal Dose
DIS:
13345 assignments
From D. Forkel-Wirth, HSE
Chart: Collective personal dose (person-mSv)
| STAFF | MPA | CONTRACTORS
Passive dose distribution : 1st of March 2013 - 31st of July 2014 | 340.6 | 581.3 | 363.8
Chart: Individual dose distribution 1.3.2013 – 31.10.2014
| 0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9 | 1 | 1.1000000000000001 | 1.2 | 1.3 | 1.4 | 1.5 | 1.6 | 1.7 | 1.8 | 1.9 | 2 | 2.1 | 2.2000000000000002 | 2.2999999999999998 | 2.4 | 2.5 | 2.6 | 2.7 | 2.8 | 2.9 | 3.2 | 3.6 | 4 | 4.5999999999999996
valeurs | 6821 | 977 | 557 | 288 | 229 | 150 | 125 | 113 | 86 | 73 | 71 | 46 | 39 | 33 | 36 | 24 | 19 | 20 | 11 | 15 | 10 | 12 | 4 | 9 | 5 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
58 %
42 %

## Slide 6: Technical Preparation
Procedures incl. Safety measures
EC / EU-conformity of mechanical equipment
Pre-LS1 Training on the job
ALARA approach for radiation protection

## Slide 7: Technical procedures
Several 1000 pages of procedures for SMACC
Pictorial guide
Safety requirements for every process step

## Slide 8: Chemical Safety Highlights during LS1
Exposure monitoring
Chemical exposure monitoring campaigns were organized with external laboratories, to determine the degree of exposure to various Hazardous Chemical Agents
fibreglass in building 927;
welding fume in building 100 and the LHC Tunnel;
organic vapours in building 101
From J. Gulley, HSE

## Slide 9: Job-related training
Thorough training of all workers on mock-ups in Bld. 180

## Slide 10: LS1 – ALARA Committees
before optimization
after optimization
Total estimated collective dose for ALARA 3 interventions in LS1:
before optimization : 840 mSv - after optimization : 423mSv
Effectively taken: 240 mSv
Chart: 
 | 65.8 | 4.2 | 48.523 | 5.2 | 33 | 141.8 | 31.8 | 170 | 88.5 | 16 | 236
 | 10.02 | 4.2 | 27.6 | 2.8 | 21 | 76.6 | 24.3 | 85 | 53.4 | 6.4 | 111.8
Collective dose [mSv]
ISOLDE
Cabling LHC IR 3-7
PS CV
PS Beam Dump
SPS –LSS1 phase 1
PS Magnets
TCC2/TDC2 works
SPS –LSS1 phase 3
ISOLDE
TCC2/TDC2 Cabling
11 jobs for approval
From T. Wijnands & A. Pardons, EN
SPS –LSS1 phase 2

## Slide 11: Lessons for Technical Preparation
Most accidents suffered during activities on the surface
Technical + Safety documentation and on-the-job training instrumental for accident prevention
Extend the model to LS2 subprojects
ALARA process will be key to radiation protection performance in LS2 (Injectors !)

## Slide 12: Safety Training
  LS1 sensibilisation on SIR
  Classroom training
  2-level RP training
  Training infrastructure

## Slide 13: LS1 Safety Training Matrix
Work Area | Safety Introduction / Safety during LS1 | Accelerator Safety 4 | Electrical Safety Awareness | Self-Rescue Mask | Radiation Protection
LHC | X |  | X | X | X
SPS | X |  | X | X | X
PS and other injectors | X | X | X |  | X
Experimental areas | X | Where existing |  |  | X
Workshops | X |  |  |  | 
Work with radioactive objects | X |  |  |  | X
As a professional electrician, an “electrical habilitation” from the group leader is required

## Slide 14: Classroom Safety Training
8750 “very urgent” training requests
Training not targeted to CERN
Language barrier
2009
2010
2011
2012
2013
2014
2015
2016
Run 1
Repair
LS 1 Long Shutdown
1000
6000
5000
4000
3000
2000
persons
trained
From C. Balle, HSE

## Slide 15: RP Training
From D. Forkel-Wirth, HSE
SOFRANEXT | 1401 (FR)
CERN | 241 FR + 582 EN
2224 persons
(1884 during LS1)
(2nd October 2014)
Radiation Protection Training for Controlled Rad. Area (Face2Face):
5978 persons
(5th January 2015)
Radiation Protection Training for Supervised Radiation Areas (e-learning)

## Slide 16: Safety Training: Lessons
CERN is a World-Laboratory
Safety Training shall be targeted to CERN
  Content
  Language
HSE freezes requirements and course types
Departments evaluate training needs
  Number of arrivals during LS
  Technical Documentation → Risk Assessment → Safety training requirement

## Slide 17: Safety Training Infrastructure
To deliver, Safety training needs
  Trainers and technical personnel
  Infrastructure (Safety Training Centre)
  The present solutions must be consolidated until the “rush” during LS2
From C. Balle, HSE

## Slide 18: Safe solutions for unforeseen issues
Safety Bulletin October 2013
  HSE Formalisation of the “bump-cap” policy of A&T DSOs at workplaces without the hazard of falling objects.
Others:
  Self-Rescue Mask and Helmet not on the persons, but in reach
  Recognition of electrical safety training under different legislations from France (e.g. Poland)
  Ventilation speed for geometers
  Work-around to failing LHC lifts (means of evacuation)
  Co-activities during equipment check-out

## Slide 19: Safety Rules and Regulations
Last-minute Safety measures, after budgets have been allocated
  e.g. Special vacuum cleaners
  Electrical “habilitation” instead of electrical safety awareness
Recommendation:
  Freeze all Safety measures well before LS
  Allows consideration in budget allocation
  and inclusion in contractual documents

## Slide 20: Coordination and Follow-Up
Team of coordinators
  Sufficient number
  Sufficient authority
Cooperation of Safety Officers in A&T sector, GS and PH
Technical tools
  IMPACT for activity planning
  Automatisation of operational dosimetry
  TREC for equipment from accelerator areas

## Slide 21: Operational Dosimetry and IMPACT
Radiation dose reports in IMPACT
Extensive use of IMPACT in 2014
Chart: 
| 2012 | 2013 | 2014
All activities | 7519 | 11343 | 13095
RP approval | 151 | 1710 | 2615
8686 reports generated in 2014
+
+ IMPACT
From D. Forkel-Wirth, HSE

## Slide 22: TREC & Transport of radioactive goods
Departure | Radioactive Transports
Meyrin | 1248 (part on-site)
Prévessin | 683 (part on site)
SPS and LHC | 875 (public roads)
TOTAL | 2806
TREC | 
RP checks of components | 39395
components measured | 3373 t
radioactive components | 2618 t
of which radioactive waste | 722 t

## Slide 23: Coordination and Follow-Up: Lessons
Preserve force and authority of coordinators
Too many last minute activities:
  Improve planning in the last months before start-up
IMPACT tool integrates most Safety aspects related to the activity
  IMPACT does not replace Supervisor responsibility
  IMPACT not suitable to grant conditional access
Electrical Lock-Outs: reproduce good LHC example in injectors

## Slide 24: Management and Communication
“Safety First” was one motto for the LS1
Safety officer representation in all LS1-related management- and coordination meetings
  Close collaboration with coordination
Regular contributions on Safety matters in LSC and Subproject-Committees
Safety coordinators and officers present on-site

## Slide 25: Clean-Up and Waste
Better discipline during pre-sorting
Temporary waste storage
Waste elimination to host state repositories
Conventional waste is also an issue !
Incinerable waste,
Before sorting
After sorting and measurement,
ready for clearance
Chart: 
| 2010 | 2011 | 2012 | 2013 | 2014
masse (T) | 193.118 | 126.211 | 357.991 | 427 | 294.9
Volume (m3) | 445.03 | 398.71 | 521.303 | 1030 | 792
From D. Forkel-Wirth, HSE

## Slide 26: Safety Summary
what | I - keep | II - improve | III – change
List the different aspects in the management of the work carried out during the LS1 | Define what should be kept and was an added value during the LS1 | Define what you propose to improve in order to better manage the LS2 | Define what was a bottleneck to carry out the work during the LS1 and needs to be changed for LS2
Safety Training | LS specific safety training Training targeted to risk profile of person | Freeze access and training req’s early Assess training needs | Electrical training for electricians Safety training centre
Safety Rules |  | Freeze well before LS | 
Procedures & Accident prevention |  | Extend to all subprojects | 
Inspections |  | Announce and plan early | 
ALARA approach | Worked well |  | Take preparatory work into account
(radioactive) waste & material |  | Better discipline | Storage space (in progress)
Radioactive work areas |  |  | Need to be identified and (temporarily) classified (in progress)
Coordination | Keep at similar level |  | 
Last minute jobs |  | Only with serious justification |