## Slide 1: TE-EPC Activities during LS1
V. Montabonnet [TE-EPC]

## Slide 2: Scope
LS1 & TE-EPC Activities
TE-EPC Organisation
TE-EPC Feedbacks

## Slide 3: LS1 TE-EPC Activities
LS1 = 94x group activities as defined in PLAN
LS1 was mainly LHC and SPS in term of activity volume.
LS2 will have more activities and more scattered around the different machines

## Slide 4: LS1 & SPS Consolidation
Transformers
Earth switches
Thyristor stacks
18kV cables
SPS

## Slide 5: LS1 & Static Var Compensators
New 400V double-source Cooling plant consolidation New Coils
New earthing switches New Capacitors Maintenance of resistors

## Slide 6: LS1 & LHC
Some Figures
  61 converters relocated [R2E Project]
  2600 DC cable disconnection for ELQA tests
  1892 Lock-outs

## Slide 7: LS1 & LHC
14500 Output Module diodes replaced
4725 crimped hoses replaced (4.3km)
2500 fans installed
750 PSU upgraded (60A)
460 PSU upgraded for R2E (600A)

## Slide 8: LHC & CSCM Tests
Heavy modifications of the RB converters for the tests
  6 months of preparation and tests
  1 Engineer [Part Time], 1 Technician and 2 electromechanical technicians at full time

## Slide 9: TE-EPC Organisation
What worked well
  Preparation
    Work breakdown structure
    Work package analysis (scope, person responsible, resource requirements, procedures, time and cost estimation, status/reporting, dead line)
    Workload & planning for internal support resources

## Slide 10: TE-EPC Organisation
What worked well
    Organisation
      New FSUs resource allocation (x2 for BE-09 and TE-05)
      Setting of internal group priorities
      Mobilisation of TE-EPC different teams with a dynamic allocation (FSUs, staff …)
      Accountability & engagement of the teams
Lessons learned
    Keep points
      Anticipation & Preparation
    Limitation
      Manpower during installation/maintenance & tests phases
V. Montabonnet TE-EPC

## Slide 11: TE-EPC & LS1 Coordination
What worked well
  Work package Analysis - Useful for co-activity, constraints and service support identification
  Flexibility given by the Coordination Team - Useful to manage priority all around CERN complex and access constraints
  Trust and very good communication with the Coordination Team
V. Montabonnet TE-EPC

## Slide 12: TE-EPC & LS1 Coordination
What could be improved
  Don’t forget to plan
    Infrastructure Maintenance for TE-EPC Test Beds
    Maintenance of SVC’s related to the ‘Réseau Stable’
    Cleaning Activities at the end of LS1
    Access constraints to be reported in the Access Conditions Web Page and/or ADAMS’s database (Access to Accelerators)

## Slide 13: Electrical Safety
What worked well
  Centralisation of the Demande de Travaux on LHC circuit DC side
  Identification of the different types of hazards and risk assessment (procedure, VIC …)
  Central planification
  Role appointment clearly identified for LHC circuit consignation
V. Montabonnet TE-EPC

## Slide 14: Electrical Safety
What could be improved
  LHC Electrical Safety Organisation not well known by everybody at the beginning of LS1.
    Could be part of a SIR training module
  In Injector complex, role appointment for Circuit Consignation not clearly identified
    Need a same organisation as for the LHC ?
V. Montabonnet TE-EPC

## Slide 15: Tests & Organisation
What could be improved
  Some tests requesting power converters arrived very late (LHC Energy Extraction System Test, Access & EIS validation …)
    Need a clear list of tests
    Need for each test:
      Testpackage Analysis to identify safety issue, the contribution of the different groups/services, the time needed
      Procedures in advance
      Assignment of Coordination Work
V. Montabonnet TE-EPC

## Slide 16: Test & Quality Assurance
What could be improved
  For LHC Normal Conducting Magnet Circuit & Injector Circuit, develop Automatic Test Sequences as for the LHC Cold Circuits for Quality Assurance
V. Montabonnet TE-EPC
    Same tests every year
    Better traceability of the tests and their results
    Better detection of performance deviation

## Slide 17: Tests & Planification
What worked well
  Test Levelling (machine by machine) - very useful for manpower issue
  Time for tests. Their duration cannot be shrunk.
V. Montabonnet TE-EPC

## Slide 18: Conclusions
LS1 was successful with 100% of the baseline completed
Good and effective organisation
Positive feedback and very good collaboration with coordination team & services
Safety and tests issues could be improved
V. Montabonnet TE-EPC