## Slide 1: Q6 IR1&5 Modification for an operation at 1.9K
H. Prin, B. Feral, C. Bertone, V. Parma, M. Bajko, S. Claudet, C. Garion, V. Baglin

## Slide 2: TE-MSC activities
 | 1.9K |  | 4.5K | 
 | Duration | FTE | Duration | FTE
Mechanical study with the design office | 4 to 5 Months | 2 |  | 
Transport | See slide 4 |  | ~0.5 days | 4
Storage of the 4 Q6 cryoassemblies(larger supervised or controlled area) | SMI2 - SMS18 -? |  | Tunnel | 
Disassembly of the end cap extremities, thermal shield, jumper, service module… | 2 weeks | 2 |  | 
Disconnection of the pick-ups and DCF capillaries |  |  |  | 
Openings on the cold mass end covers | 2 days | 1 |  | 
Insertion of the heat exchanger tube and welding to the cold mass + pressure test | 1 week | 2 |  | 
Assembly of the phase separator and revision of the cooling circuits for an operation @ 1.9K | 3 weeks | 2 |  | 
Assembly of the service module |  |  |  | 
Reconnection of the pick-ups and DCF capillaries | 1.5 week | 2 |  | 
Jumper welding in the opposite direction |  |  |  | 
Preparation for cold tests | 2 weeks | 1 |  | 
Pressure and leak test |  |  |  | 
Cold test @ 1.9K in SM18 | 5 weeks | 1 |  | 
Stripping before installation and extremities reassembly | 1.5 week | 1 |  | 
Transport | See slide 4 |  | ~0.5 days | 4
General coordination and following of the work: Procurement follow-up, QA, inspection, documentation, tests,… | ~17 weeks | 1 |  | 
To be done
during LS3
~1.5 FTE
over 17 weeks per Q6
1 FTE
over 17 weeks

## Slide 3: TE-MSC activities cost
Personal
  Design office 80kCHF
  Disassembly/Assembly (for the 4 Q6) 200kCHF
  Coordination & QA 40kCHF
320kCHF
Material (for the 4 Q6)
  Heat exchanger and associated compensators, flanges, flares… 60kCHF
  QSS, phase separator, cryogenic circuit piping modification… 200kCHF
  Pressure, Leak, cold tests and NDT 200kCHF
  460kCHF
(CERN staff work and supervision not included)

## Slide 4: EN-HE activities
The magnet trip is dependant of the jumper height to enter in SMI2
  Low jumper assemblies are travelling through UJ22, TI2 and PMI2
  High jumper assemblies require to pass through the ALICE’s low beta platform and then by road
Trip and activities duration:
Magnet removal or installation 1.5h 4p
Transport through one sector 1.5h 3p
Passing over LHC machine in UJ22 0.5d 4p
Transport between UJ22 and SMI2 0.5d 4p
ALICE’s low beta platform disassembly 4w 4p (night work to be agreed with ALICE)
Lifting through PX24 1h 3p
Transport by truck on the road 1h 1p
In IP1, cryo-assemblies have high jumpers
In IP5, cryo-assemblies have low jumpers
Keet in mind: these activities have to performed for the Q4 that will be installed in Q5 slots

## Slide 5: Cryogenics evaluation
Main advantages for SAM@1.9K w.r.t 4.5K:
Excellent wetting of conductors, as all pressurised helium volume fills the cold mass volume (at 4.5K, we control a level, that has to be confirmed above the top of the coils with the so called boil-off tests)
Excellent autonomy for small perturbations or stops: depending on heat losses, the pressurised helium has about 10-15 hrs autonomy before being relief via the quench valves, whereas only 2-4 hours before being empty if at 4.5K
Main disadvantage for SAM@1.9K w.r.t 4.5K:
Required conversion and associated work (mainly MSC), but as well for cryo instrumentation and feedthroughs that will have to be with He-guard
The cost of refrigeration is higher (1/T), but on a very small amount of magnets, therefore not a sizing criteria for the refrigeration system.
The beam screen operating temperature range base line remains 5-20K (see nest slide) independently of the magnet operating temperature.

## Slide 6: Vacuum evaluation
Regardless of the magnet operating temperature, the functionalities associated to the beam screens are essential (heaters, k refrigeration lines…). All these are already implemented in the current Q6 and have demonstrated their efficiency at 4.5K.
The base line for the range of the beam screen operating temperature for the “standalone” magnets remains 5-20K independently from the magnet temperature. An operation range between 40-60K could be envisaged like in the inner triplet but there is not strong argument to change today.
The cryosorbers are mandatory for an operation at 4.5K, their presence does not seem to be a showstopper for an operation at 1.9K  today no activity has to be foreseen at the level of the beam screen.
The present distance form Q6 to the crab cavities (about 58m) prevents from possible contamination from cryosorbers dust. (To be assessed for the Q5 case)
In case of a carbon coating up to Q6, the compatibility with the cryosobers has to be demonstrated.

## Slide 7: Summary
To operate Q6 in IR1&5 at 1.9K, we have to adapt the existing cryo-assemblies (lack of spare magnets and major components). The job has to be performed during LS3 in parallel with the HL-LHC installation upgrade and other consolidation activities in the tunnel. The cost estimation for the four Q6 modification is about 800kCHF. It requires 2.5FTE from the MSC group over 68 weeks.
An operation at 4.5K requires a displacement of the present Q6 by few meters. In case of 1.9K cryo-assemblies have to be stored and modified on surface. The ones from IR1 might be installed in IR5 and vice versa (to inverse the service module side and respect the beam screen orientation associated to the focalisation plane and orbit corrector orientation).
Risks during handling and execution of the work are not excluded and have to be considered.
The passage through ALICE cavern has to be scheduled for the removal and reinstallation. This has to be done at least for the Q4 that will become Q5.
Operating the magnet at 1.9K offers more flexibility from the cryogenics point of view but there is no strong argument for such a change.
The base line for beam screen operation temperature range for the standalone magnets (D2-Q5-Q6) stays 5-20K. No modification needed for the cryogenic distribution nor for the Q5 and Q6 and this level.
The vacuum performance is not affected by the magnet operating temperature. The presence of the cryosorbers does not seem to be a showstopper for an operation at 1.9K. But in case of a carbon coating up to Q6, the compatibility has to be verified and in case of an operation at 4.5K, the activity in situ must be established.