## Slide 1: AD start-up 2014 A brief summary

## Slide 2: Contents
LS1 activities
Planning
Progress
Main issues
Outlook for 2015

## Slide 3: LS1 work (selected items)
Controls:
  ACCOR (almost) completed, including FESA, InCA and Java migration
  Central timing renewal, AD is now de-coupled from accelerator complex
  Cycle generation software adapted/re-newed
  New Beam Request Server
Magnets:
  DR.BHN06 renovated
  DR.DHV2904 & 2917 replaced by new type
  DE.Q7020 & 7030 replaced by new type (+ re-shuffling of line)
Vacuum system renovation (25% of consolidation pgm completed)
Stochastic cooling HW/SW/electronics/Servo motors renovation
RF C02 HV & tuning supplies and interlock system renewal
New Access Points and interlock system separation
Magnetic Horn stripline failure. Discovered late…

## Slide 4: Planning
Detailed planning by Technical Coordinator:
  Regular meetings during LS1
  Many modifications leading up to the start-up
Access System tests done in advance in collaboration with op
HW-tests and cold checkout planned by TC-team together with BE/OP
HWT/CC/beam start-up done by op:s team from the ACR together with eq. specialists.
HWT & CC activities flexible; faults/debugging duration not known in advance, planning not always followed
Setting-up with beam by op-team from ACR, 2-shift rota
No formal check-lists
Hand over “back-up” operation to ccc once machine is stable and beam quality satisfactory

## Slide 5: Progress (main steps..)
Start-up with beam initially planned 1/8 – 19/8, Physics start 19/8
Physics run actually started 16/9
  5/8: First beam on target after Horn strip-line repair completed.
  6/8: Circulating beam at 3.5 GeV/c w. good lifetime.
  8/8: C10 systems working, first signs of cooling.
  15/8: Beam cooled and decelerated to 2 GeV/c. after debugging of stochastic cooling and Schottky measurement system.
  20/8: Beam at 300 MeV/c
  24/8: Beam cooled at 300 MeV/c and decelerated to 100 MeV/c with decent efficiency.
  28/8: First signs of cooling at 100MeV/c
  4/9: Good cooling achieved at 100 MeV/c
  10/9: Beam ejected
  16/9: All ejection beam-lines set-up and beam delivered to experiments. Low ASACUSA and ALPHA efficiency due to Horizontal fluctuations.

## Slide 6: Main issues
Some additional delay due to the Magnetic Horn Strip-line repair. Started at low current while monitoring focusing effect with RP monitors.
Lengthy debugging (days) of new timing/cycle/BRS system:
  PS/AD cycle synchro
  Pause/un-pause AD cycle
  Cycle editing, plateau insertion
  Ejection timing not configured at start-up
Debugging timing + clocks for Schottky intensity measurement system
Lengthy set-up of BCT timing
C10 cavities start-up: HW problems and very low initial beam intensity
C02 renovation with new HV and tuning power supplies & new electronics and interlock system.
  Many (intermittent) bugs HW/SW
C02 LL:
  Frequency synthesiser replaced w/o our knowledge and with wrong setting
  experts not always available, days lost for ejection set-up.

## Slide 7: Main issues
Stochastic cooling renovation:
  p/u structure movement system motor drive/controls: much time spent to make it operational before abandoning and use expert-sw. FESA-class bugs resolved towards end of 2014 run.
  Debugging static and dynamic parameter control & other issues related to new HW installation (PFF)
  GSM noise re-appeared: new Cryo-temperature sensors removed on pickup tanks & discovered that gain for AD Hall system was back to max. (New GSM HW + contractor ?)
Orbits: Polarity mess-up with the 4 H correctors around the electron cooler ( a lot of time lost…):
  Various configurations tried…
  2904 and 2917; new magnets (calibration curves)
  Cables re-routed and patched (for B393) =>
    Erratic connections made @ power supplies
  Normally no big deal, but orbit pickup calibration factor corruption was discovered (2/9) after much struggling (HW problems with old orbit system, losses during ramps/plateaus, orbit bumps not local, orbit corrections sometimes converging and sometimes diverging, lengthy manual cross checks etc. etc.)
  Large orbit jumps on some occasions, traced to DHZ2908 which after installing a field probe became stable
  Orbit corrections are always necessary at low energies.
ABS orbit correction no longer available
  Lengthy YASP set-up: operational end August

## Slide 8: Main issues
Electron cooler set-up:
  Cooling effect very sensitive to trajectory imperfections
  New timing set-up (new beam loss scenarios discovered)
  New HW fault: frequent drop-outs depending on e-beam trajectory. Not yet solved.
Ejection lines:
  Several cabling errors due to B393 re-routing
  Crossed cables, labelling errors
  Negative corrector settings in some elements not possible => CO bug
  Large H fluctuations (detrimental to ASACUSA and ALPHA):
    DR.DHZ2908
    Neighbouring AEGIS solenoid ramping w/o info or agreement
    DR.SME5306S: recent power supply mod with different regulation and steeper ramps: Believed to cause additional fringing fields outside septum blade.
    Checks with various ramping rates seem to confirm this
    Work-around installed; synchronous timing to have identical effect on each cycle.
    => fluctuations reduced by a factor 2.5 (which is close to previous years values)

## Slide 9: On the good side…
Many systems did actually start-up w/o particular issues….
Target area fully operational very fast
Modified ejection line layout (preparation for ELENA) with new optics and some new magnets: set-up for all experiments was very smooth !
Beamline to the new BASE experiment commissioned w/o problems !

## Slide 10: Remaining (main) issues
Residual fluctuations in ejection line trajectories
Intensity still not optimal
Electron cooler drop-outs
Somewhat high V emittances at 2 GeV/c
RP alarms due to new rules and detector placement
  Lower alarm limits
  weak points in ring shielding
  losses when using BPM:s during s-u in experimental areas
  monitoring of typical workplaces inside user barracks

## Slide 11: General remarks / conclusion
Large number of upgrades/modifications => It was really a re-commissioning ! This took > 6 months back in 1999….
AD team works 2 shifts Mo – Fri, 1 shift (12h) shift Sat – Sun
Start-up during holiday period
A fair amount of PSB/PS down-time
Equipment specialists not always available for AD issues ( sometimes only 1 person has the expertise…)
Equipment specialists sometimes busy with higher priority work
Cumulative machine issues seem to have an exponential effect on start-up duration….

## Slide 12: Outlook for 2015
Late start-up due to re-location of kicker pulse generator equipment into B393.
First beam to AD planned for 1/6, but is now delayed to ~17/6 with physics start ~6/7
<3 weeks for setting-up leaves little time for studies.