## Overview of LS1 EPC Activities

- Figures and Pictures

- Mainly LHC and SPS Main Circuits

- What have been planned, what have been done

## Work Organisation

- Internal to EPC

  - Mobilisation  of different teams, dynamic allocation (FSU, staff …)

  - Workpackage (WBS) : Scope,  Responsibilities, Interfaces, Tasks, Manpower, Costs, Specific Needs (Storage …), Minimisation of risks, Status/ Reporting

  - Lessons

    - Keep points = Anticipation

    - Limitation = Manpower (installation & tests)

  - Good support of services

- External with EN-MEF mainly

  - Plan useful for central information BUT should be accessible not only by Group Leaders

  - Workpackage Analysis - Very Useful for co-activity, constraints identification

  - Flexibility given by EN-MEF - Useful to manage priority all around CERN Complex  and constraints

  - Trust and very good communication with the coordination team

  - Don’ forget to plan

    - Infrastructure Maintenance for EPC Test Beds

    - Maintenance of SVC related to ‘Reseau Stable’

  - Access Status Web Page should include the constraints

## Mains Issues

  - Safety - Concepts/Roles not known or not well defined

    - Chargé de Travaux, Chargé de Consignation ….

    - Seconde Etape de Consignation : MALT

    - Autorisation de Travaux

    - Training on SIR to be added for informing people?

  - Tests

    - List of tests to be performed requesting power converters not defined or arrived too late : Ex LHC Energy Extraction Test, EIS

    - Work package Analysis for Short-Circuit Tests & Warm Magnets missing – What tests should be performed and the services needed ? Who is coordinated the tests?

    - Problem of co-activity between Installation and Tests

    - Test coordination team needs people at full time and available during the preparation process before  the tests

    - Tests need time. Their duration cannot be shrunk.

    - Test Levelling (machine by machine) - very useful for manpower issue

    - LHC Tests and Tracking Tests tools to be deployed in injectors

## Conclusions

- 100% of the baseline was completed

- Good an effective organisation

- Positive feedback and very good collaboration with coordination team

- Safety and Tests issues to improve

- LS2 Mains concerns

  - More activities : LHC and LIU (Booster, PS …)

  - Storage for LIU project

  - Manpower