## Slide 1: Feedback on Warm Magnet Activities during LS1
J.Bauche, on behalf of the TE/MSC/MNC section
With contributions from:
P. Catherine, M. Dumas, P. Fessia, A. Newborough, P. Thonet, and D. Tommasini

## Slide 2: Outline
Magnet maintenance program in LS
Review of TE/MSC/MNC activities in LS1
  Foreseen
  Unforeseen
Feedback
  Support from/to other groups
  Coordination
  Electrical and radiation safety
  Infrastructure (incl. access)
Resources
Summary

## Slide 3: Main Conclusions
LS meets well magnet maintenance program; magnet inspection dedicated period at start of LS period shall be kept
Overall feedback:
  LS1 work well prepared, well in advance (commitment of resources already at this stage). Initiatives like IEFC workshop 03/2012 helped a lot.
  Excellent collaboration with other groups, good communication in technical coordination meetings
Additional workload from inspection results or from external requests
SMACC priority committed a lot of MNC resources. Support with external collaborations (BINP & NCBJ) helped to recover some
Margin to be considered in schedules in particular for restart phase (late activities / issues found during restart tests)
Prioritization of projects is of utmost importance for resource allocation
Radiation aspects well addressed (e.g. TDC2 / LSS1+); few electrical safety issues: reminder of basic safety rules
Safety rules and procedures demanding more and more resources

## Slide 4: Spare slides from IEFC workshop 03/2012

## Slide 5: Magnet baseline strategy for LS1
Memorandum addressed in October 2011:
TE/MSC/MNC activities in IEF during LS1 (EDMS 1169429)
We intend to complete:
  Full inspection of the magnets
  Corrective maintenance
  Preventive maintenance and necessary consolidations
  Necessary actions in highly radioactive areas
  LIU activities to be done during LS1
To reserve resources for LHC splice consolidation, we will put on hold:
  Less urgent consolidations (SMIT quadrupoles in L2, L3 and PSB; SPS pole shims, PS busbars and PFW’s, NEA interlock cabling, etc.)
  Many desirable but less urgent maintenance activities
Most of it could not be done during short shutdowns of the last 3 years

## Slide 6: Maintenance and consolidation in IEF
Detailed inspection of magnets
  Removal of the magnet covers
  Electrical tests
  Audio-visual inspection in pulsed mode
  Thermal inspections
Machine conditions
  Machine closed to non-MNC personnel during power tests
  Power, cooling, interlocks, access operational
Support from other groups
  BE/OP to power the magnets and lock the accesses
  TE/EPC support for power converters operation
To be done in the beginning of LS1
(except zones!)
In all machines
Loose electrical connection

## Slide 7: Maintenance and consolidation in IEF
Corrective / preventive maintenance
  Repair / replacement of faulty magnets
  Shimming in-situ or replacement of magnets with critical coil movement
  Refurbishment of defective magnets in workshops
  Cleaning of all magnet filters
Machine conditions
  Free access for handling and transport in the tunnel (coactivity)
Support from other groups
  EN/HE, TE/VSC, BE/ABP for magnet replacements
Activity spread over the whole LS1 duration, ending with the most radioactive zones
In all machines
Clogged filter
Clogged coil

## Slide 8: Maintenance and consolidation in IEF
  Revise most critical auxiliary magnet cooling circuits
  Missed preventive maintenance
  Replacement of internal flexible hoses
  Check hoses crimping system
  Activity spread over the whole LS1 duration
PS Booster
ONO/XNO/QSK-Type IA
OSK/XSK/DVT/DHZ (Type B)

## Slide 9: Maintenance and consolidation in IEF
  Removal of unused magnet in beam lines 7000 and 8000
  Required for the ELENA project
Machine conditions
  Opening the concrete roof of AD
Support from other groups
  EN/HE, TE/VSC
AD transfer lines
BHZ 8000 – 30 T
BTI 8002 – 7.5 T
Layout of transfer line 8000

## Slide 10: Maintenance and consolidation in IEF
  Refurbishment in-situ of separator magnets GPS and HRS
  Missed preventive maintenance
Support from other groups
  None if work in-situ
  EN/HE, TE/VSC, BE/ABP, if major refurbishment in workshop is needed
After radiation cool-down period
ISOLDE
GPS 70 deg. magnet
HRS 60 deg. magnet
HRS 90 deg. magnet

## Slide 11: Maintenance and consolidation in IEF
  Replacement of PFW sets on main units #55 and #75
  Corrective maintenance
  Crimped contact resistance increase monitored recently
Support from other groups
  EN/HE, TE/VSC, BE/ABP
After radiation cool-down period
PS ring
PS main unit
Typical increase of contact resistance
PFW internal assembly

## Slide 12: Maintenance and consolidation in IEF
  Refurbishment of most critical quadrupole cooling circuits
  Corroded brazed hydraulic connections on several magnets
  Degraded internal soft hoses to be replaced
Support from other groups
  EN/HE, TE/VSC, BE/ABP for replacement of some of the magnets
TT2 transfer line
Degraded hydraulic connection brazed joints
TT2 quadrupoles

## Slide 13: Maintenance and consolidation in IEF
  Refurbishment of defective magnets
  F61N.DVT01 out of service due to water leak, replacement requires to dismount part of the concrete block shielding around
  F61N.DHZ01 in degraded state, no spare
  Magnets to be refurbished in workshop
Support from other groups
  EN/HE, TE/VSC, BE/ABP
East Area
F61N.DVT01
F61N.DHZ01

## Slide 14: Maintenance and consolidation in IEF
  Replacement of the SMH.01 splitter by a “standard” dipole
  Control system of mechanical movement is “orphan” equipment
  Split functionality not needed anymore with modification of beam distribution mode (replacement of MNP23 septum by MCB)
Support from other groups
  EN/HE, TE/VSC, BE/ABP
Start after radiation cool-down period
East Area
MEP35 splitter
MCB dipole

## Slide 15: Maintenance and consolidation in IEF
  Special inspections and tests of main magnet circuits
  Inspection of the busbars  removing of all BB covers
  Completion of capacitive discharge tests campaign (3/3): 250 dipole coils
Machine conditions
  Sectors 1-2 and 2-3 not accessible during a few days (capacitive discharge)
Support from other groups
  TE/EPC to separate the SMD’s from the load in sector 6-1 and 1-2
After cool-down time for works in half-sextants 1+ and 2-
SPS
Inter-turn short-circuit on MBB 40330 during capacitive discharge campaign 2/3 in 2011
SPS cross-section at MBB

## Slide 16: Maintenance and consolidation in IEF
  Replacement of all cooling supply flexible hoses
  Consolidation approved, all 2000 hoses already purchased in 2010
  Equipment stored since then, could not be installed during previous short shutdowns
Support from other groups
  EN/CV to empty demineralized water circuits in all sextants
When all inspections requiring cooling water will be completed
SPS and transfer lines
Delaminated cooling hose
Burst cooling hose

## Slide 17: Maintenance and consolidation in IEF
  Expected exchange of 10 to 15 main magnets, following audio-visual inspection results
  Standard preventive and corrective maintenance (few spares)
Machine conditions
  Need access to material lift
Support from other groups
  EN/HE, TE/VSC, BE/ABP
SPS
Main dipole exchange in the SPS

## Slide 18: Maintenance and consolidation in IEF
  Refurbishment of the 10 most critical MBA magnets with corroded manifold brazed joints
  Brazed joints corrosion  sign of future water leaks
  Problem identified on 70 dipoles, mostly MBA
Machine conditions
  Possibility to do it in ECX5 to avoid logistics
  in surface? TBC
  Otherwise, need access to material lift
Support from other groups
  EN/HE, TE/VSC, BE/ABP
SPS
Corroded brazed joint

## Slide 19: Maintenance and consolidation in IEF
  Suppression of weak electrical contacts of water pressure and water temperature interlocks
  False triggering of interlock system  important part of piquet interventions
  Decision to be taken about technical solution
Support from other groups
  Possibly TE/MPE, depending on technical solution
After cool-down period
North Experimental Area – TCC2
kg/cm²
Interlock
circuit
Manometer with gold tip contacts corroding due to water pressure oscillations

## Slide 20: Maintenance and consolidation in IEF
  Improvements to magnet supply circuits
  Reduction of hoses interconnections in radiation exposed areas
  Replacement of obsolete electro-valves by manual valves
  Proper sleeving of power cables connections on the ground
After radiation cool-down period
North Experimental Area – TCC2
Quick connector gaskets degraded by irradiation
Improper electrical connections to be sealed with appropriate sleeves

## Slide 21: Maintenance and consolidation in IEF
  EN/EL - Removal of magnets in SPS – LSS1+
  To allow access to cable trays for irradiated cable replacement campaign
To be confirmed
Requests from other groups
Layout of dumping region
Requests to other groups
  DGS/RP – Support needed in all interventions described above
  TE/EPC – Consignation of power converters
  EN/CV – Maintain flow in demineralized water circuits

## Slide 22: LHC Injector Upgrade activities
  Upgrade of cooling circuits of the main bending and quadrupole magnets
  Necessary to allow 2 GeV operation of main magnets
  Cannot fit with other modifications in LS2 planning
  Removal of flow-switches and installation of additional temperature interlocks
  Upgrade of hydraulic connections
Activity spread over the whole LS1 duration, ending with the most radioactive zones
LIU-PSB
PSB main Quadrupole magnet
PSB main bending magnet

## Slide 23: LHC Injector Upgrade activities
  Installation of the PSB injections magnets
  To reduce congestion during the connection of LINAC 4
  BI.BVT10 – required for LINAC 4 (160 MeV) operation
  BI.QNO 50 & 60 – Consolidation action (profit of vacuum opening)
Support from other groups
  EN/HE, TE/VSC, BE/ABP
To be confirmed based on magnet availability and planning agreement
LIU-PSB
Design of new BI.BVT 10
Magnets BI.BVT10 (red) and BI.QNO 50 & 60 (green)

## Slide 24: LHC Injector Upgrade activities
  Coating of 16 dipoles and 4 quadrupoles in 2 adjacent cells of sextant 5
  Validation of both magnetron sputtering and hollow cathode coating of VC with a-C during 2014 MD’s
  Dipoles removed from machine to be coated in workshop (50% to be rebuilt)
  Installation of pre-coated VC in quadrupoles
Machine conditions
  Access needed to material lift
Support from other groups
  EN/HE, TE/VSC, BE/ABP
All magnet should be removed from SPS at the beginning of LS1, and put back in place at the end in a single batch
LIU-SPS (e-cloud mitigation)
Magnetron sputtering *
Hollow cathode coating *
* Pictures: courtesy of P.Costa Pinto – TE/VSC

## Slide 25: LHC Injector Upgrade activities
  Modification of the MDHD 11832 for injection dogleg compensation
  Modification of the coils powering scheme from series to parallel to increase strength
  Required to be done in workshop
Machine conditions
  Access needed to material lift
Support from other groups
  EN/HE, TE/VSC, BE/ABP
LIU-SPS (Q20)
Layout of half-cell 118
MDHD11832 (green)

## Slide 26: Resources
MNC staff and FSU resources
MNC resources distribution per activity in 2011
MNC resources distribution per activity during LS1

## Slide 27: Summary
Baseline strategy described in EDMS 1169429
  More than half of the staff and FSU personnel of MNC will be involved in the LHC splice consolidation
  We will perform all the necessary actions to ensure a reliable operation of the magnets in the CERN accelerator complex, including the ones only possible during a long shutdown
  We will perform all the necessary actions required by the LIU and the other approved projects
  We must postpone less urgent consolidation and maintenance
We acknowledge in advance our colleagues for:
  Their support to our activity
  Ensuring the availability of the technical services during the inspections
  To avoid interrupting the water flow in magnets for long periods