## Slide 1
List of BI Open Actions
Gian Piero Di Giovanni, R. Jones, M. Meddahi, B. Mikulec, G. Rumolo, J. Tan
LIU-PSB WG Meeting
16th April 2015

## Slide 2
Forewords
First BI review held the 29th January 2015, see https://indico.cern.ch/event/367898/
  Detailed presentation from J. Tan (WP holder for LIU-PSB 6: Beam Instrumentation).
  Some deadline was found incompatible with the expected baseline, in particular concerning the
  readiness for a possible Linac4 connection at the end of 2016.
  These mismatches raised a general concern and triggered a global review of the LIU-PSB project,
  see https://indico.cern.ch/event/376324/, to check the readiness for the Linac4 connection of all
  the involved equipment.
K. Hanke presented a summary of the LIU-PSB review at the LIU Project Team meetings.
As a consequence, the management launched a review of the most critical WPs, to better understand the
status of the different projects.
J. Tan presented the status of BI WP to the management on Tuesday, based on the latest developments:
  For instance Linac4 beam commissioning at 160 MeV expected to start mid-June 2016.
    Part 1 of HST in Q2 2016.
    Part 2 of HST in Q3 2016.
In this slides we summarize the open action as derived from the meeting.

## Slide 3
Open Actions (I)
H0/H- Current Monitors Electronics:
  The proposal needs to be distributed and reviewed with BE/OP (F. Roncarolo).
H0/H- Current Monitors:
  Check the need to order spares, 19 kCHF, to align with magnets spares (J. Tan/J. Borburgh).
H- charge-exchange, Beam Profile and Foil Inspection:
  Keep only the 2 spares foreseen (not 4, extra 33 kCHF)? To be checked that it is practical
  to remove old unit & re-install (J. Tan/S. Burger/W. Weterings).
BI.SMV position measurement plates:
  Positions now defined for outgoing beams - integration to be checked (B. Mikulec/B. Riffaud).
BI.BTV30:
  ECR required (J. Tan/S. Burger).
SEM for injection matching:
  SRR & ECR required (J. Tan).
  Decision taken to move installation to YETS 17-18, but with study of possibility for PPM
  device re-visited (F. Roncarolo).
  Decision on spare grids to be taken once cost of final design clear.

## Slide 4
Open Actions (II)
BCTs - BR.TMD in 8L1:
  ALARA to be followed-up (R. Froeschl).
PSB-TMS: (J. Tan/L. Soby/J. Belleman)
  BI needs to prioritize in 2015 on:
    Demonstrating 200 mm resolution for low intensity.
    Demonstrating reliable operation with new firmware/software.
    Electronics to be ready for deployment in EYETS 16-17.
Wideband BPM:
  Design based on PS. Built at CERN? Feasible for end 2016? (J. Tan/J. Belleman).
  DIC+SRR+ECR to be submitted (J. Tan/J. Belleman).
BLM:
  PS specs needed to enable regrouping of electronics order (LIU Management).
  ECR in 2015: include FLAT ionization chambers and ionization chambers to replace ACEMs (J. Tan/
  C. Zamantzas).
Wire Scanners:
  Need to find specifications (B. Mikulec/J. Tan).
  We may need re-sectorization of vacuum as section 11 is in the same vacuum sector as
  extraction elements (J. Hansen).
  What do we need to get out of critical path with this WU? (R. Jones/B Dehning).