## Slide 1: The CERN-MEDICIS project MEDICIS-PROMED kick off 21 April 2015
Stefano Marzari EN-STI-RBS
Keith Kershaw EN-STI-TCD

## Slide 2: Contents :
M E D I C I S
Medical Isotopes Collected from ISOLDE
How ISOLDE produces Isotopes
The MEDICIS idea
Main constraints on the project
Time line
Conclusions

## Slide 3
We are here
ISOLDE
CERN site Meyrin
ISOLDE site since 1992 and future MEDICIS facility

## Slide 4
ISOLDE experimental hall
ISOLDE Target area
ISOLDE Class A laboratory
CERN-MEDICIS project
ISOLDE Area
Swiss – French border

## Slide 5
The ISOLDE facility
in the CERN Proton Accelerator scheme
CERN-MEDICIS
LINAC 2
BOOSTER
ISOLDE
PROTON 1.4 GeV, 2uA, delivery to ISOLDE

## Slide 6
Isotopes for ISOLDE
CERN-MEDICIS principle:
Use protons (~90%) normally lost into the Beam Dump
ISOLDE Target
Protons 1.4 GeV
Isotopes production
MEDICIS Target
ZOOM
Beam dump

## Slide 7
Target Manufacture
(workshop)
Characterization test
(workshop)
Irradiation
(ISOLDE)
Isotope extraction
(MEDICIS)
Decay storage
(MEDICIS)
Dismantling
(Hot Cell)
Disposal
(PSI)
Isotope separation
(MEDICIS)
Isotope collection
(MEDICIS)
Isotope purification
(MEDICIS)
QA – packaging & shipping
2. TARGET life
1. ISOTOPE production
We have 2 main
PROCESSES :
Remote handling
(Robot or Monorail)
Manual handling

## Slide 8
Constraints on the MEDICIS Project
A) SAFETY: radiation and contamination risk
  Targets become radioactive / collected isotopes are radioactive :
  Radiation => shielding
  Contamination containment => nuclear ventilation
  Storage area for Target cool down
  Remote handling of targets
  Personnel Access control
  Provision in the lab for safe packaging and dispatch
B) MEDICIS must not disrupt ISOLDE operation
  All civil engineering and ventilation work had to be completed to a tight schedule during Isolde shut-down (2013 – 2014)
  MEDICIS operation must not interfere with ISOLDE physics

## Slide 9
ISOLDE buildings
Extension for MEDICIS
ISOLDE and MEDICIS irradiation points
MEDICIS Laboratory
Monorail for Target transport
Robot
Future Hot cell
Mass separator
Chemical lab (purification)
Quality control and shipping
Radioactive target storage
New nuclear ventilation
Additional shielding
Fire doors (new fire sector)
MEDICIS general layout :

## Slide 10: Handling: Robots and monorail working together…

## Slide 11: What we already did in this time…
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Time line (up to now):
Building
Shielding
Irradiation point
Ventilation system
Building connection
Robot installation and shielded doors (partially)

## Slide 12: Ground breaking ceremony 4.9.2013
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 13: Earth works: Move electrical services and 4000m3 earth removal
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Drilling machine for soil analysis by RP

## Slide 14: Building: concrete foundations
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 15: Building: prefab walls & concrete
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Prefabricated walls

## Slide 16: Building: Magnetite concrete walls for shielding
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Magnetite ore
Preparation
Magnetite concrete high density 3.9 kg/dm3 (normal concrete 2.2 kg/dm3)

## Slide 17: Building: Concrete roof, technical room for CV (ventilation) and lasers
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 18: Building: External walls, water tightness & thermal insulation
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 19: Building: Re-cover with earth~3000 m3
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 

## Slide 20: Internal: irradiation point and RCS (rail conveyor system)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Proton Beam
60 kV
Cover earthed
Tested with protons:
A success !
Design by M. Vagnoni
Test

## Slide 21: Internal: shielding (temporary and permanent)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
22m3 blocks (magnetite, iron, concrete and barite).
42m3 of Magnetite ore temporary (by blowing)
<0.5 uSv/h during 2014 Isolde operation
End of shut down
ISOLDE start up
Shielding Fluka optimization by Ricardo Augusto

## Slide 22: Building: external finishing and doors (fire, ventilation & sound insulation for CV technical room)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Many thanks to:
GS-SE-DOP

## Slide 23: Ventilation & connection between old and new building
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Building connections
CV room (aspiration and filters)
CV room (controls)
Many thanks to:
CERN CV group and
MEDICIS Laboratory

## Slide 24: Internal: Robot rail and shielded door
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Shielded door C:
(K. Kershaw)
Robot rail (J-L. Grenard)

## Slide 25: Next steps in this time period
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Time line (next steps) :
Finalize Handling Robot & monorail
Finalize Shielded doors
Off-line separator
Tests and final commissioning

## Slide 26: Robot & shielded doors & storage shelves finalization
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Robot already delivered (J-L. Grenard)
Shielded doors A & B:
(K. Kershaw)
Storage shelves (V. Barozier & Y.Gavrikov)

## Slide 27: Rail conveyor system and shielding completion & ventilation air lock
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Radiation Hard conveyor
Final RCS network
Design by M. Vagnoni
Air lock
Shielding completion

## Slide 28: Frontend, separator, collection box and services (HV, control, vacuum)
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Power supply & HV
Vacuum &
Gas storage
Controls
Target station & separator
Separator (KU-Leuven)
Collection box

## Slide 29: Laboratory equipment
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Glove boxes
Fume hoods

## Slide 30: Final commissioning & start up…
9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2013 |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  | 
Tests:
Handling (robot & conveyor)
Off line device (Frontend, separator, collection)
Access system
Safety monitoring (environment, radioprotection)
General safety (power cut, fire, ventilation…)

## Slide 31
Civil engineering schedule in the 2013-2014 long shut down was extremely tight
=> Building finished on time !
The 2015 shut down was also challenging with the new ventilation system and building integration
=> Ventilation close to completion !
Luckily for this project we benefit from 50 years previous experience at ISOLDE :
  i.e. Design inputs, risk analysis, ISOLDE operations and target production…
  Industrial Kuka robots and failure risk analysis (like ISOLDE)
  Front End, separator design and process (like ISOLDE)
Conclusions :

## Slide 32
Acknowledgements !
Roland Arnoul, Ricardo Augusto, Roger Barlow, Vincent Barozier, Michele Battistin, Ana-Paula Bernardes, Michel Bonnet, Alexandre Broche, Francesco Canepa, Richard Catherall, Michal Czech, Mathieu Deschamps, Alexandre Dorsival, Yury Gavrikov, Jean-Louis Grenard, Ielyzaveta Kobzeva, Camille Lemesre, Roberto Losito, Christophe Loup, Yisel Martinez, Christophe Mitifiot, Frank Moro, Rene Necca, Julien Parra-Lopez, Eliseo Perez-Duenas, Andrea Polato, Giacomo Potuto, Silvain Samson, Eva Sanchez, Christelle Saury, Alexander Stadler, Thierry Stora, Matteo Vagnoni, Francesco Venturini, Joachim Vollaire
THANKS for your Attention !