## Slide 1
BI LIU-PS review
Topics covered:
New Fast Wire-Scanners
Wire-Scanner with 40 MHz acquisition mode
BGI
BLM “standard” in the ring
BLM “fast” (diamond detector)
Injection SEM grid
Ring SEM + Turn by Turn
WCM
Fast BPM in the ring (wide-band pickup)
BPM in TT2 (high wideband)
Conclusions

## Slide 2: New Fast Wire-Scanners
Status
  Budget : 0 (used) / 500.000 CHF (available)
  SPS prototype (chamber + mechanics) installed and being characterized
Plans
  Prototype electronics (SPS) end-of-year 2015
  Budget might be revised
  5 units to be produced for the PS 2017-2018
  Installation in 2019
  PSB specification being written by B. Holzer then PS

## Slide 3: Wire-Scanner 40Mhz acq. mode
Status
  Budget : 10.000 / 9.500 CHF
  2 cables pulled and plugged + patch panel
Plans
  Test with software to be done
  Analog part (cable in the tunnel) being tested
  Digital part : cable 40Mhz to be plugged, FESA server to be ready, test end-of-year 2015

## Slide 4: BGI
Status
  Budget : 89.650 / 460.000 CHF
  Design ongoing
  Request for a technical student accepted → convert to a PhD student instead (2016)
  Request for a VIA by BI-SW accepted
Plans
  No ECR yet
  a. End-of-year 2015 tank installation (blank flange)
  b. If a. then magnet installation
  c. If b. then installation of the instrument

## Slide 5: BLM “standard” in the ring
Status
  Budget : 0 / 250.000 CHF (electronics)
  Solution for a ionization support found (W. Andreazza)
Plans
  Budget : 250.000 CHF requested to cover the total budget
  Installation 2019
  Unused cables to be taken out
  Specification document from R. Steerenberg
  ECR for cables in preparation

## Slide 6: BLM “fast” (diamond)
Status
  Budget : 87400 / 312.600 CHF
  Devices ordered and delivered (16 + 2)
  Cable requested to EN-EL(end of year 2015?)
  Acquisition controlled by OASIS
Plans
  Cable pulled end of year 2015?
  If cable installed then installation of the detectors

## Slide 7: Injection SEM grid
Status
  Budget : 0 / 100.000 CHF
  Vacuum chamber ready end 2015 (Jan Hansen)
  Chamber space for BI reserved
  Drawing done (C. Vuitton)
  Same grid but different mechanical system
Plans
  Shielding around the grid (protection)
  Analysis to be done by B. Salvant (impedance)
  OK for 2017

## Slide 8: Ring SEMs + Turn by Turn
Status
  Budget : 0 / 200.000 CHF
  Prototype electronic ADC ready October (same as PSB)
  Old system to be replaced (consolidation)
  Same cables
Plans
  Budget to be lowered (100K → BLM?)
  Validation of the new electronic
  Investigation where to put the electronic crate

## Slide 9: WCM
Status
  Budget : 150.000 (80.000 + 70.000 Guzik) / 185.500 CHF
  2 devices ready to be installed
  IEFC decision not to install because of the WCM outgassing rate that could interfere with ion operation
Plans
  Installation end-of-year
  New ECR to be created
  Ghost detection 50ns → Quality bunch rotation + splitting (25ns)
  Attenuation + protection electronic operational? (RF+CO)
  OASIS card to eventually replace Guzik (→ SPS LIU Budget)
  Request for a vacuum valve + jacket etuvage

## Slide 10: Fast BPM in the ring (wide-band)
Status
  Budget : 13.800 / 25.000 CHF
  In production
  ECR sent
Plans
  Installation end-of-year

## Slide 11: BPM in TT2 (high wideband)
Status
  Budget : 900 / 16.700 CHF
  Device FT16.UDC314 moved
  4 new cables pulled
Plans
  Project terminated
  15800 CHF available

## Slide 12: Conclusions
Fast WS prototype tests (electronics + mechanics)
Budget “standard” BLM to be extended (+250KCHF)
Diamond BLM ready to be used in 2016
Electronics for the SEM turn by turn to be tested in October 2015
WCM installation pending + validation of an attenuation/protection electronic circuit