## Slide 1: North Area Consolidation: meeting 1
S. Evrard, EN-MEF
18.06.2015

## Slide 2: Content
Introduction / Attendance
Identification and selection of activities*
Procedure*
Consolidation documentation
Consolidation activities in 2015
Next steps
Recap
* Selection of slides presented by M. Benedikt @ LMC on 29. April 2015.

## Slide 3: Introduction
Consolidation project for the PS East Area and SPS North Area is included in the general CERN Accelerator Consolidation Project
Clearly the requests exceed the allocated budget, need to do a selection
Coordination Team (S. Evrard - M. Wilhelmsson) to follow the activities and budget.
  Define work-packages for each activity, collect all relevant information from the work package holders
  Check that all work activities are documented in detail following the quality assurance plan
  Schedule and follow the activities, ensuring the compatibility of the beam operations and available manpower
  Work-package meetings along with YETS/EYETS planning meetings to discuss the details
  Regular report to EATM

## Slide 4: Attendance
First name Surname | Group | First name Surname | Group
Jens Spanggaard | BE-BI | Adrian Fabich | EN-MEF
Oscar Andujar | BE-OP | Ilias Efthymiopoulos | EN-MEF
James Ridewood | BE-OP | Mats Wilhelmsson | EN-MEF
Eduard Feldbaumer | DGS-RP | Lau Gatignon | EN-MEF
Jean-paul Jullien | DGS-SEE | Sylvain Girod | EN-MEF
Bill Bannister | EN-CV | Damien Grenier | EN-STI
Jani Lehtinen | EN-CV | Didier Vaxelaire | GS-ASE
James Dilwyn Devine | EN-EL | Frederic Magnin | GS-SE
Emmanuelle Delachenal | EN-GMS | Maryse Da Costa | IT-CS
Oliver Boettcher | EN-HE | Jean-Paul Burnet | TE-EPC
Roberto Rinaldesi | EN-HE | Yves Gaillard | TE-EPC
Katy Foraz | EN-MEF | Pierre Dahlen | TE-MPE
Dominique Missiaen | EN-MEF | Richard Mompo | TE-MPE
Jean-Frederic Fuchs | EN-MEF | Markus Zerlauth | TE-MPE
Erwan Harrouch | EN-MEF | Philip Schwarz | TE-MSC
John Robert Etheridge | EN-MEF | Jeremie Bauche | TE-MSC
Simon Mataguez | EN-MEF | Jose Antonio Ferreira Somoza | TE-VSC

## Slide 5: Identification and selection of activities
Identification of needs and demand was done by the group owning the equipment concerned:
  Expected to be in line with LHC general priorities and requests
    via LMC meetings and group representative
  Expected to be in line with IEFC general priorities and requests
    via IEFC meetings group representative
  Expected to be in line with Upgrade projects and requests
    via group representation in projects
Request to consolidation project for financing (including consolidation documentation)
Review of all group’s requests by consolidation project
    Interaction with upgrade projects, as required.
Outcome at consolidation day with all groups present
    Information to Dep. MBs, LMC, IEFC.

## Slide 6: Procedure
CERN’s Activity Planning Tool (APT) used as central tool for handling and tracking all accelerator consolidation requests
    • All LHC, PS and SPS consolidation WUs collected in APT (~400 WUs)
    • North and East area consolidation being re-integrated
    Basic interaction takes place with Group Leaders and Department Planning officers.

## Slide 7: APT status for NA-CONS (I)
NA-CONS |  |  |  |  |  |  |  |  |  |  |  | 
18/06/2015 |  |  |  |  |  |  |  |  |  |  |  | 
Group | Projet | Statut | Budget code | Workunit description | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
EN-CV | NA-CONS | Planned | 53610 | {[P1] Chilled water piping NA} | 270 | 200 | 0 |  |  |  |  | 
 |  |  | 53597 | {[P2] Consolidation of the NA62 ventilation System} | 650 |  |  |  |  |  |  | 
 |  |  | 53598 | {NA-CONS Cooling and Ventilation in target area} | 220 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 1,140 | 200 | 0 |  |  |  |  | 
 |  | Draft 3 | 53639 | {North Area cooling towers reject water} |  |  |  |  | 0 |  |  | 
 |  | Draft 3 Total |  |  |  |  |  |  | 0 |  |  | 
 | NA-CONS Total |  |  |  | 1,140 | 200 | 0 |  | 0 |  |  | 
EN-CV Total |  |  |  |  | 1,140 | 200 | 0 |  | 0 |  |  | 
EN-MEF | NA-CONS | Planned | 63309 | {Beam line items renovation MEF} | 333 |  |  |  |  |  |  | 
 |  |  | 63308 | {Collimators renovation in the NA beamlines} | 200 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 533 |  |  |  |  |  |  | 
 | NA-CONS Total |  |  |  | 533 |  |  |  |  |  |  | 
EN-MEF Total |  |  |  |  | 533 |  |  |  |  |  |  | 
EN-STI | NA-CONS | Planned | 63310 | {Production target upgrade} | 190 |  |  |  |  |  |  | 
 |  |  | 63316 | {SPS North Area} | 168 |  |  |  |  |  |  | 
 |  |  | 63720 | {NI Consolidation - ATB movable devices} | 20 |  |  |  |  |  |  | 
 |  |  | 63311 | {Collimator TCSC} | 385 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 763 |  |  |  |  |  |  | 
 | NA-CONS Total |  |  |  | 763 |  |  |  |  |  |  | 
EN-STI Total |  |  |  |  | 763 |  |  |  |  |  |  | 
DGS-RP | NA-CONS | Planned | 57399 | {RP North Area} |  | 202 |  |  |  |  |  | 
 |  | Planned Total |  |  |  | 202 |  |  |  |  |  | 
 | NA-CONS Total |  |  |  |  | 202 |  |  |  |  |  | 
DGS-RP Total |  |  |  |  |  | 202 |  |  |  |  |  | 
GS-ASE | NA-CONS | Planned | 72188 | {Detection systems} | 2 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 2 |  |  |  |  |  |  | 
 |  | Draft 3 | 22125 | {Exp. Areas access control - Test platform} | 160 | 350 | 350 | 350 | 350 |  |  | 
 |  | Draft 3 Total |  |  | 160 | 350 | 350 | 350 | 350 |  |  | 
 | NA-CONS Total |  |  |  | 162 | 350 | 350 | 350 | 350 |  |  | 
GS-ASE Total |  |  |  |  | 162 | 350 | 350 | 350 | 350 |  |  | 
Grand Total |  |  |  |  | 4,296 | 948 | 547 | 843 | 350 | 300 | 300 | 300
Planned – approved activities |  |  |  |  |  |  |  |  |  |  |  | 
Draft 3 – activities reviewed by the PL and to be approved as soon as the budget is available |  |  |  |  |  |  |  |  |  |  |  | 
Draft 4 – new activities to be assessed by the PL |  |  |  |  |  |  |  |  |  |  |  | 
Draft 5 – activities reviewed by the PL and not approved – kept for the traceability |  |  |  |  |  |  |  |  |  |  |  | 
Has just been updated for 2015

## Slide 8: APT status for NA-CONS (II)
NA-CONS |  |  |  |  |  |  |  |  |  |  |  | 
18/06/2015 |  |  |  |  |  |  |  |  |  |  |  | 
Group | Projet | Statut | Budget code | Workunit description | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
TE-EPC | NA-CONS | Active | 99630 | {[P]; Renovation of power converters} | 975 | 0 | 0 | 0 | 0 | 0 |  | 
 |  | Active Total |  |  | 975 | 0 | 0 | 0 | 0 | 0 |  | 
 | NA-CONS Total |  |  |  | 975 | 0 | 0 | 0 | 0 | 0 |  | 
TE-EPC Total |  |  |  |  | 975 | 0 | 0 | 0 | 0 | 0 |  | 
TE-MPE | NA-CONS | Draft 3 | 22130 | {[P3] WIC for TLs to SPS (TT2 & TT10)} |  |  |  |  |  | 300 | 300 | 300
 |  | Draft 3 Total |  |  |  |  |  |  |  | 300 | 300 | 300
 | NA-CONS Total |  |  |  |  |  |  |  |  | 300 | 300 | 300
TE-MPE Total |  |  |  |  |  |  |  |  |  | 300 | 300 | 300
TE-MSC | NA-CONS | Draft 3 | 99177 | {[P]; Consolidation of null field probe} |  |  | 30 | 50 |  |  |  | 
 |  |  |  | {[P]; Nettoyage filtre aimants} |  |  | 17 |  |  |  |  | 
 |  |  |  | {[P]; Remise en Ã©tat Eletta} |  |  |  | 16 |  |  |  | 
 |  |  |  | {[P]; Remplacement anti-retour} |  |  |  | 69 |  |  |  | 
 |  |  |  | {[P]; Remplacement electrovanne} |  |  |  | 69 |  |  |  | 
 |  |  |  | {[P]; Remplacement interconnexion puissance} |  | 16 |  |  |  |  |  | 
 |  |  |  | {[P]; Remplacement joint raccord Walther} |  |  |  | 19 |  |  |  | 
 |  |  |  | {[P]; Renovation rack interlocks} |  | 130 | 100 | 220 |  |  |  | 
 |  | Draft 3 Total |  |  |  | 146 | 147 | 443 |  |  |  | 
 | NA-CONS Total |  |  |  |  | 146 | 147 | 443 |  |  |  | 
TE-MSC Total |  |  |  |  |  | 146 | 147 | 443 |  |  |  | 
TE-VSC | NA-CONS | Active | 97728 | {[P]; Vacuum chambers replacement + new ion pumps} |  | 50 | 50 | 50 |  |  |  | 
 |  | Active Total |  |  |  | 50 | 50 | 50 |  |  |  | 
 | NA-CONS Total |  |  |  |  | 50 | 50 | 50 |  |  |  | 
TE-VSC Total |  |  |  |  |  | 50 | 50 | 50 |  |  |  | 
BE-BI | NA-CONS | Planned | 64312 | {NA-CONS Beam instrumentation in target area} | 53 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 53 |  |  |  |  |  |  | 
 | NA-CONS Total |  |  |  | 53 |  |  |  |  |  |  | 
BE-BI Total |  |  |  |  | 53 |  |  |  |  |  |  | 
EN-EL | NA-CONS | Planned | 53654 | {NA-CONS Electric Infrastructure in target area} | 240 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 240 |  |  |  |  |  |  | 
 | NA-CONS Total |  |  |  | 240 |  |  |  |  |  |  | 
EN-EL Total |  |  |  |  | 240 |  |  |  |  |  |  | 
EN-HE | NA-CONS | Planned | 53324 | {Crane renovation EHN1} | 430 |  |  |  |  |  |  | 
 |  | Planned Total |  |  | 430 |  |  |  |  |  |  | 
 | NA-CONS Total |  |  |  | 430 |  |  |  |  |  |  | 
EN-HE Total |  |  |  |  | 430 |  |  |  |  |  |  | 
Grand Total |  |  |  |  | 4,296 | 948 | 547 | 843 | 350 | 300 | 300 | 300
Planned – approved activities |  |  |  |  |  |  |  |  |  |  |  | 
Draft 3 – activities reviewed by the PL and to be approved as soon as the budget is available |  |  |  |  |  |  |  |  |  |  |  | 
Draft 4 – new activities to be assessed by the PL |  |  |  |  |  |  |  |  |  |  |  | 
Draft 5 – activities reviewed by the PL and not approved – kept for the traceability |  |  |  |  |  |  |  |  |  |  |  | 
Ʃ = 8 MCHF
(out of 95 MCHF proposed)

## Slide 9: Consolidation documentation
Standardized EDMS documentation accompanying each consolidation request:
Context and scope of the consolidation activity
  Risk analysis description
Proposed technical solution
  Description, alternatives, replacement vs. renewal, etc.
Impact of consolidation
  Effect on future operation, maintenance needs & cost, lifetime, homogenization of equipment, safety …
Impact of implementation on other technical systems, projects and technical groups
Resource estimate
Budget estimate, personnel estimate,
Timeline with project planning and milestones
TEMPLATE is available now : https://edms.cern.ch/document/1508942/1

## Slide 10: North Area Consolidation activities in 2015
North Area Consolidation budget situation 2015 |  |  |  |  |  | 
Dep | Group | BC | Budget Code Description | Payment Budget (CHF) | % paid | % committed
BE | BI | 64312 | NA Target Consolidation - TBIU/D | 53,000 | 18% | 20%
DGS | RP | 57399 | RP for North Area Consolidation | 100,000 | 1% | 1%
EN | HE | 53324 | Crane renovation EHN1 | 430,000 | 0% | 95%
EN | CV | 53596 | Replacement of the ventilation units in the NA PC rooms | 0 |  | 
EN | CV | 53597 | Ventilation underground NA62 | 650,000 | 0% | 0%
EN | CV | 53598 | NA-CONS Cooling and Ventilation in target area | 220,000 | 0% | 10%
EN | CV | 53610 | Chilled water piping North Area | 270,000 | 0% | 0%
EN | EL | 53654 | NA-CONS Electric Infrastructure in target area | 240,000 | 52% | 55%
EN | MEF | 63308 | Collimators renovation in the NA beamlines | 200,000 | 0% | 11%
EN | MEF | 63309 | Beam line items renovation MEF | 333,000 | 2% | 2%
EN | STI | 63310 | Production target upgrade | 190,000 | 4% | 6%
EN | STI | 63311 | Collimator TCSC | 385,000 | 5% | 7%
EN | STI | 63316 | SPS North Area | 168,000 | 4% | 27%
EN | STI | 63720 | NI Consolidation - ATB movable devices | 20,000 | 17% | 71%
GS | ASE | 72188 | Gas detection SPS exp. areas (N+W) | 2,000 | 0% | 0%
GS | SE | 76388 | North area consolidation civil engineering | 100,000 | 28% | 78%
TE | EPC | 99630 | Electronics for North Area Power Convertors | 450,000 | 0% | 10%
 |  |  |  | 3,811,000 | 5% | 23%
 | Very low commitments |  |  |  |  | 
 | High commitments |  |  |  |  | 
 | Commitments without budget |  |  |  |  | 

## Slide 11: Next steps
2015 activities: APT figures have bee updated
 All groups to carry out their planned activities
2016 activities and afterwards: clarify scope of activities, schedule ensuring the compatibility of the beam operations and available manpower.
All groups to update APT requests and document them by means of the Consolidation Work Unit template document

## Slide 12: Recap
Identification of needs and demand is done by the group owning the equipment concerned
CERN’s Activity Planning Tool (APT) = central tool for handling the requests
Basic interaction takes place with Group Leaders and Department Planning officers
Standardized EDMS documentation accompanying each consolidation request
NA consolidation meetings to be held on a monthly basis