## Slide 1: LHC Shut-down 08 Skeleton of schedule: proposal
K. Foraz

## Slide 2
Helium storage
  @ CERN : 45t (Ghe) + 12t (Lhe) + 12t (Lhe av. in Jan.08)
  Virtual : 25t
  Up to 6 sectors can be stored from January
Consolidation in sector 34
  Last dipole transported
   Cool-down to 1.9K of sectors 12 & 23
  End of works
LHC SD08 – key drivers

## Slide 3: LHC SD08 – Provisional skeleton of schedule
PT
He Purge
He Purge
Maint.
Maint.
Cool-down
He Purge
&
Warm-up
300K
He Purge
Maint.
Cool -down
He Purge
He Purge
Maint.
4
5
6
Nb of sectors
He empty
Consolidation
Consolidation
Connection cryostat (1)
HE gauges
?
Discussion to power test low current circuits in progress,
in sectors 23, 56, 78 & 81

## Slide 4
ATLAS
  Maintenance of cooling towers : wk. 79
  AUG tests : tbd within wks 79
ALICE
  Maintenance of cooling towers : wk. 24
  AUG tests : 23 January (TBC by ALICE)
CMS
  Maintenance of cooling towers : wk. 4951
  AUG tests : 10 december
LHC-B
  Maintenance of cooling towers : wk. 1214
  AUG tests : tbd within wks 1214
LHC SD08 – Proposal for maintenance